## upto_Jan09
Status on 24Feb.2009
Difference of Progress in OMMS (upto 31st Jan.2009)
No. | Division | CGM | Districts | Physical Progress | [5 empty] | Financial Progress (Payment Made) in Lakhs
|  |  |  | completed roads on OMMS | Actual | Diff. | Completed length on OMMS | Actual | Diff. | Expenditure on OMMS | Actual | Diff.
1 | Rewa | IV | Anuppur | 65 | 105 | -40 | 281.79 | 407.4565 | -125.6665 | 10729.94 | 10817.6415 | -87.7015
2 | Gwalior | I | Ashoknagar | 72 | 67 | 5 | 295.4 | 273.4958 | 21.9042 | 6172.24 | 4718.03 | 1454.21
3 | Jabalpur | IV | Balaghat | 176 | 177 | -1 | 802.76 | 813.6709 | -10.9109 | 19994.22 | 19917.1 | 77.12
4 | Indore | III | Barwani | 105 | 110 | -5 | 478.97 | 482.0778 | -3.1078 | 12243.27 | 13055.6 | -812.33
5 | Bhopal | I | Betul | 164 | 169 | -5 | 812.35 | 851.0366 | -38.6866 | 21899.22 | 22198.5604 | -299.3404
6 | Gwalior | I | Bhind | 126 | 138 | -12 | 385.97 | 462.5813 | -76.6113 | 8700.06 | 10459.85 | -1759.79
7 | Bhopal | II | Bhopal | 34 | 31 | 3 | 108.48 | 111.9005 | -3.4205 | 3080.09 | 3048.62 | 31.47
8 |  |  | Burhanpur | 16 | 20 | -4 | 68.25 | 126.4761 | -58.2261 | 2585.57 | 1061.67 | 1523.9
9 | Sagar | II | Chhatarpur | 143 | 143 | 0 | 608.89 | 617.9414 | -9.0514 | 15668.54 | 16676.834 | -1008.294
10 | Jabalpur | IV | Chhindwara | 141 | 131 | 10 | 771.5 | 794.3374 | -22.8374 | 25326.94 | 25528.0741 | -201.1341
11 | Sagar | II | Damoh | 103 | 106 | -3 | 397.59 | 411.2588 | -13.6688 | 8162.87 | 8162.866 | 0.004
12 | Gwalior | I | Datia | 69 | 60 | 9 | 305.91 | 269.3115 | 36.5985 | 4235.46 | 5643.58 | -1408.12
13 | Ujjain | III | Dewas | 90 | 86 | 4 | 395.12 | 396.5569 | -1.4369 | 11326.84 | 11274.1912 | 52.6488
14 | Indore | III | Dhar | 183 | 185 | -2 | 837.18 | 948.0163 | -110.8363 | 21842.71 | 22941.141 | -1098.431
15 | Jabalpur | IV | Dindori | 115 | 128 | -13 | 472.21 | 548.0275 | -75.8175 | 15917.89 | 16786.9 | -869.01
16 | Gwalior | I | Guna | 90 | 90 | 0 | 369.34 | 392.802 | -23.462 | 7190.25 | 9078.57 | -1888.32
17 | Gwalior | I | Gwalior | 63 | 63 | 0 | 189 | 232.9693 | -43.9693 | 4956.75 | 5175.915 | -219.165
18 | Bhopal | I | Harda | 31 | 33 | -2 | 176.51 | 219.4235 | -42.9135 | 6484.95 | 6497.22 | -12.27
19 | Bhopal | I | Hoshangabad | 109 | 95 | 14 | 331.91 | 362.0262 | -30.1162 | 9663.16 | 9690.59 | -27.43
20 | Indore | III | Indore | 37 | 37 | 0 | 131.33 | 146.6377 | -15.3077 | 3514.59 | 3492.364 | 22.226
21 | Jabalpur | IV | Jabalpur | 91 | 87 | 4 | 342.62 | 356.5505 | -13.9305 | 8067.23 | 8043.312 | 23.918
22 | Indore | III | Jhabua | 146 | 133 | 13 | 610.55 | 670.5672 | -60.0172 | 19659.11 | 20435.9205 | -776.8105
23 | Jabalpur | IV | Katni | 100 | 98 | 2 | 391.05 | 408.7519 | -17.7019 | 9057.85 | 9362.9 | -305.05
24 | Indore | III | Khandwa | 76 | 71 | 5 | 325.36 | 304.4249 | 20.9351 | 7534.04 | 9658.81 | -2124.77
25 | Indore | III | Khargone | 70 | 79 | -9 | 353.25 | 426.4778 | -73.2278 | 11682.1 | 11257.456 | 424.644
26 | Jabalpur | IV | Mandla | 175 | 194 | -19 | 807.03 | 897.7668 | -90.7368 | 18703.24 | 19049.89 | -346.65
27 | Ujjain | III | Mandsaur | 144 | 146 | -2 | 648.9 | 694.4262 | -45.5262 | 17440.13 | 18452.54 | -1012.41
28 | Gwalior | I | Morena | 243 | 244 | -1 | 778.17 | 842.2538 | -64.0838 | 18255.14 | 18692.21 | -437.07
29 | Jabalpur | IV | Narsinghpur | 77 | 79 | -2 | 317.13 | 328.7214 | -11.5914 | 8027.84 | 8013.6456 | 14.1944
30 | Ujjain | III | Neemuch | 61 | 60 | 1 | 305.98 | 304.6084 | 1.3716 | 5701.24 | 5700.12 | 1.12
31 | Sagar | II | Panna | 94 | 99 | -5 | 427.01 | 461.1105 | -34.1005 | 11993.07 | 12373.58 | -380.51
32 | Bhopal | II | Raisen | 42 | 57 | -15 | 258.73 | 352.9283 | -94.1983 | 8945.25 | 9408.91 | -463.66
33 | Bhopal | I | Rajgarh | 147 | 146 | 1 | 562.22 | 589.3807 | -27.1607 | 12778.99 | 12818.5454 | -39.5554
34 | Ujjain | III | Ratlam | 48 | 80 | -32 | 233.95 | 379.9505 | -146.0005 | 8549.78 | 11383.1523 | -2833.3723
35 | Rewa | IV | Rewa | 91 | 88 | 3 | 396.89 | 441.3043 | -44.4143 | 11503.96 | 12342.874 | -838.914
36 | Sagar | II | Sagar | 158 | 158 | 0 | 688.27 | 696.2915 | -8.0215 | 14194.71 | 14197.32 | -2.61
37 | Rewa | IV | Satna | 125 | 144 | -19 | 436.86 | 556.5244 | -119.6644 | 11631.23 | 12560.1179 | -928.8879
38 | Bhopal | II | Sehore | 63 | 114 | -51 | 284.43 | 541.9258 | -257.4958 | 16921.22 | 17002.4231 | -81.2031
39 | Jabalpur | IV | Seoni | 210 | 223 | -13 | 894.33 | 959.2053 | -64.8753 | 26332.74 | 26482.45 | -149.71
40 | Gwalior | I | Seopur | 53 | 35 | 18 | 256.74 | 221.0791 | 35.6609 | 5976.88 | 6233.56 | -256.68
41 | Rewa | IV | Shahdol | 101 | 104 | -3 | 521.75 | 523.5253 | -1.7753 | 12762.28 | 12919.142 | -156.862
42 | Ujjain | III | Shajapur | 105 | 107 | -2 | 420.97 | 475.8032 | -54.8332 | 12489.05 | 12482.6164 | 6.4336
43 | Gwalior | I | Shivpuri * | 141 | 145 | -4 | 681.28 | 745.9731 | -64.6931 | 14709.65 | 17166.79 | -2457.14
44 | Rewa | IV | Sidhi | 147 | 146 | 1 | 848.41 | 890.3525 | -41.9425 | 25259.79 | 25091.3272 | 168.4628
45 | Sagar | II | Tikamgarh | 145 | 151 | -6 | 549.1 | 582.5302 | -33.4302 | 11759.59 | 11823.959 | -64.369
46 | Ujjain | III | Ujjain | 80 | 74 | 6 | 362.92 | 366.2323 | -3.3123 | 12258.87 | 12341.508 | -82.638
47 | Rewa | IV | Umria | 36 | 51 | -15 | 227.1 | 339.4124 | -112.3124 | 7119.55 | 7172.6848 | -53.1348
48 | Bhopal | II | Vidisha | 86 | 89 | -3 | 437.45 | 482.4832 | -45.0332 | 11429.76 | 11565.92 | -136.16
|  |  |  | 4987 | 5176 | -189 | 21588.91 | 23708.5657 |  | 580439.85 | 600259.0016 | -19819.1516