## PR-1
Format PR-1
Road Wise Details of Physical /Financial Progress Position upto Month :
Package No. :- | [5 empty] | District :- |  |  |  | Probable amount of contract :- | [8 empty] | Tender Rate :
Name of Contractor :- | [9 empty] | Date of Work Order : - | [8 empty] | Actul Date of Completion :
Name of Consultant :- | [9 empty] | Stipulated date of completion :-
Road Wise Prograss Report
Sr. No. | Block | Name of Parliamentary constituency | Name of Assembly constituency | Name of road | Type of Road N/U | Length (kms) | Total Cost (lakh) (T.S.) | Physical/Financial Progress (Cumulative) | [13 empty] | Actual Date of Complition of Road | Remark
[8 empty] | Preparatory work (kms) | Earth work (kms) | GSB (kms) | WBM (G1) (kms.) | WBM (G2) (kms.) | WBM (G3) (kms.) | Shoulder Work (kms) | Tarring (kms) | Cement Concrete road (kms) | No. of CD work / completed |  |  | Cost of work done (lakh) | Amount Paid (lakh)
[17 empty] | Sanction | Completed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 | 20 | 21 | 22 | 23
Total Roads in the Package : | [7 empty] | Completed : |  |  |  | Ongoing : | [5 empty] | Unstarted :
Average Labour engaged by the Contractor for the month :

## PR-2
Format PR-2
Progress of Works for the Month of
Name of PIU -
S. No. | Phase | Package No. | DiStrict | Cost of Work Done ( Rs. Lakh) |  |  | Amount Paid ( Rs. Lakh) |  |  | Finencial Progress In % | Remarks | FINAL Yes / No
|  |  |  | Till Last month | This Month | Cumulative upto | Till Last month | This Month | Cumulative upto
1 | 2 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 13 | 15 | 16 | 17

## PR-3
Format PR-3
PIU : | [7 empty] | Month :
S.No. | Phase | Name of Packages | No of Roads Contained in the Package | Sanctioned Amount | Expenditure Made (Up to the month) | Date of Completion | Date of issue Completion Certificate by the Connsultant | Date of Final Payment Made by GM | Date of Verification by GM | If Incomple Assign Reason | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12

## PA-1
Format PA-1
Performance appraisal of Supervision Consultants Phase as on
Date of Work Order:
Parameters | Team Leader's Name: |  | Resident Engineer's Name:
| Date of Joining: |  | Date of Joining:
| Touring days: |  | Touring days :
| No. of works inspected: |  | No. of works inspected :
| Quantitative Assessment* | Remarks | Quantitative Assessment* | Remarks
Leadership traits
Technical knowledge
Organizational Capability
Physical presence in the PIU
Interaction with the PIU staff
Interaction with Contractor’s
Dispute resolution ability
Supervision of works
Frequency /Adequacy of QC tests
Submission of reports
Attention to Progress
Functioning of the Laboratory
Submission/Preparation of Bill’s
Evaluation of Contractor’s claims
Other Key Staff | No. Joined / No. Required | Overall Quantitative Assessment* | Remarks#
Assistant Resident Engineers
Assistant Material Engineers
Field Engineers
* on a scale of 1 to 10; 10 indicating the best and 1 indicating the worst. |  |  | # express briefly the main points, comments & remarks
General Manager
M.P.R.R.D.A. PIU

## PA-2
Format PA-2
Performance Appraisal of Contractor's Team
S.N. | Package No. | Team (Requirement/Joined) |  |  |  | Project Engineer's Name | Score | Material Engineer's Name | Score | Lab Technician's Name | Score | FE's Name | Score
|  | PE | ME | LT | FE
Note:1. Please send information in this format every month.
2. Please assess the performance of team member's on a scale of 1to 10, 10 idicating the best and 1 indicating the worst.
3. Please assess the performance on the basis of following criteria-
1. Presence
2. Decision making ability
3. Supervision
4. Quality control
5. Technical knowledge and ability to deliver services
6. Dispute resolution ability
7. No. of tests conducted

## PA-3
Format PA-3
Following roads were inspected by GM/Team Leader/Resident Engineer. Month………..-2004 , Phase…….
PIU………………………….. No.of days on tour…………….. No. of roads inspected………………………….
Date | Package No. | Name of the Road | Inspection Report/Observation

## PA-4(I)
Format PA-4 (I)
PIU ………………….
Distt. ………………..
(Report to be taken by GM from Consultant)
Inspection of Completed roads to ensure maintanance by Contractar
Sr. No. | Package No. | Name of Road | Name of Officer (Who Inspected Road) | Designation | Date of Inspection | Overall Condition of Road |  |  |  | Observation in Brief | Action Taken by GM |  | Remark
[6 empty] | V. Good | Good | Fair | Poor |  | Date | Report in brief
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Note : Columm 11, obsarvation contains following points :-
1. Riding surface Km.wise
2. Condition of each culvert and bridge
3. Potholes Km.wise
4. Failure of crust if obsered
5. Condition of Shoulders
6. Position of road sign boards
7. New encrochment made if any
8. Shoulders and berms are jungle free or not

## PA-4(II)
Format PA-4 (II)
PIU ………………….
Distt. ………………..
Report of GM on the maintenance of roads to be given to CGM
Sr. No. | Package No. | Name of Road | Name of Officer | Date of Inspaction | Overall condition of road in the light of inspection (Phase indicate points on which maintanance is required |  |  |  | Action Taken by GM for Maintenance |  | Remark
[5 empty] | V. Good | Good | Fair | Poor | Date | Report in brief
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12

## DPR format
Performance Appraisal of DPR Consultants as on …………….
PIU:
Name of Consultancy: |  |  | Date of Work Order:
Particulars | No. of roads | Length of roads (kms) | Stipulated Date of Completion :
Total |  |  | Date of Team Joining :
Work started in |  |  | Whether Team Leader staying at PIU (Y/N):
Work completed in |  |  | Whether C.B.R tests done in PIUs supervision (Y/N):
PPRs submitted for |  |  | Whether Laboratary established(Y/N):
Errors / Corrections in |  |  | Bills Submitted (Amt. In lakhs) :
DPRs submitted for |  |  | Payment (Amt. In lakhs) : -
Qualitative Assessment of Team Leader:
Qualitative Assessment of other staff :
Overall Assessment of the work :

## IIIB
Format III B
FORMAT FOR
Abstract of Report of State Quality Monitors for the month of ……………………….
Name of PIU: Name of SQM:
S.No. | District | Month of Visit | No. of Works Visited |  |  | Grading
[6 empty] | Poor |  |  | Average |  |  | Good |  |  | Very Good
|  |  | C | I | T | C | I | T | C | I | T | C | I | T | C | I | T
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Total District wise
Total for the Month
Instructions to fill up Format
1. This Format will be filled up District wise and Month wise.
2. Column No. 1 & 2 are self explanatory.
3. In this Format C,I & T stands for Completed work, Incomplete work and Total works.
4. In Column No. 4,5 & 6 No. of works visited should be mentioned.
5. In Column No. 7 to 18 the works graded as Poor, Average, Good and Very Good as graded by State Quality Monitor should be mentioned.
6. The Total of every District should be done and grand Total should also be done.

## IIIC
Format III C
Action Taken Statement on the Pending Reports of NQMs
Name of National Quality Monitor: Date of Inspection
S.No. | Name of Block & Name of Work | Paragraph of Report on which action required. |  | Parawise Action Taken. | Whether Action is complete (Yes/No) | If 'No' in col 6, specify the Date when the Action will be completed | Remarks/ Reasons for delay if any
|  | S.No.of Para. | Action Required
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Note: This report with signature of SQC is sent every month to NRRDA by post.
Format III C
Remarks of SQC
(Name and Signature of SQC)
Guidelines to fill up the format
1. In case of On going works, if the overall grading of work is less than “Good” and in case of completed works if overall grading of work is less then “Very Good”, the action taken report is to be prepared.
2. Separate format shall be filled up for each District.
3.Column 1 & 2 are self explanatory.
4. In Column No. 3 & 4, the serial No. of paragraphs of Report of National Quality Monitor and in short the action warranted is required to be mentioned .
5.In Column No. 5, short descriptions of the action taken should be mentioned.
6.In Column No. 6, it should be mentioned that whether the action taken is complete or not.
7. If the reply in the Column No.6 is No then in Column No. 7, the date is to be mentioned on which the action will be completed.
8.Column No. 8 may be used for remarks and reasons for delay in taking action should be mentioned.
9.The Format will be filled up by the EE/DPIU and sent to SQC. The SQC will fill up the Remark Column and forward the Report to the NRRDA.

## Format FC-1
Format : FC - 1
PIU: Quarter:
S. No. | District | No. of cases Pending at Start of Quarter | No. of Cases referred to Forest Department during quarter | No. of cases cleared by Forest Department during quarter | No. of Cases pending at the end of quarter with Forest Department
[5 empty] | <3 months | 3-6 Months | >6 Months | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9

## PT-1
Format - PT-1
M. P. Rural Road Development Authourity
Monthly Report for Physical Target and Achievement under PMGSY / ADB
Name of PIU : | [14 empty] | Month :
S. No. | Package No. | Phase | Date of Issue of Work order | Due date of Completion | Target for Reported month |  |  | Cumalative Target |  |  | Achievement in reported month |  |  | Cumalative Achievement |  |  | Remark
[5 empty] | No. Of Road | Length | No. of CD's | No. Of Road | Length | No. of CD's | No. Of Road | Length | No. of CD's | No. Of Road | Length | No. of CD's
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Note : - | Use Seprate Sheet for PMGSY / ADB Works.

## TL-1
Format TL 1
Month: |  | PIU:
Contractor | Package No. | Cost (Lakhs) | No. of roads |  |  | Length (Kms) | Date of work order | Stipulated date of completion | Date of completion | If incomplete likely date of completion
|  |  | C | I | T
Total
C- Completed, I - Incomplete, T-Total

## TL-2
Format TL 2
Technical staff of contractor
Month:
Technical Staff | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor
| Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no.
| Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed
Project Engineer
Asst. Project Engineer
Material Engineer
Asst. Material Engineer
Lab Technician
Field Engineer
Others (Pls specify)
Deployment of machinery by contractor
Equipment | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor
| Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no.
| Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed

## TL-3
Format TL 3
Milestones to be achieved (in financial terms)
Month: April, 04
Package No. | Date of work order | Months passed since work order | % Achievement as on date | 1st Quarter | 2nd Qaurter | 3rd Quarter | 4th Quarter
Example | 12.03.04 | 1 | 1.2% | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%

## TL-4
Format TL 4
Status of work
Month: PIU:
Items
| Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No.
| Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms)
Earthwork
GSB
WBM GII
WBM GIII
Hard shoulder
BT work
CD works (Nos.)
Financial Progress (In Lakhs)
Items | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No.
A. Work plan for the month
B. Progress achieved (Cumulative)
C. Progress till previous month (Cumulative)
D. Progress in this month

## TL-5
Format TL 5
Technical staff of consultant
Month:
Technical Staff | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no.
| Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed
TL
ARE
AME
FE
RE
Others (Pls specify)

## TL-6
Format TL 6
Name of Road: |  |  |  | District |  |  |  | PAC including tender %
Package No. |  |  |  | Length as per DPR
Block: |  |  |  | Actual length
PAC: |  |  |  | Above/Below percentage
|  |  | As per DPR |  |  | As paid |  |  | Variation
S.No. | SOR No. | Particulars | Quantity | Rate | Amount | Quantity | Rate | Amount | Saving | Excess
Jungle clearance
Earthwork
Ghat cutting
Select soil
Hard shoulder
GSB
G 2
G 3
CC road
Prime coat
Tack coat
Seal coat
OPGC
MPM/BM
MSS
CD work
Others if any (Pls Specify)