## CGM FA
Format : CGM FA
Financial Achievement
Month : September | [7 empty] | CGM :
S. N. | PIU | Target for the month (Rs. In Lakhs) | Achievement (Rs. In Lakhs) | % Achievement | Total Target from July 05 to March 06 (Rs. Lakhs) | Total achievement upto the month (from July 05 to September 05) Rs Lakhs | % Achievement (July 05 to September 05) | If target not achieved reasons |  |  | Measures taken by CGM to cover the gap in next month
[8 empty] | GM | Consultant | Contractor
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Balaghat | 101.98 | 72.8 | 71.3865 | 2716.39 | 151.56 | 5.5795
2 | Barwani | 101.33 | 24 | 23.685 | 2205.78 | 104.85 | 4.7534
3 | Betul | 186.23 | 112.1 | 60.1944 | 3647.82 | 300.82 | 8.2466
4 | Bhind | 97.1 | 157.6 | 162.3069 | 2109.52 | 413.19 | 19.5869
5 | Bhopal | 186.2 | 61.47 | 33.0129 | 3711.9 | 131.97 | 3.5553
6 | Chhatarpur | 213.7 | 107.5 | 50.3042 | 3770.06 | 319.53 | 8.4755
7 | Chhindwara | 121.58 | 62.9 | 51.7355 | 2370.99 | 192.23 | 8.1076
8 | Damoh | 94.39 | 26.6 | 28.181 | 1946.09 | 76.62 | 3.9371
9 | Dewas | 120.45 | 2.6 | 2.1586 | 3413.71 | 290.78 | 8.518
10 | Dhar | 149.86 | 55.7 | 37.168 | 3131.72 | 211.41 | 6.7506
11 | Guna | 127.86 | 55.6 | 43.4851 | 1870.13 | 171.57 | 9.1742
12 | Gwalior | 50 | 37.1 | 74.2 | 1770.95 | 132.41 | 7.4768
13 | Hoshangabad | 121.15 | 54.7 | 45.1506 | 3457.4 | 217.42 | 6.2885
14 | Indore | 147.81 | 30.5 | 20.6346 | 3055.26 | 112.15 | 3.6707
15 | Jabalpur | 134.29 | 55.2 | 41.1051 | 2266.45 | 145.14 | 6.4038
16 | Jhabua | 190.83 | 80.5 | 42.1841 | 3347.42 | 145.24 | 4.3389
17 | Khargone | 105.42 | 88.3 | 83.7602 | 2567.16 | 205.52 | 8.0057
18 | Mandla | 87.92 | 36 | 40.9463 | 2137.5 | 179.09 | 8.3785
19 | Mandsaur | 103.8 | 50.4 | 48.5549 | 2397.88 | 111.24 | 4.6391
20 | Morena | 157.11 | 113.6 | 72.306 | 2507.97 | 256.29 | 10.219
21 | Narsinghpur | 97.21 | 0 | 0 | 2202.83 | 40.5 | 1.8385
22 | Panna | 132.4 | 34.1 | 25.7553 | 2595.34 | 115.29 | 4.4422
23 | Raisen | 100.54 | 112.7 | 112.0947 | 1259.07 | 162.82 | 12.9318
24 | Rajgarh | 64.79 | 16.1 | 24.8495 | 1143.49 | 99.06 | 8.663
25 | Rewa | 104.8 | 20.4 | 19.4656 | 2593.11 | 60.65 | 2.3389
26 | Sagar | 82.87 | 52.9 | 63.8349 | 2311.84 | 77.24 | 3.3411
27 | Satna | 164.74 | 92 | 55.8456 | 2855.92 | 164.65 | 5.7652
28 | Seoni | 131.1 | 53 | 40.4272 | 2435.8 | 218.03 | 8.9511
29 | Shahdol | 104.02 | 0 | 0 | 3072.88 | 20.12 | 0.65476
30 | Shivpuri | 92.92 | 3.4 | 3.6591 | 2465.73 | 176.76 | 7.1687
31 | Sidhi | 143.58 | 93.6 | 65.1901 | 3122.65 | 175.87 | 5.6321
32 | Tikamgarh | 84.08 | 21.3 | 25.333 | 1370.61 | 59.56 | 4.3455
33 | Ujjain | 197.63 | 126.4 | 63.9579 | 4003.16 | 296.12 | 7.3972
34 | Vidisha | 99.95 | 14.5 | 14.5073 | 1898.87 | 201.46 | 10.6095
35 | Katni | 90.5 | 0 | 0 | 1678.13 | 0 | 0
36 | Dindori | 114.22 | 26.5 | 23.2008 | 2126.17 | 107.77 | 5.0687
| Total | 4404.36 | 1952.07 | 44.3213 | 91537.7 | 5844.93 | 6.3853
Signature Chief General Manager MP Rural Roads Development Authority

## CGM PP
Format : CGM PP
Physical Progress
Month : | [6 empty] | CGM :
S.N. | PIU | Total number of packages sanctioned | Total number of packages in progress | Total number of roads in progress | Number of packages completed in the reporting month | Number of roads completed in the reporting month | Total length of roads completed in the reporting month | Number of packages completed upto the reporting month (April 05 to September 05) | Number of roads completed upto the reporting month (April 05 to September 05) | Total length of roads completed upto the reporting month (April 05 to September 05) | Wheather Phase I, II and Phase III packages completed | If not, expected dates of completion (Phasewise)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TOTAL
Signature Chief General Manager MP Rural Roads Development Authority

## CGM MR
Format : CGM MR
Maintenance Report
Month : | [6 empty] | CGM :
S. N. | PIU | Total No. of packages completed | Total roads completed | No. of roads on which maintenance required | No. of roads on which maintenance work done | Estimate of expenditure incurred | If there is gap between column 5 and column 6, No. of roads to be taken for maintenance in the next month | The name of the oldest road (with date of completion) still left without maintenance
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TOTAL
Signature Chief General Manager MP Rural Roads Development Authority

## CGM PFB
Format : CGM PFB
Payment of Final Bills
Month : | [6 empty] | CGM :
S.N. | PIU | No. of packages completed | No. of packages for which final payment have been made before the reported month | No. of package for which final payment made in the month | Total packages for which final payment cleared | If final payment not made reasons for delay | The oldest completed package without final payment | Name of completed packages to be cleared in the next month
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TOTAL
Signature Chief General Manager MP Rural Roads Development Authority

## CGM PV
Format : CGM P V
Progress for PMGSY - Phase V
Month : | [7 empty] | CGM :
S.N. | PIU | Name of packages sanctioned | No. of roads in the package | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Physical progress | Expenditure made in the month (Rs. Lakhs) | Total expenditure upto the month | No. of roads on which work not started | Reasons for non start of the work
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TOTAL
Signature Chief General Manager MP Rural Roads Development Authority

## CGM ADB I-II
Format : CGM ADB I-II
Progress for PMGSY - ADB I-II
Month : | [7 empty] | CGM :
S.N. | PIU | Name of packages sanctioned | No. of roads in the package | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Physical progress | Expenditure made in the month (Rs. Lakhs) | Total expenditure upto the month | No. of roads on which work not started | Reasons for non -start of the work
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TOTAL
Signature Chief General Manager MP Rural Roads Development Authority

## CGM QC
Format: CGM QC
Quality Control
Month : | [11 empty] | CGM :
S.N | PIU | Total No. of roads |  | Ranking of completed roads |  |  |  | Ranking of incomplete roads |  |  |  | Name of block benchmark roads | Name of district benchmark roads | Number of roads inspected in the reporting month |  |  |  | No. of ATR pending
|  | Complete | Under progres | Very good | good | Fair | Poor | Very good | good | Fair | Poor |  |  | GM | Consultant | CGM | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TOTAL
Signature Chief General Manager MP Rural Roads Development Authority

## CGM MC
Format : CGM MC
Monitoring of Consultants' Work
Month : |  |  |  | CGM :
S.N | PIU | Name of consultant | Performance of consultant in the reporting month |  |  | If unsatisfactory recommendation of CGM
|  |  | Good | Satisfactory | Unsatisfactory
1 | 2 | 3 | 4 | 5 | 6 | 7
TOTAL
Signature Chief General Manager MP Rural Roads Development Authority