## Phase-I,2,3,4 (6)
PIU wise Targets for July-05 to March-06
SN | Name of Piu's | Phase | Total No. of Road | Length of Road | Sanctioned Cost | Cost of Work Done | cost including tender % | Payment Made | Balance works left | No. of Road Works Completed | Length | Hab Benefited | No. of Works under Progress | I | II | III | IV | Balnace May | Difference | TARGET-ACHIEV | MAY+ JUNE TARGET | Target for May | June |  | July-05 | Aug-05 | Sept-05 | Oct-05 | Nov-05 | Dec-05 | Jan-O |  | Jan-06 | Feb-O |  | Feb-06 | Mar-O |  | Mar-06
1 | 2 | 3 | 4 | 4 | 5 | 6 | 5 | 6 | 7 | 8 | 9 | 10 | 9 | [8 empty] | 8 | 9 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 14 | 15 |  | 15 | 16 |  | 16
1 | Balaghat | 0 | 88 | 449 | 6348.8 | 5518.3 | 3169.2642 | 5659.8 | 1039.6642 | 49 | 279.19 | 96 | 39 | 0 | 41 | 8 | 0 | 1206.1742 | 166.51 | 145.3893 | 311.8993 | 155.9496 | 155.9496 | 27.7517 | 133.9664 | 101.9832 | 101.9832 | 203.9664 | 207.9328 | 207.9328 | 81.8993 |  | 81.8993 | 0 |  | 0 | 0 | 0 | 0
2 | Barwani | 0 | 44 | 290.025 | 4853.266 | 2893.64 | 2844.25 | 3046 | 1626.55 | 24 | 152.7 | 37 | 20 | 7 | 14 | 3 | 0 | 1803.09 | 176.54 | 200.074 | 376.614 | 188.307 | 188.307 | 42.045 | 126.9795 | 101.3275 | 101.3275 | 192.655 | 233.959 | 269.6345 | 210.9385 |  | 210.9385 | 222.702 |  | 222.702 | 167.0265 | 0 | 167.0265
3 | Betul | 0 | 69 | 429.11 | 6982.8 | 4437.08 | 6583.4469 | 4752.6 | 2192.9269 | 34 | 219.943 | 94 | 35 | 4 | 18 | 11 | 1 | 2523.4169 | 330.49 | 134.4134 | 464.9034 | 232.4517 | 232.4517 | 76.6208 | 142.8053 | 139.6463 | 139.6463 | 249.2927 | 245.6107 | 342.098 | 258.416 |  | 258.416 | 385.9494 |  | 385.9494 | 289.462 | 0 | 289.462
4 | Bhind | 0 | 80 | 240.723 | 4237.7395 | 2740.38 | 2795.55 | 2673.9 | 1341.95 | 48 | 136.215 | 58 | 32 | 12 | 19 | 9 | 8 | 1437.5 | 95.55 | 207.814 | 303.364 | 151.682 | 151.682 | 23.45 | 104.5845 | 97.0975 | 97.0975 | 154.195 | 169.169 | 218.7795 | 153.7535 | 50 | 203.7535 | 198.442 |  | 198.442 | 148.8315 | 50 | 98.8315
5 | Bhopal | 0 | 63 | 78.49 | 4751.29 | 997.06 | 5171.17 | 3790.4 | 2280.68 | 32 | 53.68 | 39 | 31 | 19 | 5 | 8 | 0 | 3155.64 | 874.96 | -399.608 | 475.352 | 237.676 | 237.676 | 216.1767 | 143.642 | 134.034 | 134.034 | 228.068 | 247.284 | 351.71 | 310.926 |  | 310.926 | 417.704 |  | 417.704 | 313.278 | 0 | 313.278
6 | Chhatarpur | 0 | 79 | 368.71 | 6137.13 | 3298.54 | 5673.2 | 3306.3 | 2740.95 | 35 | 117.96 | 45 | 43 | 14 | 21 | 0 | 0 | 2866.65 | 294.22 | 282.592 | 576.812 | 288.406 | 288.406 | 73.555 | 166.3585 | 172.0475 | 172.0475 | 274.095 | 302.717 | 425.4535 | 369.0755 |  | 369.0755 | 490.946 |  | 490.946 | 368.2095 | 0 | 368.2095
7 | Chhindwara | 0 | 72 | 438.86 | 9138.0695 | 6413.9124 | 4873.32 | 6648.1 | 1585.52 | 50 | 283.11 | 101 | 22 | 16 | 17 | 14 | 3 | 1979.701 | 394.181 | -39.648 | 354.533 | 177.2665 | 177.2665 | 91.3477 | 127.9905 | 119.276 | 121.576 | 158.552 | 195.981 | 256.5425 | 181.6715 | 50 | 231.6715 | 242.246 |  | 242.246 | 181.6845 | 50 | 131.6845
8 | Damoh | 0 | 70 | 229.795 | 4263.873 | 3215.28 | 4654.97 | 3335.1 | 1319.87 | 34 | 120.581 | 59 | 36 | 0 | 29 | 5 | 0 | 1539.72 | 219.85 | 70.231 | 290.081 | 145.0405 | 145.0405 | 52.7175 | 104.047 | 90.9935 | 94.3935 | 131.987 | 158.094 | 211.034 | 158.741 | 50 | 208.741 | 211.76 |  | 211.76 | 158.82 | 50 | 108.82
9 | Dewas | 0 | 120 | 275.452 | 7903.54 | 4220.66 | 6022.33 | 8349.8 | 1684.93 | 92 | 223.525 | 79 | 28 | 16 | 37 | 22 | 17 | 3197.38 | 1512.45 | -1143.391 | 369.059 | 184.5295 | 184.5295 | 274.8917 | 125.283 | 119.2465 | 120.4465 | 168.493 | 200.566 | 268.776 | 204.649 |  | 204.649 | 272.84 |  | 272.84 | 204.63 | 0 | 204.63
10 | Dhar | 0 | 94 | 511.365 | 8760.1505 | 6590.31 | 5298.98 | 6771.7 | 1653.28 | 62 | 342.835 | 99 | 32 | 8 | 30 | 17 | 7 | 2006.08 | 352.8 | 143.184 | 495.984 | 247.992 | 247.992 | 58.8 | 205.328 | 142.664 | 149.864 | 265.328 | 330.656 | 330.656 | 228.784 |  | 228.784 | 0 |  | 0 | 0 | 0 | 0
11 | Dindori | 0 | 59 | 244.192 | 4422.79 | 2825.33 | 2652.59 | 3021.29 | 1352.33 | 42 | 170.97 | 58 | 17 | 12 | 16 | 12 | 2 | 1548.31 | 195.98 | 110.034 | 306.014 | 153.007 | 153.007 | 47.2442 | 105.3905 | 107.6165 | 114.2165 | 195.233 | 200.781 | 220.6235 | 59.5715 | 139.57 | 199.1415 | 199.37 | -80 | 119.37 | 59.37 | 59.57 | 0.2
12 | Guna | 0 | 68 | 252.761 | 5882.66 | 4652.28 | 2750.93 | 4724.4 | 535.83 | 54 | 253.639 | 64 | 14 | 19 | 19 | 11 | 5 | 722.231 | 186.401 | -25.652 | 160.749 | 80.3745 | 80.3745 | 31.0668 | 103.583 | 76.7915 | 76.7915 | 64.283 | 107.166 | 107.166 | 0.049 |  | 0.049 | 0 |  | 0 | 0 | 0 | 0
13 | Gwalior | 0 | 77 | 134.777 | 3458.05 | 1859.4 | 2439.21 | 3253 | 999.91 | 48 | 84.715 | 47 | 29 | 25 | 18 | 5 | 0 | 1345.15 | 345.24 | -45.267 | 299.973 | 149.9865 | 149.9865 | 57.54 | 63.166 | 49.9955 | 49.9955 | 99.991 | 126.332 | 163.157 | 189.498 | 20 | 209.498 | 147.3 | 50 | 197.3 | 110.475 | 70 | 40.475
14 | Hoshangabad | 0 | 95 | 288.816 | 6903.89 | 4203.08 | 5248.85 | 6356.1 | 1942.95 | 66 | 163.94 | 69 | 29 | 5 | 43 | 16 | 2 | 2883.18 | 940.23 | -523.645 | 416.585 | 208.2925 | 208.2925 | 197.5175 | 131.145 | 117.1475 | 121.1475 | 194.295 | 222.29 | 305.44 | 269.435 |  | 269.435 | 332.6 |  | 332.6 | 249.45 | 0 | 249.45
15 | Indore | 0 | 101 | 110.47 | 4811.32 | 1673.64 | 3738.76 | 5022.2 | 1756.26 | 72 | 85.105 | 28 | 28 | 15 | 35 | 21 | 1 | 2803.74 | 1047.48 | -645.676 | 401.804 | 200.902 | 200.902 | 181.7692 | 153.089 | 147.813 | 147.813 | 175.626 | 226.178 | 288.715 | 179.267 | 30 | 209.267 | 250.148 |  | 250.148 | 187.611 | 30 | 157.611
16 | Jabalpur | 0 | 60 | 259.542 | 4615.281 | 3112.98 | 4130.3 | 3057.85 | 1685.83 | 33 | 134.56 | 63 | 27 | 10 | 13 | 6 | 4 | 1711.2628 | 145.5272 | 284.6708 | 430.198 | 215.099 | 215.099 | 26.047 | 150.8075 | 134.2915 | 134.2915 | 208.583 | 261.615 | 299.3905 | 232.4225 |  | 232.4225 | 151.102 | 50 | 201.102 | 113.3265 | 50 | 63.3265
17 | Jhabua | 0 | 89 | 421.676 | 7313.816 | 4377.63 | 3848.02 | 4431.2 | 1697.62 | 58 | 260.42 | 93 | 31 | 11 | 24 | 19 | 4 | 1904.97 | 207.35 | 301.936 | 509.286 | 254.643 | 254.643 | 34.5583 | 229.762 | 144.881 | 144.881 | 269.762 | 339.524 | 339.524 | 229.286 |  | 229.286 | 0 |  | 0 | 0 | 0 | 0
18 | Katni | 0 | 38 | 214.612 | 3689.37 | 2053.89 | 3464.68 | 2254.74 | 1209.94 | 7 | 42.591 | 15 | 31 | 0 | 3 | 4 | 0 | 1403.09 | 193.15 | 115.186 | 308.336 | 154.168 | 154.168 | 40.8625 | 113.671 | 90.497 | 90.497 | 200.994 | 207.342 | 214.665 | 101.013 | 61.97 | 162.983 | 109.292 |  | 109.292 | 81.969 | 61.97 | 19.999 | 162.98
19 | Khargone | 0 | 58 | 344.505 | 5967.35 | 3338.61 | 3417.31 | 3446.21 | 1708.4 | 41 | 209.93 | 67 | 17 | 14 | 16 | 11 | 0 | 1953.41 | 245.01 | 138.795 | 383.805 | 191.9025 | 191.9025 | 61.2525 | 136.4825 | 105.42 | 105.42 | 200.84 | 212.965 | 277.3225 | 219.4475 |  | 219.4475 | 257.43 |  | 257.43 | 193.0725 | 0 | 193.0725
20 | Mandla | 0 | 64 | 376.5 | 5744.62 | 3775.77 | 4126.375 | 3969.52 | 1558.39 | 26 | 167.84 | 58 | 18 | 5 | 0 | 16 | 5 | 1796.215 | 237.825 | 104.56 | 342.385 | 171.1925 | 171.1925 | 48.6725 | 103.273 | 87.9195 | 87.9195 | 185.839 | 186.546 | 249.112 | 219.819 |  | 219.819 | 250.264 |  | 250.264 | 187.698 | 0 | 187.698
21 | Mandsaur | 0 | 62 | 197.785 | 4782.7 | 2481.83 | 3307.85 | 4165 | 1276.05 | 47 | 124.67 | 52 | 15 | 17 | 18 | 11 | 1 | 1974.05 | 698 | -403.08 | 294.92 | 147.46 | 147.46 | 121.4275 | 103.6575 | 103.8025 | 103.8025 | 146.705 | 167.315 | 211.2625 | 131.8725 | 70 | 201.8725 | 175.79 | 30 | 205.79 | 131.8425 | 100 | 31.8425
22 | Morena | 0 | 78 | 282.374 | 5087.005 | 3331.06 | 3019.55 | 3585.3 | 1138.75 | 53 | 197.34 | 71 | 25 | 13 | 23 | 10 | 7 | 1416.18 | 307.43 | 25.195 | 332.625 | 166.3125 | 166.3125 | 51.2383 | 160.875 | 105.4375 | 145.4375 | 110.875 | 221.75 | 221.75 | 112.625 |  | 112.625 | 0 |  | 0 | 0 | 0 | 0
23 | Narsinghpur | 0 | 58 | 217.691 | 3817.8368 | 2349.2 | 3904.23 | 2560.04 | 1344.19 | 29 | 114.207 | 48 | 29 | 0 | 23 | 6 | 0 | 1405.91 | 384.32 | -45.754 | 338.566 | 169.283 | 169.283 | 76.9883 | 132.0735 | 97.2095 | 97.2095 | 194.419 | 204.147 | 236.4925 | 156.2205 | 50 | 206.2205 | 129.382 | 47.04 | 176.422 | 97.0365 | 97.04 | -0.0035
24 | Panna | 0 | 49 | 230.745 | 3682.1265 | 2100.19 | 3940.65 | 2357.25 | 1583.4 | 6 | 40.8 | 13 | 43 | 2 | 4 | 0 | 0 | 1840.46 | 257.06 | 207.58 | 464.64 | 225.5475 | 239.0925 | 48.355 | 138.77 | 102.3975 | 102.3975 | 194.795 | 227.94 | 243.765 | 156.91 | 50 | 206.91 | 183.3 | 20 | 203.3 | 137.475 | 70 | 67.475
25 | Raisen | 0 | 36 | 250.76 | 4639.5503 | 3723.12 | 4568.58 | 3891.51 | 677.07 | 21 | 143.31 | 73 | 15 | 5 | 11 | 4 | 1 | 1003.08 | 326.01 | -59.139 | 266.871 | 128.123 | 138.748 | 51.1367 | 136.282 | 68.541 | 68.541 | 118.382 | 114.164 | 114.164 | -0.054 |  | 0 | 0 |  | 0 | 0 | 0 | 0
26 | Rajgarh | 0 | 47 | 206.145 | 3533.827 | 2736.85 | 1803.04 | 2604.1992 | 495.84 | 41 | 171.464 | 66 | 6 | 12 | 12 | 11 | 6 | 623.4795 | 127.6395 | 21.1125 | 148.752 | 74.376 | 74.376 | 21.2732 | 69.584 | 64.792 | 64.792 | 98.284 | 99.168 | 99.168 | 0.052 |  | 0.052 | 0 |  | 0 | 0 | 0 | 0
27 | Rewa | 0 | 70 | 319.126 | 4942.0075 | 3177.24 | 4155.64 | 3295.1 | 1695.94 | 32 | 155.465 | 76 | 38 | 14 | 7 | 11 | 0 | 1813.39 | 117.45 | 304.342 | 421.792 | 210.896 | 210.896 | 24.1183 | 143.199 | 104.797 | 104.797 | 209.594 | 252.198 | 295.693 | 281.197 | 0 | 281.197 | 173.98 | 30 | 203.98 | 130.485 | 30 | 100.485
28 | Sagar | 0 | 82 | 414.088 | 7063.768 | 5523.615 | 3456.97 | 5680.8 | 1257.47 | 50 | 249.472 | 84 | 32 | 21 | 24 | 5 | 0 | 1484.675 | 227.205 | 71.189 | 298.394 | 149.197 | 149.197 | 50.2938 | 106.3235 | 82.8735 | 82.8735 | 165.747 | 202.647 | 212.0705 | 128.9705 | 75 | 203.9705 | 157.694 | 43.27 | 200.964 | 118.2705 | 118.27 | 0.0005
29 | Satna | 0 | 68 | 281.951 | 4779.4757 | 2794.32 | 3359.2 | 2975.7 | 1561.95 | 29 | 108.47 | 33 | 39 | 6 | 22 | 1 | 0 | 1813.8738 | 251.9238 | 226.1062 | 478.03 | 232.0005 | 246.0295 | 36.9031 | 138.8305 | 91.083 | 91.083 | 172.166 | 209.603 | 246.9675 | 224.4045 | 0 | 224.4045 | 149.458 | 50 | 199.458 | 112.0935 | 50 | 62.0935
30 | Seoni | 0 | 59 | 338.716 | 5775.3825 | 4556.39 | 5746.24 | 4767.6 | 978.64 | 2246.93 | -2025.31 | 4362.59 | -6422.25 | 10772.84 | -14980.16 | 27998.93 | -45194.02 | 1211.16 | 486.79 | -193.198 | 293.592 | 146.796 | 146.796 | 81.1317 | 117.864 | 88.932 | 88.932 | 197.864 | 195.728 | 195.728 | 93.592 |  | 93.592 | 0 |  | 0 | 0 | 0 | 0
31 | Shahdol | 0 | 82 | 331.422 | 7033.5 | 3679.489 | 4443.69 | 5515.5 | 2080.39 | 49 | 202.346 | 69 | 32 | 10 | 24 | 11 | 4 | 2604.549 | 524.159 | -108.081 | 416.078 | 208.039 | 208.039 | 131.0397 | 104.0195 | 104.0195 | 104.0195 | 208.039 | 208.039 | 312.0585 | 312.0585 |  | 312.0585 | 416.078 |  | 416.078 | 312.0585 | 0 | 312.0585
32 | Shivpuri | 0 | 76 | 363.69 | 7543.12 | 4812.79 | 6400.76 | 6371.6 | 1258.58 | 44 | 217.07 | 66 | 32 | 16 | 17 | 10 | 1 | 1842.387 | 583.807 | -279.639 | 304.168 | 152.084 | 152.084 | 114.8662 | 139.155 | 92.929 | 92.929 | 205.858 | 178.31 | 215.013 | 77.465 | 130 | 207.465 | 146.812 | -20 | 126.812 | 110.109 | 110 | 0.109
33 | Sidhi | 0 | 62 | 361.605 | 6110.5873 | 4823.84 | 5506.41 | 4718.3 | 1546.87 | 33 | 225.74 | 87 | 29 | 10 | 13 | 8 | 2 | 1631.61 | 335 | 28.16 | 363.16 | 181.58 | 181.58 | 72.6092 | 114.2365 | 87.3435 | 87.3435 | 184.687 | 208.473 | 258.9235 | 252.7095 |  | 252.7095 | 201.802 |  | 201.802 | 151.3515 | 0 | 151.3515
34 | Tikamgarh | 0 | 57 | 205.48 | 3398.03 | 2361.58 | 1878.6 | 2327.03 | 681.6 | 35 | 138.85 | 54 | 22 | 11 | 13 | 11 | 0 | 750.26 | 68.66 | 135.82 | 204.48 | 102.24 | 102.24 | 11.4433 | 98.16 | 84.08 | 84.08 | 142.56 | 136.32 | 136.32 | 0.08 |  | 0.08 | 0 |  | 0 | 0 | 0 | 0
35 | Ujjain | 0 | 86 | 210.67 | 6716.63 | 3308.47 | 4764.77 | 6193.2 | 1634.97 | 62 | 143.808 | 57 | 24 | 13 | 28 | 10 | 11 | 2543.29 | 908.32 | -581.326 | 326.994 | 163.497 | 163.497 | 227.08 | 131.7485 | 131.7485 | 131.7485 | 203.497 | 203.497 | 245.2455 | 15.2455 | 200 | 215.2455 | 326.994 | 0 | 326.994 | 245.2455 | 200 | 45.2455
36 | Vidisha | 0 | 44 | 275.755 | 5388.426 | 3808.5846 | 3076.93 | 3787.9 | 998.93 | 401 | 1549.295 | 603 | 29 | 370 | 2915.93 | 366 | 103 | 1189.32 | 190.39 | 109.289 | 299.679 | 149.8395 | 149.8395 | 31.7317 | 99.893 | 99.9465 | 99.9465 | 99.893 | 199.786 | 199.786 | 199.679 |  | 199.679 | 0 |  | 0 | 0 | 0 | 0
| Total |  | 2504 | 10447.384 | 200479.7781 | 127766.341 | 146236.6162 | 152666.2392 | 52124.4212 | 4085.93 | 5260.446 | 7083.59 | -5453.25 | 11504.84 | -11407.23 | 28691.93 | -44999.02 | 64934.5853 | 13955.9085 | -1125.4309 | 12830.4777 | 6396.1393 | 6434.3383 | 2815.5227 | 4606.0258 | 3790.6216 | 3855.3216 | 6475.4431 | 7411.7935 | 8792.1399 | 6001.6903 | 976.54 | 6978.2843 | 6201.3854 | 220.31 | 6421.6954 | 4560.8815 |  | 3364.4315