## Sheet1
Review of packages completed but final bill not paid
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | Date of Work order | Date of Completion | Date of issue Completion Certificate | Delay in months in final payment | Date of Final bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | III | Alirajpur | Alirajpur-1 | 6 | 1925 | 2006-06-10 | 30/04/09 | 2009-09-05 | 11
2 | III | Alirajpur | Alirajpur-1 | 6 | 1918 | 2006-02-11 | 31/01/10 | 2010-02-20 | 6
3 | III | Alirajpur | Alirajpur-1 | 6 | 1919 | 18/12/06 | 31/10/09 | 2010-02-15 | 6
|  |  | Alirajpur-1 Count |  | 3
4 | II | Ashoknagar | Ashoknagar | VI | MP-1324 | 02.09.06 | 10.12.08 | 2008-12-31 | 20
5 | II | Ashoknagar | Ashoknagar | B-3 | MP-1352 | 31.12.05 | 07.10.08 | 2009-01-15 | 19
6 | II | Ashoknagar | Ashoknagar | VI | MP-1322 | 15.09.06 | 06.04.09 | 2009-07-31 | 13
7 | II | Ashoknagar | Ashoknagar | VII | MP-4726 | 02.06.07 | 04.06.09 | 2009-07-31 | 13
8 | II | Ashoknagar | Ashoknagar | VII | MP-4725 | 25.04.07 | 22.06.09 | 2009-08-20 | 12
|  |  | Ashoknagar Count |  | 5
9 | IV | Balaghat | Balaghat-1 | 8 | MP0136 | 2008-01-08 | 2010-01-31 | 2010-01-31 | 6
|  |  | Balaghat-1 Count |  | 1
10 | III | Barwani | Barwani-1 | Phase-VII | MP02-19 | 25-07-07 | 31-12-08 | 2008-12-31 | 20
11 | III | Barwani | Barwani-1 | Phase-VII | MP02-16 | 11-06-07 | 30-06-09 | 2009-06-30 | 14
12 | III | Barwani | Barwani-1 | Phase-IX | MP02-37 | 2008-02-06 | 2009-06-01 | 2009-06-01 | 14
13 | III | Barwani | Barwani-1 | Phase-IX | MP02-42 | 16-07-08 | 15-07-09 | 2009-07-15 | 13
14 | III | Barwani | Barwani-1 | Phase-IX | MP02-32 | 24-07.08 | 2010-01-01 | 2010-01-01 | 7
15 | III | Barwani | Barwani-1 | Phase-IX | MP02-38 | 2008-11-06 | 25-01-10 | 2010-01-25 | 7
16 | III | Barwani | Barwani-1 | Phase-VII | MP02-17 | 2007-10-07 | 2010-02-28 | 2010-02-28 | 6
17 | III | Barwani | Barwani-1 | Phase-IX | MP02-34 | 2008-07-17 | 2010-02-17 | 2010-02-17 | 6
|  |  | Barwani-1 Count |  | 8
18 | I | Betul | Betul-2 | VIII | MP 0366 | 18.10.2007 | 30.09.09 | 2009-09-30 | 11
19 | I | Betul | Betul-2 | B-1 | MP 0351 (ADB) Bal Work | 19.02.2009 | 30.09.09 | 2009-09-30 | 11
20 | I | Betul | Betul-2 | VIII | MP 0368 | 22.05.2008 | 15.10.09 | 2009-10-15 | 10
21 | I | Betul | Betul-2 | VIII | MP 0364 | 10.06.2008 | 31.03.10 | 2010-01-31 | 7
22 | I | Betul | Betul-2 | IX | MP 0396 | 02.05.2008 | 31.01.10 | 2010-01-31 | 7
23 | I | Betul | Betul-2 | X | MP 03109 | 09.09.2008 | 31.01.10 | 2010-01-31 | 7
24 | I | Betul | Betul-2 | VIII | MP 0369 | 12.05.2008 | 24.02.10 | 2010-02-24 | 6
|  |  | Betul-2 Count |  | 7
25 | I | Bhopal | Bhopal | IX | MP-0526 | 2008-05-13 | 2010-02-17 | 2010-02-17 | 6
|  |  | Bhopal Count |  | 1
26 | IV | Chhindwara | Chhindwara-2 | 7 | MP - 0736 | 2007-10-12 | 2009-07-16 | 2009-07-16 | 12
|  |  | Chhindwara-2 Count |  | 1
27 | I | Dewas | Dewas 1 | V | MP-1010 | 20.09.05 | 28.02.09 | 2009-04-17 | 16
28 | I | Dewas | Dewas 1 | VI | MP-1017 | 11.05.07 | 28.03.09 | 2009-04-23 | 16
29 | I | Dewas | Dewas 1 | VIII | MP-1030 | 17.03.08 | 31.03.09 | 2009-04-25 | 16
30 | I | Dewas | Dewas 1 | IX | MP-1049 | 02.03.09 | 31.01.10 | 2010-02-22 | 6
|  |  | Dewas 1 Count |  | 4
31 | III | Dhar | Dhar-3 | 10 | MP 11107 | 2009-03-02 | 2010-02-15 | 2010-02-24 | 6
|  |  | Dhar-3 Count |  | 1
32 | III | Dhar | Dhar-4 | 8 | MP-1138 | 12.05.08 | 15.01.10 | 2010-01-27 | 7
|  |  | Dhar-4 Count |  | 1
33 | II | Guna | Guna | V | MP-1315 | 2005-09-16 | 2008-01-31 | 2008-01-31 | 31
34 | II | Guna | Guna | VI | MP-1319 | 2006-06-24 | 2008-12-31 | 2008-12-31 | 20
35 | II | Guna | Guna | B-1 | MP-1351 | 2005-02-23 | 2009-03-23 | 2009-03-23 | 17
36 | II | Guna | Guna | IX | MP-1332 | 2008-05-15 | 2009-04-30 | 2009-04-30 | 16
37 | II | Guna | Guna | IX | MP-1325 | 2008-05-05 | 2009-06-30 | 2009-06-30 | 14
38 | II | Guna | Guna | III | MP-1309 (Part) | 2008-09-22 | 2009-07-31 | 2009-07-31 | 13
39 | II | Guna | Guna | IX | MP-1330 | 2008-05-05 | 2009-08-04 | 2009-08-04 | 12
|  |  | Guna Count |  | 7
40 | I | Harda | Harda | B-4 | MP-1557 | 19.09.07 | 29.06.09 | 2009-06-29 | 14
41 | I | Harda | Harda | 6 | MP-1511 | 19.09.07 | 31.12.09 | 2010-01-15 | 7
|  |  | Harda Count |  | 2
42 | I | Hoshangabad | Hoshangabad | B-2 | MP 1651 | 23.12.05 | 31.07.09 | 2009-07-31 | 13
43 | I | Hoshangabad | Hoshangabad | B-3 | MP 1652 | 29.12.05 | 29.09.09 | 2009-09-29 | 11
|  |  | Hoshangabad Count |  | 2
44 | IV | Jabalpur | Jabalpur | IX | 1829 | 2008-06-12 | 2009-11-30 | 2009-11-30 | 9
45 | IV | Jabalpur | Jabalpur | VI | 1821 | 2006-07-20 | 2010-02-10 | 2010-02-10 | 6
|  |  | Jabalpur Count |  | 2
46 | III | Jhabua | Jhabua-1 | 4 | MP -1912 | 2004-03-04 | 2008-12-30 | 2009-12-31 | 8
47 | III | Jhabua | Jhabua-1 | 8 | MP-19-42 | 2008-02-18 | 2009-08-30 | 2010-02-22 | 6
48 | III | Jhabua | Jhabua-1 | 8 | MP-19-81 | 2008-05-30 | 2009-07-31 | 2010-02-22 | 6
|  |  | Jhabua-1 Count |  | 3
49 | III | Khargone | Khargone-3 | V | 22-17 | 2006-01-19 | 2009-11-30 | 2009-11-30 | 9
|  |  | Khargone-3 Count |  | 1
50 | III | Khargone | Maheshwar | 2 | MP-2203 | 2002-04-30 | 2003-06-26 | 2003-04-24 | 88
51 | III | Khargone | Maheshwar | B-3 | MP-2253 | 2006-01-14 | 2007-11-30 | 2007-11-30 | 33
52 | III | Khargone | Maheshwar | X | MP-22143 | 2008-10-08 | 2009-03-30 | 2009-03-30 | 17
53 | III | Khargone | Maheshwar | X | MP-22141 | 2009-03-01 | 2009-08-26 | 2009-08-26 | 12
54 | III | Khargone | Maheshwar | X | MP-22158 | 2008-10-08 | 2010-01-31 | 2010-02-10 | 6
55 | III | Khargone | Maheshwar | X | MP-22134 | 2008-09-24 | 2010-03-31 | 2010-02-28 | 6
56 | III | Khargone | Maheshwar | X | MP-22139 | 2008-09-30 | 2010-02-28 | 2010-02-28 | 6
|  |  | Maheshwar Count |  | 7
57 | I | Mandsaur | Mandsaur 1 | VI | MP-24-09 | 2006-09-23 | 31.10.2008 | 2009-04-16 | 16
58 | I | Mandsaur | Mandsaur 1 | B-2 | MP-24-52 | 2006-01-24 | 31.10.2007 | 2009-04-13 | 16
59 | I | Mandsaur | Mandsaur 1 | VII | MP-24-15 | 2007-07-30 | 31.07.2008 | 2009-05-04 | 15
60 | I | Mandsaur | Mandsaur 1 | VII | MP-24-17 | 2007-06-11 | 07.11.2008 | 2009-06-22 | 14
61 | I | Mandsaur | Mandsaur 1 | VII | MP-24-16 | 2007-08-08 | 31.03.2009 | 2009-10-22 | 10
62 | I | Mandsaur | Mandsaur 1 | IX | MP-2429 | 05.06.2008 | 31.10.2009 | 2009-11-12 | 9
63 | I | Mandsaur | Mandsaur 1 | IX | MP-2433 | 28.06.2008 | 31.10.2009 | 2009-11-14 | 9
64 | I | Mandsaur | Mandsaur 1 |  | MP-24-06(A) B/W | 2005-10-14 | 15.10.2009 | 2009-12-10 | 8
65 | I | Mandsaur | Mandsaur 1 | IV | MP-24-06 B/W | 24-05-08 | 31.05.2009 | 2010-01-29 | 7
|  |  | Mandsaur 1 Count |  | 9
66 | I | Mandsaur | Mandsaur 2 | IX | 24 | 12.06.08 | 2009-12-05 | 2010-01-13 | 7
67 | I | Mandsaur | Mandsaur 2 | IX | 25 | 12.06.08 | 2010-01-06 | 2010-01-29 | 7
68 | I | Mandsaur | Mandsaur 2 | IX | 28 | 05.06.2008 | 2009-12-22 | 2010-01-09 | 7
|  |  | Mandsaur 2 Count |  | 3
69 | IV | Rewa | Mauganj | B-4 | MP-3260 | 2006-10-19 | 2009-04-15 | 2009-04-15 | 16
|  |  | Mauganj Count |  | 1
70 | II | Panna | Panna | B-4 | MP-2854 | 30.10.06 | 31.01.08 | 2008-01-31 | 31
|  |  | Panna Count |  | 1
71 | II | Panna | Pawai | VIII | MP-2820 | 13.12.07 | 26.06.09 | 2009-06-26 | 14
72 | II | Panna | Pawai | VI | MP-2816 | 28.02.07 | 04.07.09 | 2009-07-04 | 13
73 | II | Panna | Pawai | VIII | MP-2842B | 12.12.08 | 28.02.10 | 2010-02-28 | 6
|  |  | Pawai Count |  | 3
74 | I | Raisen | Raisen 1 | VI | MP 2920 | 2006-09-05 | 2009-10-30 | 2009-10-30 | 10
|  |  | Raisen 1 Count |  | 1
75 | I | Ratlam | Ratlam 2 | B-3 | MP - 3152 | 2006-01-23 | 2009-01-19 | 2009-01-19 | 19
|  |  | Ratlam 2 Count |  | 1
76 | IV | Rewa | Rewa-1 | SC | SC - 3203 | 2008-01-17 | 2008-10-31 | 2008-12-31 | 20
77 | IV | Rewa | Rewa-1 | 4 | 3213(B.W.) | 2006-09-05 | 2009-03-31 | 2009-03-31 | 17
78 | IV | Rewa | Rewa-1 | B-4 | 3257 | 2006-11-13 | 2009-03-31 | 2009-03-31 | 17
79 | IV | Rewa | Rewa-1 | 3 | 3209(B.W.) | 2007-05-05 | 2009-04-30 | 2009-04-30 | 16
80 | IV | Rewa | Rewa-1 | 8 | 3235 | 2008-01-01 | 2009-06-15 | 2009-06-15 | 14
|  |  | Rewa-1 Count |  | 5
81 | IV | Rewa | Rewa-2 | 8 | MP-3245 | 07.03.08 | 10.11.08 | 2008-11-10 | 21
|  |  | Rewa-2 Count |  | 1
82 | II | Sagar | Sagar | B-4 | 3356 | 2006-10-16 | 2009-08-31 | 2009-09-26 | 11
83 | II | Sagar | Sagar | 3 | 3310A | 2006-08-21 | 2008-10-28 | 2008-11-06 | 21
|  |  | Sagar Count |  | 2
84 | I | Sehore | Sehore-2 | 6 | MP-3517 | 2007-04-20 | 2009-01-31 | 2009-02-15 | 7
|  |  | Sehore-2 Count |  | 1
85 | III | Barwani | Sendhwa | 3 | MP-02 05 | 21.04.03 | 28.02.06 | 2006-04-30 | 52
86 | III | Barwani | Sendhwa | Phase VI | MP 02 14 | 27.08.06 | 31.03.09 | 2009-03-31 | 17
87 | III | Barwani | Sendhwa | B-3 | MP-02 55 | 18.01.06 | 10.06.07 | 2009-06-15 | 14
88 | III | Barwani | Sendhwa | B-4 | MP-02 57 | 17.08.06 | 31.01.09 | 2009-06-25 | 14
89 | III | Barwani | Sendhwa | B-4 | MP-02 58 | 17.08.06 | 20.04.08 | 2009-06-25 | 14
90 | III | Barwani | Sendhwa | Phase IX | MP 02 73 | 19.09.08 | 31.05.09 | 2009-07-31 | 13
91 | III | Barwani | Sendhwa | Phase IX | MP 02 65 | 15.07.08 | 10.07.09 | 2009-11-24 | 9
|  |  | Sendhwa Count |  | 7
92 | IV | Seoni | Seoni-1 | IX | MP-3670 | 2008-04-24 | 2009-10-15 | 2009-11-17 | 9
93 | IV | Seoni | Seoni-1 | IX | MP-36114 | 2008-05-25 | 2010-02-05 | 2010-02-20 | 6
|  |  | Seoni-1 Count |  | 2
94 | IV | Seoni | Seoni-2 | 9 | MP-3673 | 2008-05-26 | 2009-05-20 | 2009-05-20 | 15
95 | IV | Seoni | Seoni-2 | 9 | MP-3689 | 2009-03-02 | 2009-11-30 | 2009-11-30 | 9
96 | IV | Seoni | Seoni-2 | 7 | MP-3638 | 2007-07-07 | 2009-12-28 | 2009-12-30 | 8
97 | IV | Seoni | Seoni-2 | 9 | MP-3684 | 2008-07-31 | 2010-01-30 | 2010-01-30 | 7
98 | IV | Seoni | Seoni-2 | 9 | MP-3674 | 2008-05-02 | 2010-02-26 | 2010-02-26 | 6
|  |  | Seoni-2 Count |  | 5
99 | I | Shajapur | Shajapur | B-2 | MP-3951-C | 2008-02-13 | 2009-11-30 | 2010-02-22 | 6
|  |  | Shajapur Count |  | 1
100 | IV | Sidhi | Sidhi-3 | 7 | MP-4130 | 2007-08-07 | 2009-07-25 | 2009-07-20 | 13
101 | IV | Sidhi | Sidhi-3 | B-1 | MP-4151 | 2007-09-14 | 2009-07-31 | 2009-07-31 | 13
102 | IV | Sidhi | Sidhi-3 | B-4 | MP-4162 | 2006-08-28 | 2009-10-31 | 2009-10-31 | 10
|  |  | Sidhi-3 Count |  | 3
103 | I | Vidisha | Vidisha | 6 | 4515 | 2006-06-22 | 2009-07-31 | 2009-07-31 | 10
104 | I | Vidisha | Vidisha | 5 | 4514 | 2005-10-05 | 2009-08-31 | 2009-08-20 | 11
105 | I | Vidisha | Vidisha | B-3 | 4554 | 2006-01-18 | 2008-05-31 | 2009-04-20 | 15
|  |  | Vidisha Count |  | 3
|  |  | Grand Count |  | 105