## CGM FA
Format : CGM FA
Financial Achievement
Month |  | May06
S. N. | CGM | PIU | Target for the month (Rs. In Lakhs) | Achievement (Rs. In Lakhs) | % Achievement | Total Target from April 06 to Mar 07 (Rs. Lakhs) | Total achievement upto the month (from April 06 to May06) Rs Lakhs | % Achievement (April 06 to May06) | If target not achieved reasons related to |  |  | Measures taken by CGM to cover the gap in next month
[9 empty] | GM | Consultant | Contractor
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | I | Betul | 747.74 |  | 0% | 7131.49 |  | 0%
2 | I | Bhind | 196.51 |  | 0% | 3453.61 |  | 0%
3 | I | Biaora | 298.96 |  | 0% | 2934.78 |  | 0%
4 | I | Guna | 442.47 |  | 0% | 4000.85 |  | 0%
5 | I | Gwalior | 143.89 |  | 0% | 2656.66 |  | 0%
6 | I | Hoshangabad | 418 |  | 0% | 5991.13 |  | 0%
7 | I | Morena | 598.52 |  | 0% | 6614.79 |  | 0%
8 | I | Shivpuri | 342.36 |  | 0% | 6729.4 |  | 0%
|  | Total | 3188.45 | 0 | 0% | 39512.71 | 0 | 0%
9 | II | Bhopal | 485 |  | 0% | 4532 |  | 0%
10 | II | Chhatarpur | 479.96 |  | 0% | 3966.6 |  | 0%
11 | II | Damoh | 385.53 |  | 0% | 2836.66 |  | 0%
12 | II | Panna | 467.4 |  | 0% | 4543.83 |  | 0%
13 | II | Raisen | 249.49 |  | 0% | 2216.29 |  | 0%
14 | II | Sagar | 444.69 |  | 0% | 3764.16 |  | 0%
15 | II | Tikamgarh | 252.41 |  | 0% | 3658.61 |  | 0%
16 | II | Vidisha | 230.82 |  | 0% | 3936.28 |  | 0%
|  | Total | 2995.3 | 0 | 0% | 29454.43 | 0 | 0%
17 | III | Barwani | 312.62 |  | 0% | 3231.12 |  | 0%
18 | III | Dewas | 293.56 |  | 0% | 3182.51 |  | 0%
19 | III | Dhar | 666.21 |  | 0% | 7727.01 |  | 0%
20 | III | Indore | 452.58 |  | 0% | 4908.48 |  | 0%
21 | III | Jhabua | 774.53 |  | 0% | 7978.03 |  | 0%
22 | III | Khargone | 345.81 |  | 0% | 3871.45 |  | 0%
23 | III | Mandsaur | 465 |  | 0% | 5520.82 |  | 0%
24 | III | Ratlam | 209.3 |  | 0% | 2865.35 |  | 0%
25 | III | Shajapur | 385.02 |  | 0% | 3986.4 |  | 0%
26 | III | Ujjain | 399.05 |  | 0% | 5276.32 |  | 0%
|  | Total | 4303.68 | 0 | 0% | 48547.49 | 0 | 0%
27 | IV | Balaghat | 439.87 |  | 0% | 3204.5 |  | 0%
28 | IV | Chhindwara | 370.21 |  | 0% | 5124.9 |  | 0%
29 | IV | Dindori | 445.79 |  | 0% | 3661.53 |  | 0%
30 | IV | Jabalpur | 471.55 |  | 0% | 3366.8 |  | 0%
31 | IV | Katni | 269.28 |  | 0% | 2004.88 |  | 0%
32 | IV | Mandla | 462.63 |  | 0% | 6174.39 |  | 0%
33 | IV | Narsinghpur | 379.9 |  | 0% | 4350.85 |  | 0%
34 | IV | Rewa | 379.53 |  | 0% | 4698.46 |  | 0%
35 | IV | Satna | 552 |  | 0% | 4653.45 |  | 0%
36 | IV | Seoni | 618.15 |  | 0% | 6218.94 |  | 0%
37 | IV | Shahdol | 476 |  | 0% | 6710.09 |  | 0%
38 | IV | Sidhi | 709.57 |  | 0% | 6123.3 |  | 0%
|  | Total | 5574.48 | 0 | 0% | 56292.09 | 0 | 0%
|  | Grand Total | 16061.91 | 0 | 0% | 173806.72 | 0 | 0%

## CGM PP
Format : CGM PP
Physical Progress
Month: |  | May06 | Total |  |  | During the month |  |  |  | During the year |  |  | Next Month
S.N. | CGM | PIU | Total number of packages sanctioned | Total number of packages in progress | Total number of roads in progress | Number of packages completed in the reporting month | Name of packages completed in the reporting month | Number of roads completed in the reporting month | Total length of roads completed in the reporting month | Number of packages completed during the year upto the reporting month May06 | Number of roads completed during the year upto the reporting month May06 | Total length of roads completed upto the reporting month May06 | Name of packages targeted to be completed in the next month | Number of roads targeted to be completed in the next month | Length of roads targeted to be completed in the next month | Phase I, II, III packages completed - Yes / No | If No, name of incomplete package with target date to complete the packages |  |  | Remarks
[17 empty] | Ph I | Ph II | Ph III
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Yes
1 | I | Betul | [18 empty] | No
2 | I | Bhind
3 | I | Biaora
4 | I | Guna
5 | I | Gwalior
6 | I | Hoshangabad
7 | I | Morena
8 | I | Shivpuri
|  | Total | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
9 | II | Bhopal
10 | II | Chhatarpur
11 | II | Damoh
12 | II | Panna
13 | II | Raisen
14 | II | Sagar
15 | II | Tikamgarh
16 | II | Vidisha
|  | Total | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
17 | III | Barwani
18 | III | Dewas
19 | III | Dhar
20 | III | Indore
21 | III | Jhabua
22 | III | Khargone
23 | III | Mandsaur
24 | III | Ratlam
25 | III | Shajapur
26 | III | Ujjain
|  | Total | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
27 | IV | Balaghat
28 | IV | Chhindwara
29 | IV | Dindori
30 | IV | Jabalpur
31 | IV | Katni
32 | IV | Mandla
33 | IV | Narsinghpur
34 | IV | Rewa
35 | IV | Satna
36 | IV | Seoni
37 | IV | Shahdol
38 | IV | Sidhi
|  | Total | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  | Grand Total | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0

## IncompleteRoads
FORMAT : CGM - ICR
Incomplete Road Status |  |  |  | (Please fill in Col. K by selecting predefined status)
SN | PMGSY/ ADB | Phase/ Batch | CGM | Name of Distt. | Name of Block | Package No. | Name of Road | Length of Road | Status previous month | Status in the reporting month | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Status
1 | ADB | I | CGM I | Betul | Amla | MP 0351 | Kathi to Dunawa | 3.2 | G3 |  |  | BT Complete
2 | ADB | I | CGM I | Betul | Athner | MP 0351 | Bakud Jod to Khairwada | 4.8 | G2 |  |  | BT Part
3 | ADB | I | CGM I | Betul | Athner | MP 0351 | Mendha Chhindwar to Wadali | 4.7 | G2 |  |  | Completed
4 | ADB | I | CGM I | Betul | Betul | MP 0352 | Sehra to Pipla | 6.9 | G3 |  |  | E/W
5 | ADB | I | CGM I | Betul | Bhainsdehi | MP 0352 | Kaudiya Kordi to Palaspani | 1.8 | G3 |  |  | Forest - Deleted
6 | ADB | I | CGM I | Betul | Bhainsdehi | MP 0352 | BNB Rd. to Majharwani | 3.25 | G3 |  |  | G-2
7 | ADB | I | CGM I | Betul | Bhimpur | MP 0352 | Adarsh Dhanora to Kund Bakaian | 4.9 | G3 |  |  | G-3
8 | ADB | I | CGM I | Betul | P. Pattan | MP 0351 | Valani to Bisnoor | 11.2 | G2 |  |  | GSB
9 | ADB | I | CGM I | Betul | Shahpur | MP 0352 | Ghana Chikhali to Shitalihiri | 4.9 | G2 |  |  | Land Dispute
10 | ADB | III | CGM I | Betul | Athner | MP 0356 | Dehgud To Rajola | 3.5 | Earth work |  |  | Not Started
11 | ADB | III | CGM I | Betul | Athner | MP 0356 | Pandurna To Patra | 6.5 | Earth work |  |  | Other - Deleted
12 | ADB | III | CGM I | Betul | Athner | MP 0356 | Mandvi Satner To Rd Gohanda | 6.5 | Earth work |  |  | Preparatory work
13 | ADB | III | CGM I | Betul | Athner | MP 0356 | Dehgud To Dondkheda | 2.5 | Preparatory |  |  | Tendered
14 | ADB | III | CGM I | Betul | Athner | MP 0356 | Athner-Betul Road to Thani | 5.1 | Preparatory
15 | ADB | III | CGM I | Betul | Athner | MP 0356 | Athner-Bhainsdehi Road to Jamathi | 0.8 | Preparatory
16 | ADB | III | CGM I | Betul | Athner | MP 0356 | Akkalwadi to Chogarh & Mandvijod to Mandvi (Intervention) | 6.05 | Earth work
17 | ADB | III | CGM I | Betul | Athner | MP 0357 | Kawla To Satkund | 5.2 | Not start
18 | ADB | III | CGM I | Betul | Betul | MP 0353 | Sonaghati Chandbehda Rd To Jhadegaon | 3 | Earth work
19 | ADB | III | CGM I | Betul | Betul | MP 0353 | Sehra Pipla (Betul Athner)Rd To Bothisihar | 5.6 | Preparatory
20 | ADB | III | CGM I | Betul | Betul | MP 0353 | Khandara to Bodi | 4.7 | Earth work
21 | ADB | III | CGM I | Betul | Betul | MP 0353 | Paratwada Rd To Kanara | 2 | Preparatory
22 | ADB | III | CGM I | Betul | Bhainsdehi | MP 0357 | Bhainsdehi Gudgaon Rd To Jamjhiri | 5.67 | Not start
23 | ADB | III | CGM I | Betul | Bhainsdehi | MP 0357 | Koilari To Kaldongri | 8.35 | Not start
24 | ADB | III | CGM I | Betul | Bhimpur | MP 0358 | Damjipura Rd ( Batki) to Jogli | 9.55 | Not start
25 | ADB | III | CGM I | Betul | Bhimpur | MP 0358 | Mohda Guruwa Rd To Kasmarkhandi | 3.9 | Not start
26 | ADB | III | CGM I | Betul | Bhimpur | MP 0358 | Damjipura To Hidli | 6 | Not start
27 | ADB | III | CGM I | Betul | Bhimpur | MP 0358 | Mohda Guruwa road to Jadiya | 5.25 | Not start
28 | ADB | III | CGM I | Betul | Chicholi | MP 0359 | Katkuhi to Naharpur& Chicholi to PMGSY Road (Intervension) | 4.687 | GSB
29 | ADB | III | CGM I | Betul | Chicholi | MP 0359 | Chicholi-Bhimpur Road to Khairy | 1.4 | GSB
30 | ADB | III | CGM I | Betul | Chicholi | MP 0359 | Bhoura-Fopaliya Road to Khapariya | 3.6 | Earth work
31 | ADB | III | CGM I | Betul | Chicholi | MP 0359 | Khapariya to Ballor | 6.3 | GSB
32 | ADB | III | CGM I | Betul | G' Dongri | MP 0353 | Padhar To Chhuri | 2.9 | GSB
33 | ADB | III | CGM I | Betul | G' Dongri | MP 0355 | Banspur Rd to Ratamati | 1.5 | GSB
34 | ADB | III | CGM I | Betul | G' Dongri | MP 0355 | Tawa Bridge To Shoba Pur | 3 | Preparatory
35 | ADB | III | CGM I | Betul | G' Dongri | MP 0355 | NH-69 To Banjaridhal | 10.5 | GSB
36 | ADB | III | CGM I | Betul | G' Dongri | MP 0355 | Siwanpat To Dulhara | 3.5 | GSB
37 | ADB | III | CGM I | Betul | Shahpur | MP 0353 | Sitaljhiri to RampurMal | 6.7 | GSB
38 | ADB | III | CGM I | Betul | Shahpur | MP 0354 | NH-69 To Pawar Jhanda | 12 | GSB
39 | ADB | III | CGM I | Betul | Shahpur | MP 0354 | Barbatpur (Shahpur) to Silpathi | 4.4 | Preparatory
40 | ADB | III | CGM I | Betul | Shahpur | MP 0354 | Shahpur to Pathai | 3.75 | Earth work
41 | PMGSY | IV | CGM I | Betul | Athner | MP 0313 | Belkund to Gargur | 19.5 | Retender
42 | PMGSY | IV | CGM I | Betul | Bhimpur | MP 03 16 | Chohtapopti to Khairda | 19.7 | Retender
43 | PMGSY | IV | CGM I | Betul | G' Dongri | MP 0315 | Chopna Road to Bhogaikhapa | 3.5 | GSB
44 | PMGSY | IV | CGM I | Betul | Shahpur | MP 0315 | Saliment to Polapatthar | 1.9 | G3
45 | PMGSY | IV | CGM I | Betul | Shahpur | MP 0315 | Banabehra to Kachhar | 4.7 | GSB
46 | PMGSY | V | CGM I | Betul | Amla | MP 0317 | Amla-Bordehi Road to Khapakhateda | 5.42 | BT
47 | PMGSY | V | CGM I | Betul | Amla | MP 0317 | Jambada-Bordehi Road to Likhadi | 2.63 | Gsb
48 | PMGSY | V | CGM I | Betul | Amla | MP 0317 | Narera to Bordehi | 7.97 | G2
49 | PMGSY | V | CGM I | Betul | Betul | MP 0318 | Betul-Athner Road to Bharkawadi | 1.3 | G2
50 | PMGSY | V | CGM I | Betul | Betul | MP 0318 | NH-59'A' to Junawani | 5.7 | G2
51 | PMGSY | V | CGM I | Betul | Betul | MP 0318 | NH-69 to Arul | 3.2 | Preparatory
52 | PMGSY | V | CGM I | Betul | Bhainsdehi | MP 0319 | Bhainsdehi- Gudgaon Rd to Sihar | 3.05 | G2
53 | PMGSY | V | CGM I | Betul | Bhainsdehi | MP 0319 | Bhainsdehi- Khamla Rd to Badgaon | 7.75 | G3
54 | PMGSY | V | CGM I | Betul | G' Dongri | MP 0318 | Pathakheda to Bakud | 4.8 | Gsb
55 | PMGSY | V | CGM I | Betul | G' Dongri | MP 0318 | Siwanpat to Katangi | 2.65 | G2
56 | PMGSY | V | CGM I | Betul | G' Dongri | MP 0318 | Sarni Road to Chorpandra | 1.5 | G3
57 | PMGSY | V | CGM I | Betul | Multai | MP 0320 | NH-69 Saikheda to Pohar | 9.1 | G3
58 | PMGSY | V | CGM I | Betul | P. Pattan | MP 0319 | Multai-Athner Rd. to Chakora | 7.7 | Gsb
59 | PMGSY | V | CGM I | Betul | P.Pattan | MP 0320 | NH-69 to Khedi Deonala | 10.17 | BT
60 | PMGSY | III | CGM I | Bhind | Ater | MP 0406 | Phoop Pratappur Rd to Akon | 6.3 | disput
61 | PMGSY | III | CGM I | Bhind | Bhind | MP 0406 | Bhind Bhander Rd to Persona | 7.69 | disput
62 | PMGSY | IV | CGM I | Bhind | Gohad | MP 0410 | Barahead RD. To Tietone | 1.1 | G2
63 | PMGSY | V | CGM I | Bhind | Ater | MP 0414 | Bhind Ater rd to Simrao | 5.2 | Earth work
64 | PMGSY | V | CGM I | Bhind | Ater | MP 0414 | Bhind Ater rd to Jamsara | 5.85 | Earth work
65 | PMGSY | V | CGM I | Bhind | Bhind | MP 0414 | Gwalior Itawa rd to Rachhedi | 8.65 | BT
66 | PMGSY | V | CGM I | Bhind | Gohad | MP 0413 | Gwalior Etawa rd to Tundeela | 3.3 | Earth work
67 | PMGSY | V | CGM I | Bhind | Gohad | MP 0413 | Tundeela rd to Chakmadhopur | 2.25 | Earth work
68 | PMGSY | V | CGM I | Bhind | Gohad | MP 0413 | Barhead to Baknasa | 6.85 | Gsb
69 | PMGSY | V | CGM I | Bhind | Gohad | MP 0413 | Barhead to Barona | 5.85 | Earthwork
70 | PMGSY | V | CGM I | Bhind | Lahar | MP 0415 | Bhind Bhander rd to Rohinijageer | 5.8 | Gsb
71 | PMGSY | V | CGM I | Bhind | Lahar | MP 0415 | Bhind Bhander rd to Chhichawali No.2 | 0.95 | G2
72 | PMGSY | V | CGM I | Bhind | Mehgaon | MP 0413 | Kripe ka pura to Haricha | 9.03 | BT
73 | PMGSY | V | CGM I | Bhind | Mehgaon | MP 0413 | Gormi to Kripe ka pura | 6.27 | Gsb
74 | PMGSY | V | CGM I | Bhind | Mehgaon | MP 0413 | Kripe ka pura to Tikari | 4 | G3
75 | PMGSY | V | CGM I | Bhind | Roun | MP 0415 | Larol to Raipura | 2.15 | Gsb
76 | PMGSY | V | CGM I | Bhind | Roun | MP 0415 | Bonapura to Larol | 5.6 | Gsb
77 | PMGSY | V | CGM I | Bhind | Roun | MP 0415 | Mooratpura to Bagiyapura | 1.1 | Gsb
78 | PMGSY | V | CGM I | Bhind | Roun | MP 0415 | Mooratpura to Bonapura | 1.07 | G2
79 | PMGSY | V | CGM I | Bhind | Roun | MP 0415 | Uncha rd to Gudha | 4 | Gsb
80 | PMGSY | V | CGM I | Bhind | Roun | MP 0415 | Pachokhara rd to Gandh | 2.58 | Gsb
81 | ADB | II | CGM I | Datia | Seondha | MP 0951 | Indergarh Pandokhar Rd. (Rarua Jeevan) to Sikari | 4.75 | GSB
82 | ADB | II | CGM I | Datia | Seondha | MP 0951 | Indergarh Pandokhar Road (ODR) upto Rarua Jeevan | 6.05 | GSB
83 | ADB | II | CGM I | Datia | Seondha | MP 0951 | Indergarh Pandokhar Road to Lahrakalan | 6.975 | GSB
84 | ADB | III | CGM I | Datia | Datia | MP 0952 | Bhadumra road to Ghughsi via Hindora Erai | 7.33 | GSB
85 | ADB | III | CGM I | Datia | Datia | MP 0952 | Gwalior Jhansi road to Bhadumra | 9 | GSB
86 | PMGSY | III | CGM I | Datia | Seondha | MP 0904 | Kudari to Parsonda Gujar via Kherona | 5.93 | GSB
87 | PMGSY | V | CGM I | Datia | Bhander | MP 0906 | Indergarh Pandokhar Samther (ODR) Road to Bilheti | 4.269 | Gsb
88 | PMGSY | V | CGM I | Datia | Bhander | MP 0906 | Pandokhar to Samthar (ODR) | 6.55 | Earth work
89 | PMGSY | V | CGM I | Datia | Bhander | MP 0906 | Pandokhar Samthar road to Bhadepura | 5.05 | Earth work
90 | PMGSY | V | CGM I | Datia | Bhander | MP 0906 | Bhadepura road to Tori | 0.55 | Earth work
91 | PMGSY | V | CGM I | Datia | Datia | MP 0906 | Kamrari road to Khamera | 5.35 | Gsb
92 | PMGSY | V | CGM I | Datia | Datia | MP 0906 | Bilhari road to Govindpur | 1.2 | Gsb
93 | PMGSY | V | CGM I | Datia | Datia | MP 0906 | Gwalior Jhansi road to Bilhari (ODR) | 2 | G3
94 | ADB | I | CGM I | Guna | Aron | MP 1351 | Aron-Raghogarh Road to Jhajhon | 3.55 | GSB
95 | ADB | I | CGM I | Guna | Aron | MP 1351 | Aron-Panwadi Hat Road to Salay | 2.75 | GSB
96 | ADB | I | CGM I | Guna | Aron | MP 1351 | Aron-Panwadi Hat Road to Kaswamadhi | 2.7 | Earth work
97 | ADB | I | CGM I | Guna | Chachoda | MP 1351 | Sanai-Bansaheda Road to Khedikalan | 1.15 | G3
98 | ADB | I | CGM I | Guna | Chachoda | MP 1351 | Gulwada to Viryai | 6.35 | GSB
99 | ADB | I | CGM I | Guna | Chachoda | MP 1351 | Binaganj-A.B. Road to Konyakalan | 13.25 | G3
100 | ADB | I | CGM I | Guna | Isagarh | MP 1351 | Dhakoni to Patkheda | 9.9 | G3
101 | ADB | I | CGM I | Guna | Raghogarh | MP 1351 | Suthaliya to Gwarkheda | 1.3 | Earth work
102 | ADB | I | CGM I | Guna | Raghogarh | MP 1351 | Nasirpur to Shahpur | 4.1 | Earth work
103 | ADB | I | CGM I | Guna | Raghogarh | MP 1351 | Janjali to Ditalwada | 3.55 | GSB
104 | ADB | III | CGM I | Guna | Bamori | MP 1353 | Guna-Padon rd(S.H. 23) to Barban | 4.2 | Not start
105 | ADB | III | CGM I | Guna | Bamori | MP 1353 | Guna-Bamori rd (O.D.R.) to Paranth | 12.9 | GSB
106 | ADB | III | CGM I | Guna | Chanderi | MP 1352 | Chanderi-Rajghat-Nanakpur Village (S.H.) to Hirawal | 5 | Preparatory
107 | ADB | III | CGM I | Guna | Chanderi | MP 1352 | Ashoknagar-Piprai(M.D.R.) to Garenthi | 8.5 | GSB
108 | ADB | III | CGM I | Guna | Raghogarh | MP 1353 | Maksudangarh-Suthaliya (S.H.) Road to Nalkheda | 1.95 | Not start
109 | ADB | III | CGM I | Guna | Raghogarh | MP 1353 | Janjali-Banskhedi (M.D.R.) to Dhinakhedi | 2.95 | Not start
110 | ADB | III | CGM I | Guna | Raghogarh | MP 1353 | Belka-Kakwada Road to Bhulay | 1.55 | Earth work
111 | ADB | III | CGM I | Guna | Raghogarh | MP 1353 | Chainpur-Dharnawada Road to Belka-Kakwasa (Inter.) | 2.8 | G2
112 | ADB | III | CGM I | Guna | Raghogarh | MP 1353 | A.B. Road (NH 3) to Pagara | 1 | Earth work
113 | ADB | III | CGM I | Guna | Raghogarh | MP 1353 | Pagara to Purena-Pureni | 4.8 | Preparatory
114 | PMGSY | IV | CGM I | Guna | mungawali | MP 1314 | Ashoknagar0Piprai Road to Mundra Bahadur | 6.7 | G2
115 | PMGSY | IV | CGM I | Guna | mungawali | MP 1314 | Ashoknagar0Piprai Road to Keshopur | 4.8 | G3
116 | PMGSY | V | CGM I | Guna | Aron | MP 1315 | Aron-Sironj (SH-23) road to Kundoli | 5.8 | G2
117 | PMGSY | V | CGM I | Guna | Ashoknagar | MP 1316 | Sadhora - Vazidpur (MDR) Road to Mathner | 5.1 | G3
118 | PMGSY | V | CGM I | Guna | Ashoknagar | MP 1316 | Ashoknagar Rasulpur Rd to Borodiya Tumen | 4.3 | G2
119 | PMGSY | V | CGM I | Guna | Chachoda | MP 1315 | A.B. (NH-3) road to Meriyakhedi khurd | 2.03 | G2
120 | PMGSY | V | CGM I | Guna | Chachoda | MP 1315 | Meriyakhedi khurd to Junapani | 1.5 | Gsb
121 | PMGSY | V | CGM I | Guna | Guna | MP 1315 | Guna-Ashoknagar (MDR) road to Pipariya (Mawan) | 3.9 | G3
122 | PMGSY | V | CGM I | Guna | Guna | MP 1315 | Tarawata to Pureni | 4.46 | Gsb
123 | PMGSY | V | CGM I | Guna | Issagarh | MP 1316 | Isagarh- Indur (MDR) Road to Dengamohchar | 2.5 | GSB
124 | PMGSY | V | CGM I | Guna | Issagarh | MP 1316 | Vijaypura- Naisarai (MDR) Road to Sandoh | 3.6 | G3
125 | PMGSY | V | CGM I | Guna | Mungaoli | MP 1317 | Mungaoli-Onder (S.H.) Road to Gora Bhadurpur | 4.9 | Gsb
126 | PMGSY | V | CGM I | Guna | Mungaoli | MP 1317 | Mungaoli-Onder - Gora Bahadurpur (S.H.) Road to Barri | 4.25 | Gsb
127 | PMGSY | V | CGM I | Guna | Mungaoli | MP 1317 | Mungaoli Onder Road to Tilla | 4.45 | G2
128 | ADB | II | CGM I | Gwalior | Bhitarwar | MP 1451 | Dabra Chinor Road to Doni | 4.49 | GSB
129 | ADB | II | CGM I | Gwalior | Bhitarwar | MP 1451 | A.B. Road (Nayagaon) to Dabra Bhitarwar (MDR) | 26.65 | G3
130 | ADB | II | CGM I | Gwalior | Dabra | MP 1451 | Pichhore Indergarh Road to Kaithoda | 3.49 | GSB
131 | ADB | II | CGM I | Gwalior | Dabra | MP 1451 | Dabra Chinor Road to Sirsa | 4.095 | Earth Work
132 | PMGSY | IV | CGM I | Gwalior | Morar | MP 1407 | Gwalior Etawah Road to Suron | 4.225 | G3
133 | ADB | II | CGM I | Harda | Harda | MP 1551 | Harda Magarda Road to Khama Padwa Bamhangaon | 7.25 | Preparatory
134 | ADB | II | CGM I | Harda | Harda | MP 1551 | NH 59 'A' Road to Pidgaon | 1.2 | GSB
135 | ADB | II | CGM I | Harda | Harda | MP 1551 | NH 59 'A' Road to Uwa | 18.85 | Earth Work
136 | ADB | II | CGM I | Harda | Timarni | MP 1552 | Harda Chhipaner to Rundlai | 4.7 | Earth Work
137 | ADB | II | CGM I | Harda | Timarni | MP 1552 | Harda Chhipaner to Kuhiwadi | 3 | Earth Work
138 | ADB | II | CGM I | Harda | Timarni | MP 1552 | NH 59 'A' Road to Sohagpur | 10.4 | Earth Work
139 | PMGSY | IV | CGM I | Harda | Harda | MP 1504 | Sontalai to Harda Khandwa Road | 23.1 | G2
140 | PMGSY | IV | CGM I | Harda | Khir kiya | MP 1505 | Temlawadi to Charuwa Gupteshwar Road | 5.95 | BT
141 | PMGSY | IV | CGM I | Harda | Timarni | MP 1504 | Chidgaon tamoli to Pantalai Dudhkachh Road | 3.25 | Earth Work
142 | PMGSY | IV | CGM I | Harda | Timarni | MP 1505 | Nayagaon to Timarni 0 Chipaner Road | 8.6 | G3
143 | PMGSY | IV | CGM I | Harda | Timarni | MP 1505 | Gadamodkala toNayagaon Chhipaner Rd | 3.91 | G2
144 | PMGSY | V | CGM I | Harda | Khirkiya | MP 1506 | Charuwa to Sawalkheda | 14.77 | Gsb
145 | PMGSY | V | CGM I | Harda | Khirkiya | MP 1506 | Sawalkheda to Sundarpani | 6.2 | G2
146 | ADB | II | CGM I | Hoshangabad | Babai | MP 1651 | Babai Ari to Shukkarwara | 15.2 | G2
147 | ADB | II | CGM I | Hoshangabad | Babai | MP 1651 | Ari to Majalpur | 3.45 | Earth Work
148 | ADB | II | CGM I | Hoshangabad | Babai | MP 1651 | Babai Ari Shukkarawara to Mangrol | 3.67 | Earth Work
149 | ADB | II | CGM I | Hoshangabad | Babai | MP 1651 | Babai-Ari to Baglon | 1.235 | Earth Work
150 | ADB | II | CGM I | Hoshangabad | Babai | MP 1651 | Ari to Bagalkhedi | 4.225 | Preparatory
151 | ADB | II | CGM I | Hoshangabad | Babai | MP 1651 | Sangakheda to Chandla | 4.2 | GSB
152 | ADB | II | CGM I | Hoshangabad | Babai | MP 1651 | Shukkarwara to Gudla | 3.825 | G1
153 | ADB | III | CGM I | Hoshangabad | Seoni Malwa | MP 1652 | Shivpur to Bhensadeh | 4.05 | Earth work
154 | ADB | III | CGM I | Hoshangabad | Seoni Malwa | MP 1652 | Seoni Malwa-Shivpur to Richhi Rd. JN | 2.275 | G2
155 | ADB | III | CGM I | Hoshangabad | Seoni Malwa | MP 1652 | Richhi to Luchgaon | 6.5 | Not start
156 | ADB | III | CGM I | Hoshangabad | Seoni Malwa | MP 1652 | Bhensadeh to Kajali | 3.25 | Preparatory
157 | ADB | III | CGM I | Hoshangabad | Seoni Malwa | MP 1652 | Seoni Malwa-Ramgarh to Kolgaon | 0.975 | Earth work
158 | PMGSY | IV | CGM I | Hoshangabad | Babai | MP 1613 | Gora to Ari | 11 | BT
159 | PMGSY | IV | CGM I | Hoshangabad | Ban khedi | MP 1614 | Kamthi to Junheta | 3.75 | G3
160 | PMGSY | IV | CGM I | Hoshangabad | hoshangabad | MP 1611 | Nanpa to Itarsi Tigaria Road | 5.4 | G2
161 | PMGSY | IV | CGM I | Hoshangabad | Kesla | MP 1612 | Chheetapura to Sukhtawa Kala Akhar Road | 22.4 | BT
162 | PMGSY | IV | CGM I | Hoshangabad | Seoni Malwa | MP 1611 | Badanchikli to Dharmakundi Itarsi Rd | 4.1 | G2
163 | PMGSY | V | CGM I | Hoshangabad | Hoshangabad | MP 1617 | Chandon to Karpa | 2.925 | Gsb
164 | PMGSY | V | CGM I | Hoshangabad | Hoshangabad | MP 1617 | Dahalwarakala to Piparpani | 4 | G2
165 | PMGSY | V | CGM I | Hoshangabad | Hoshangabad | MP 1617 | Rahatwara to Nagwara | 3.575 | Gsb
166 | PMGSY | V | CGM I | Hoshangabad | Kesla | MP 1615 | NH 69 to Morpani | 6.3 | Gsb
167 | PMGSY | V | CGM I | Hoshangabad | Kesla | MP 1615 | Nh 69 to Kalaakhar | 3.3 | G2
168 | PMGSY | V | CGM I | Hoshangabad | Kesla | MP 1615 | Chhitapura to Borkheda | 7.08 | G2
169 | PMGSY | V | CGM I | Hoshangabad | Kesla | MP 1615 | Kalaakhar Borkheda to Khora | 1.55 | G2
170 | PMGSY | V | CGM I | Hoshangabad | Pipariya | MP 1616 | Hathwas to Jamara | 0 | Not start
171 | PMGSY | V | CGM I | Hoshangabad | Sohagpur | MP 1616 | Jamara Hathwas to Chanderi | 1 | G3
172 | PMGSY | V | CGM I | Hoshangabad | Sohagpur | MP 1616 | SH 22 to Barangi | 3 | Earthwork
173 | ADB | I | CGM I | Morena | Joura | MP 2551 | Sumawali to Singhora Via Loha Basai | 17.2 | BT
174 | ADB | I | CGM I | Morena | Joura | MP 2551 | Parsota toTiktoli Doomdar | 6.35 | G3
175 | ADB | I | CGM I | Morena | Joura | MP 2552 | Kaimara to Barwasin | 4.95 | G3
176 | ADB | I | CGM I | Morena | Morena | MP 2552 | Bandha to Peepar Kheda | 5.25 | G3
177 | ADB | III | CGM I | Morena | Ambah | MP 2553 | Ambah-Aroli Rd to Rithona | 5.3 | Preparatory
178 | ADB | III | CGM I | Morena | Ambah | MP 2553 | Ambah-Aroli Rd to Kakarai | 1.1 | Preparatory
179 | ADB | III | CGM I | Morena | Ambah | MP 2553 | Ambah -Aroli Rd to Pura Bhadoli | 2.32 | Preparatory
180 | ADB | III | CGM I | Morena | Ambah | MP 2553 | Sangoli Rd to Purwas Khurd | 2.35 | Earth work
181 | ADB | III | CGM I | Morena | Ambah | MP 2553 | Morena Mehgaon rd to Beraua | 6.35 | G2
182 | ADB | III | CGM I | Morena | Ambah | MP 2553 | M.M. Rd to Jwala Singh ka Pura | 0.75 | Not start
183 | ADB | III | CGM I | Morena | Ambah | MP 2553 | M.M. Rd to Tareni | 11.5 | GSB
184 | ADB | III | CGM I | Morena | Kailarsh | MP 2554 | Bijhgarhi Rd to Rajpura Jageer | 1.3 | G2
185 | ADB | III | CGM I | Morena | Kailarsh | MP 2554 | M.S. Rd to Labhkaran | 3.68 | GSB
186 | ADB | III | CGM I | Morena | Kailarsh | MP 2554 | Arroda Rd to Chamargawa | 0.8 | Preparatory
187 | ADB | III | CGM I | Morena | Morena | MP 2556 | AB Canal Rd to Bindwa Qwari | 1.4 | Earth work
188 | ADB | III | CGM I | Morena | Morena | MP 2556 | AB Rd to Canal to DJ Rd | 15.1 | G2
189 | ADB | III | CGM I | Morena | Morena | MP 2556 | AB Canal Rd to Khaskheda | 0.8 | G2
190 | ADB | III | CGM I | Morena | Morena | MP 2556 | AB Canal to Ghospur | 2.5 | G2
191 | ADB | III | CGM I | Morena | Morena | MP 2556 | AB Rd to Piparsa | 3.5 | Earth work
192 | ADB | III | CGM I | Morena | Pahargarh | MP 2554 | Bijhgarhi Rd to Pachokhara | 3.23 | G3
193 | ADB | III | CGM I | Morena | Pahargarh | MP 2554 | Nepari to Brijgarhi | 15.27 | G2
194 | ADB | III | CGM I | Morena | Pahargarh | MP 2554 | Bijhgarhi Rd to Ram Lal ka Pura | 2.93 | G3
195 | ADB | III | CGM I | Morena | Porsa | MP 2555 | Porsa Gormi Rd to Tarsuma | 9.2 | GSB
196 | ADB | III | CGM I | Morena | Porsa | MP 2555 | Ratan Basai Rd to Chuslai | 5.32 | Not start
197 | ADB | III | CGM I | Morena | Porsa | MP 2555 | M.M. Rd to Ratan Basai | 10.5 | Not start
198 | PMGSY | IV | CGM I | Morena | Joura | MP 2510 | Bagchini to Nandpura | 7.03 | BT
199 | PMGSY | IV | CGM I | Morena | Morena | MP 2510 | A.B. rd to Pahari | 3.725 | BT
200 | PMGSY | V | CGM I | Morena | Joura | MP 2513 | M.S. Rd to Sahrana | 3.9 | BT
201 | PMGSY | V | CGM I | Morena | Joura | MP 2513 | M.S. Rd to Jafrabad | 0.575 | BT
202 | PMGSY | V | CGM I | Morena | Joura | MP 2513 | M.S. Rd (Bilgaon) to Kheria | 7.25 | BT
203 | PMGSY | V | CGM I | Morena | Joura | MP 2513 | B.K. Rd to Balla ka Pura | 0.82 | BT
204 | PMGSY | V | CGM I | Morena | Morena | MP 2513 | Tilonda to Methana | 2.5 | BT
205 | PMGSY | V | CGM I | Morena | Morena | MP 2513 | Methana to Babarkheda | 1.5 | G3
206 | PMGSY | V | CGM I | Morena | Morena | MP 2513 | A.B. Rd to Sundar pur | 1.55 | BT
207 | PMGSY | V | CGM I | Morena | Porsa | MP 2512 | L.N. Rd to Hari Har ka Pura | 0.95 | G3
208 | PMGSY | V | CGM I | Morena | Porsa | MP 2512 | L.N. Rd to Mahua Police Styation Road (B.T. Rd) | 18.025 | G2
209 | PMGSY | V | CGM I | Morena | Porsa | MP 2512 | L.N. Rd to Khadiya Porsa | 0.805 | G3
210 | PMGSY | V | CGM I | Morena | Porsa | MP 2512 | L.N. Rd to Dhurandhar ka Pura | 1.1 | G3
211 | PMGSY | V | CGM I | Morena | Porsa | MP 2512 | L.N. Rd to Shahas ka Pura | 5.1 | G2
212 | PMGSY | V | CGM I | Morena | Porsa | MP 2512 | L.N. Rd to (Nagra) Kotra | 2.3 | G2
213 | PMGSY | V | CGM I | Morena | Porsa | MP 2512 | Harihar ka Pura to Chand ka pura | 1.85 | G3
214 | PMGSY | V | CGM I | Morena | Sabalgarh | MP 2514 | Ratiyapura via Bateswra | 16.1 | G3
215 | ADB | III | CGM I | Rajgarh | Khilchipur | MP 3051 | Bamangaon to Sonkheda Kalan | 2.5 | Preparatory
216 | ADB | III | CGM I | Rajgarh | Khilchipur | MP 3051 | Sonkheda kalan to Sandawata | 5.5 | Preparatory
217 | ADB | III | CGM I | Rajgarh | Khilchipur | MP 3051 | Chhapiheda to Kankriya | 4.75 | Not start
218 | ADB | III | CGM I | Rajgarh | N'garh | MP 3052 | Boda - N'garh Rd. to Hinotiya | 7.55 | Earth work
219 | ADB | III | CGM I | Rajgarh | N'garh | MP 3052 | Boda - Borkheda Rd. to Panwadi | 0.75 | Earth work
220 | ADB | III | CGM I | Rajgarh | N'garh | MP 3052 | Jamuniya Ganesh Junction to Jamuniya Johar | 1.95 | Earth work
221 | ADB | III | CGM I | Rajgarh | N'garh | MP 3052 | Eklera - Kurawar Road to Manpura Gujarati | 0.6 | Preparatory
222 | ADB | III | CGM I | Rajgarh | Rajgarh | MP 3051 | Rajgarh-Khujner Rd. to Saredi | 3.5 | Earth work
223 | ADB | III | CGM I | Rajgarh | Rajgarh | MP 3051 | Banskheda to Dehri karar | 4 | Earth work
224 | ADB | III | CGM I | Rajgarh | Rajgarh | MP 3051 | Chhatukheda-Sondhiya to Kali Talai | 4.8 | Earth work
225 | PMGSY | IV | CGM I | Rajgarh | Narsinghgarh | MP 3008 | NH012 to Jaumunia Ganesh | 3.6 | BT
226 | PMGSY | V | CGM I | Rajgarh | Biaora | MP 3010 | NH-12 to Lasudliya Maharaj | 2.8 | G3
227 | PMGSY | V | CGM I | Rajgarh | Biaora | MP 3010 | Biaora to Habipura | 1.85 | Earthwork
228 | PMGSY | V | CGM I | Rajgarh | Biaora | MP 3010 | Suthaliya to Pahadgarh | 4.15 | Gsb
229 | PMGSY | V | CGM I | Rajgarh | Biaora | MP 3010 | NH-3 to Chatha | 4.4 | GSB
230 | PMGSY | V | CGM I | Rajgarh | Biaora | MP 3010 | Kalipeeth to Chatha | 8 | G2
231 | PMGSY | V | CGM I | Rajgarh | Jirapur | MP 3012 | Pachor-Machalpur Rd. to Tamboliya | 2.5 | G2
232 | PMGSY | V | CGM I | Rajgarh | Jirapur | MP 3012 | SH-14 to Sadalpur | 3.75 | BT
233 | PMGSY | V | CGM I | Rajgarh | Jirapur | MP 3012 | Jirapur to Rajahedi | 8 | BT
234 | PMGSY | V | CGM I | Rajgarh | Narsingarh | MP 3011 | NH-12 to Khanpura | 7.2 | BT
235 | PMGSY | V | CGM I | Rajgarh | Narsingarh | MP 3011 | Khanpura Rd. to Daulatpura | 4.5 | Earth work
236 | PMGSY | V | CGM I | Rajgarh | Narsingarh | MP 3011 | Talen Eklera Road to Kansrod | 2.7 | BT
237 | PMGSY | V | CGM I | Rajgarh | Sarangpur | MP 3013 | A.B. Rd. to Nainwada | 1 | G2
238 | PMGSY | V | CGM I | Rajgarh | Sarangpur | MP 3013 | Nainwada to Chhapra | 0.75 | G2
239 | PMGSY | V | CGM I | Rajgarh | Sarangpur | MP 3013 | Nainwada to Kamalsar | 3.65 | G2
240 | PMGSY | V | CGM I | Rajgarh | Sarangpur | MP 3013 | Sarangpur-Sandawata Rd to Nipaniyatula | 4.3 | GSB
241 | PMGSY | V | CGM I | Rajgarh | Sarangpur | MP 3013 | Sarangpur-Sandawata Rd. to Balodi | 1.575 | Earth work
242 | ADB | III | CGM I | Sheopur | Kharhal | MP 3751 | Ajapura awada road to Mayapur | 3.05 | Earth work
243 | ADB | III | CGM I | Sheopur | Kharhal | MP 3751 | Ajapura awada road to Junction of Mayapur road | 3.75 | Earth work
244 | PMGSY | III | CGM I | Sheopur | Sheopur | MP 3703 a | Manpur to Bagadiya | 12.25 | BT
245 | PMGSY | IV | CGM I | Sheopur | Vijaypur | MP 3704 | Tentra Goras rd. to Panchogawan | 3.4 | G3
246 | PMGSY | IV | CGM I | Sheopur | Vijaypur | MP 3704 | Tentra Goras Rd. to Balawni* | 17.8 | G3
247 | PMGSY | V | CGM I | Sheopur | SHEOPUR | MP 3706 | Baroda kunjapura road to Baglda | 13.9 | GSB
248 | PMGSY | V | CGM I | Sheopur | Sheopur | MP 3708 | Makravada to Subkara | 8.95 | G2
249 | PMGSY | V | CGM I | Sheopur | Vijaypur | MP 3707 | Goras Tentra road to Syarda | 2.7 | G2
250 | PMGSY | V | CGM I | Sheopur | Vijaypur | MP 3707 | Shyampur Beerpur Road to Gohar | 2.6 | Preparatory
251 | PMGSY | V | CGM I | Sheopur | Vijaypur | MP 3707 | Raghunathpur Balawani road to Arrodari | 7.7 | GSB
252 | PMGSY | V | CGM I | Sheopur | Vijaypur | MP 3707 | L105 to Kheronakalan | 5.15 | Earth work
253 | PMGSY | V | CGM I | Sheopur | Vijaypur | MP 3707 | L108 to Kheroda khurd | 2.9 | Earth work
254 | ADB | II | CGM I | Shivpuri | Karera | MP 4052 | NH25 to Sillarpur | 0.9 | G3
255 | ADB | II | CGM I | Shivpuri | Karera | MP 4052 | Pichhore dinara road to Dhand | 5.1 | G3
256 | ADB | II | CGM I | Shivpuri | Karera | MP 4052 | NH25 to Bamhari(two parts Nichroli) | 10.2 | G2
257 | ADB | II | CGM I | Shivpuri | Khaniyadhana | MP 4051 | Pichhore rannod road (Mayapur) to L094 Pura II | 2.05 | G2
258 | ADB | II | CGM I | Shivpuri | Khaniyadhana | MP 4051 | Chanderi pichore road to Khirkit | 10.85 | G2
259 | ADB | II | CGM I | Shivpuri | Khaniyadhana | MP 4051 | Khirkit to Basahar | 3.1 | G2
260 | ADB | II | CGM I | Shivpuri | Pichhore | MP 4051 | Pichhore gora road to Ganesh Kheda | 3 | G2
261 | ADB | II | CGM I | Shivpuri | Pichhore | MP 4051 | Ganesh Kheda to Pipro | 11 | G2
262 | ADB | III | CGM I | Shivpuri | Karera | MP 4053 | Sadkheda to Karatha | 1.7 | G3
263 | ADB | III | CGM I | Shivpuri | Karera | MP 4053 | KB road to Bungaban | 1.38 | GSB
264 | ADB | III | CGM I | Shivpuri | Karera | MP 4053 | Sad road to Muganwli | 1.38 | G2
265 | ADB | III | CGM I | Shivpuri | Karera | MP 4053 | Badora road to Toda Pichhore | 0.6 | G2
266 | ADB | III | CGM I | Shivpuri | Karera | MP 4053 | Pichhore dinara road to Buserakala | 4.95 | GSB
267 | ADB | III | CGM I | Shivpuri | Khaniya dhana | MP 4055 | RP road to Piproda ubari | 7.6 | Earth work
268 | ADB | III | CGM I | Shivpuri | Khaniya dhana | MP 4055 | RP Piproda ubari Dhapura | 3.05 | Preparatory
269 | ADB | III | CGM I | Shivpuri | Khaniya dhana | MP 4055 | CP road to Padra | 2 | GSB
270 | ADB | III | CGM I | Shivpuri | Kolaras | MP 4054 | Kolaras Bhadota road to Chandoria | 1.3 | GSB
271 | ADB | III | CGM I | Shivpuri | Kolaras | MP 4054 | AB road to Sakhnor | 6.9 | Earth work
272 | ADB | III | CGM I | Shivpuri | Nerwar | MP 4053 | Karera Nerwar road to Kaliphadi | 4.3 | GSB
273 | ADB | III | CGM I | Shivpuri | Nerwar | MP 4053 | Kaliphadi to Saboli | 4.5 | GSB
274 | ADB | III | CGM I | Shivpuri | Nerwar | MP 4053 | SH 25 Bilhari (Sad) road to Toriya Khurd | 4.15 | GSB
275 | ADB | III | CGM I | Shivpuri | Nerwar | MP 4053 | Toriya Khurd to Kudawali | 9.22 | GSB
276 | ADB | III | CGM I | Shivpuri | Nerwar | MP 4053 | KB road to Khadicha | 6.7 | GSB
277 | ADB | III | CGM I | Shivpuri | Nerwar | MP 4053 | Nerwar Karera road to Jaitpur | 2.55 | GSB
278 | ADB | III | CGM I | Shivpuri | Pichhore | MP 4055 | Sirsod Pichhore road to Muhar | 5.2 | Earth work
279 | ADB | III | CGM I | Shivpuri | Pichhore | MP 4055 | Pichhore Gora road to Kakrau thuni | 2.28 | Earth work
280 | ADB | III | CGM I | Shivpuri | Pichhore | MP 4055 | Pichhore Rannod road to Imalia | 2.1 | GSB
281 | ADB | III | CGM I | Shivpuri | Pichhore | MP 4055 | RP road to Gurkudwaya | 4.95 | G2
282 | ADB | III | CGM I | Shivpuri | Pohri | MP 4054 | MP road to Barod | 5.7 | G2
283 | ADB | III | CGM I | Shivpuri | Pohri | MP 4054 | Charch to Mehloni | 5.8 | Earth work
284 | PMGSY | III | CGM I | Shivpuri | Badarwas | MP 4010 | Deharda Isagarh Road to Megonabada | 8.2 | G3
285 | PMGSY | III | CGM I | Shivpuri | Narwar | MP 4011 | Magroni to Kankar | 11.67 | BT
286 | PMGSY | V | CGM I | Shivpuri | Baderwas | MP 4017 | AB road to Barai | 3.6 | G2
287 | PMGSY | V | CGM I | Shivpuri | Bederwas | MP 4017 | Pachawali rannod road to Dehrda ganesh | 7.5 | G3
288 | PMGSY | V | CGM I | Shivpuri | Shivpuri | MP 4016 | NH25 To Budi Barod (To Bichi) | 23 | G2
289 | PMGSY | V | CGM I | Shivpuri | Shivpuri | MP 4016 | AB road to Kersena | 4.2 | G2
Total I
1 | ADB | I | CGM II | Bhopal | Berasiya | MP 0551 | Ichgiri to Roniya | 3.375 | Earth work
2 | ADB | I | CGM II | Bhopal | Berasiya | MP 0551 | Naysamund to Bhilkho | 5.19 | Earth work
3 | ADB | I | CGM II | Bhopal | Berasiya | MP 0551 | Katighati to Pipalkheda | 4.2 | Not started
4 | ADB | I | CGM II | Bhopal | Berasiya | MP 0551 | SH -23 to Bhensoda | 1 | Earth work
5 | ADB | I | CGM II | Bhopal | Phanda | MP 0551 | Chopdakala to Kalyanpur | 5.4 | GSB
6 | ADB | I | CGM II | Bhopal | Phanda | MP 0551 | Vidisha Road (SH-18) to Gadmurra | 1.25 | Preparatory
7 | ADB | I | CGM II | Bhopal | Phanda | MP 0551 | Bagoniya to Tarasevaniya | 2.85 | Earth work
8 | PMGSY | III | CGM II | Bhopal | Phanda | MP 0505 | Bhopal Sehore road to Pipliya Dhakad | 2.8 | G2
9 | PMGSY | IV | CGM II | Bhopal | Beraisya | MP 0506 | Kalara to Junapani | 5 | BT
10 | PMGSY | V | CGM II | Bhopal | Berasiya | MP 0507 | SH-23 to Kadaiyashah | 7.9 | G2
11 | PMGSY | V | CGM II | Bhopal | Berasiya | MP 0507 | Junapani to Gangapipaliya | 5 | Earth work
12 | PMGSY | V | CGM II | Bhopal | Phanda | MP 0507 | Intkhedi to Bheopura | 1.75 | Preparatory
13 | ADB | I | CGM II | Chhatarpur | Badamalhara | MP 0651 | Badamalhra-Ghuwara Road to Panwari To Bhoyra | 3.15 | GSB
14 | ADB | I | CGM II | Chhatarpur | Barigarh | MP 0652 | Sarwai to Goyra | 12.5 | Earth work
15 | ADB | I | CGM II | Chhatarpur | Buxwaha | MP 0651 | NH-86 to Lohani | 6.4 | G3
16 | ADB | I | CGM II | Chhatarpur | Chhatarpur | MP 0651 | NH-86 to Bari | 1.444 | G3
17 | ADB | I | CGM II | Chhatarpur | Chhatarpur | MP 0651 | Chhartarpur By Pass to Sarani | 4 | G3
18 | ADB | I | CGM II | Chhatarpur | Laundi | MP 0652 | Laundi Mahoba Road to Didwara | 4.8 | GSB
19 | ADB | I | CGM II | Chhatarpur | Nowgaon | MP 0652 | N.H 86 (Niwari) to Dilaniya | 6.3 | G2
20 | ADB | I | CGM II | Chhatarpur | Rajnagar | MP 0652 | Kadari-Vikrampur Road to Pipat | 2.8 | GSB
21 | ADB | III | CGM II | Chhatarpur | Badamalahra | MP 0653 | NH-86 Baldevgarh Tikamgarh SH 10 To Khardodi | 10.31 | Earth work
22 | ADB | III | CGM II | Chhatarpur | Badamalahra | MP 0653 | Khardoti Road To Beeron | 1.38 | Earth work
23 | ADB | III | CGM II | Chhatarpur | Badamalahra | MP 0653 | Khardoti Road To Bamari | 1.12 | Preparatory
24 | ADB | III | CGM II | Chhatarpur | Badamalahra | MP 0653 | Khardoti Road To Bhojpur | 3.7 | Preparatory
25 | ADB | III | CGM II | Chhatarpur | Barigarh | MP 0655 | Jyoraha Barigarh Gorihar Road To Khera Kasar | 5.3 | Earth work
26 | ADB | III | CGM II | Chhatarpur | Barigarh | MP 0655 | Jyoraha Barigahr Gourihar Road to Khera Kasar Junction | 17.68 | Preparatory
27 | ADB | III | CGM II | Chhatarpur | Barigarh | MP 0655 | Kiwlaha Ro Abhau | 6.3 | Preparatory
28 | ADB | III | CGM II | Chhatarpur | Bijawar | MP 0653 | Bijawar Kishangarh (SH 10) to Kupi | 3.42 | Preparatory
29 | ADB | III | CGM II | Chhatarpur | Bijawar | MP 0653 | Gulganj Bijawar (SH10) To Maukhera | 1.15 | Preparatory
30 | ADB | III | CGM II | Chhatarpur | Chhatarpur | MP 0654 | Nowgogng Ishanagar Road To Bandhi Kalan | 0.55 | Not start
31 | ADB | III | CGM II | Chhatarpur | Chhatarpur | MP 0654 | Nowgong Ishnagar Road To Bandhi Kalan to Bandhi Khurd | 5.5 | Not start
32 | ADB | III | CGM II | Chhatarpur | Chhatarpur | MP 0654 | NH86 To Khop | 2.35 | Not start
33 | ADB | III | CGM II | Chhatarpur | Chhatarpur | MP 0654 | NH86 To Khop Kalani | 3.34 | Not start
34 | ADB | III | CGM II | Chhatarpur | Chhatarpur | MP 0654 | Kalani To Pidpa | 1.6 | Not start
35 | ADB | III | CGM II | Chhatarpur | Rajnagar | MP 0654 | Bamitha Kawar Road To Patharguwan | 1.25 | Not start
36 | ADB | III | CGM II | Chhatarpur | Rajnagar | MP 0654 | Bamitha Kawar Road To Patharguwan Junction | 3.3 | Not start
37 | ADB | III | CGM II | Chhatarpur |  | MP 0656 |  |  | Not start
38 | ADB | III | CGM II | Chhatarpur |  | MP 0656 |  |  | Not start
39 | PMGSY | II | CGM II | Chhatarpur | Barigarh | MP 0604 | App. Road Thakurra | 8.7 | RE ten. (WO2.3.06)
40 | PMGSY | III | CGM II | Chhatarpur | Barigarh | MP 0608 | Khaddi to Seelap | 5.4 | G3
41 | PMGSY | III | CGM II | Chhatarpur | Barigarh | MP 0608 | Khaddi to Palta | 6.25 | G3
42 | PMGSY | III | CGM II | Chhatarpur | Baxwaha | MP 0606 | Bamhori Deopur to Majhguwanghat | 5.23 | G3
43 | PMGSY | III | CGM II | Chhatarpur | Bijawar | MP 0607 | Bijwar Banja to Gopalpura | 1 | Not start (Land Problem)
44 | PMGSY | III | CGM II | Chhatarpur | Laundi | MP 0610 | laundi to Katiya | 17.05 | G3
45 | PMGSY | III | CGM II | Chhatarpur | Nowgaon | MP 0609 | Badagaon Harpalpur road to Imaliya | 7.5 | G2
46 | PMGSY | III | CGM II | Chhatarpur | Rajnagar | MP 0610 | Rajnagar Dumra rd. to Gomakala | 7.15 | G3
47 | PMGSY | IV | CGM II | Chhatarpur | Badamalhara | MP 0611 | Chhatarpur Sagar Road to Dhanguwa | 6 | G2
48 | PMGSY | IV | CGM II | Chhatarpur | Badamalhara | MP 0611 | Badamalhara Guwara road to Gorkhanpura | 7.5 | GSB
49 | PMGSY | IV | CGM II | Chhatarpur | Badamalhara | MP 0611 | Badamalhara Ghouhara Road to Barma | 4.46 | G3
50 | PMGSY | IV | CGM II | Chhatarpur | Barigarh | MP 0614 | Kitpura to Hanukheda | 2.51 | Not started (land problem)
51 | PMGSY | IV | CGM II | Chhatarpur | Barigarh | MP 0614 | Mudri Gorihar rd. to Manuriya | 1.134 | Earth Work
52 | PMGSY | IV | CGM II | Chhatarpur | Barigarh | MP 0614 | Chandla Sarwai road to Gohani | 7.143 | GSB
53 | PMGSY | IV | CGM II | Chhatarpur | Barigarh | MP 0613 | Prakash Bamhori to Badhorakala | 7.52 | G3
54 | PMGSY | IV | CGM II | Chhatarpur | Barigarh | MP 0613 | Gorihar Maton rd. to Manwara | 3.15 | GSB
55 | PMGSY | IV | CGM II | Chhatarpur | Barigarh | MP 0613 | Khaddi to Padwar | 13.95 | G3
56 | PMGSY | IV | CGM II | Chhatarpur | Barigarh | MP 0613 | Gorihar to Reona | 3.43 | G2
57 | PMGSY | IV | CGM II | Chhatarpur | Bijawar | MP 0612 | Bijawar Bajna Road to Patan | 7.311 | BT
58 | PMGSY | IV | CGM II | Chhatarpur | Buxwaha | MP 0611 | Bamhori to Devri | 6.34 | G3
59 | PMGSY | IV | CGM II | Chhatarpur | Laundi | MP 0614 | Laundi Mahowa to Devpur | 2.8 | GSB
60 | PMGSY | IV | CGM II | Chhatarpur | Rajnagar | MP 0614 | Dumra Laundi Road to Digoni | 6.262 | G3
61 | PMGSY | V | CGM II | Chhatarpur | Badamalhara | MP 0616 | Ghuwara Indora (SH 37) rd to Bhelda | 3.86 | Earthwork
62 | PMGSY | V | CGM II | Chhatarpur | Badamalhara | MP 0616 | Badamalhara Ghuwara (MDR) rd to Sarkana | 8.76 | G2
63 | PMGSY | V | CGM II | Chhatarpur | Chhatarpur | MP 0616 | Chhatarpur Satai Rd to Moraha | 1.2 | Gsb
64 | PMGSY | V | CGM II | Chhatarpur | Chhatarpur | MP 0616 | Chhatarpur to Satai road to Moraha Approach | 3.3 | Gsb
65 | PMGSY | V | CGM II | Chhatarpur | Chhatarpur | MP 0616 | Chhatarpur Satai Rd to Gurriya | 3.45 | Gsb
66 | PMGSY | V | CGM II | Chhatarpur | Laundi | MP 0617 | Laundi Mahoba (MDR) rd to Midka | 1.64 | Earthwork
67 | PMGSY | V | CGM II | Chhatarpur | Laundi | MP 0617 | Midka Approad to Bamhori | 3.97 | Earthwork
68 | PMGSY | V | CGM II | Chhatarpur | Laundi | MP 0617 | Bamhori App Road to Laxmanpura | 2.83 | Not start
69 | PMGSY | V | CGM II | Chhatarpur | Nowgaon | MP 0617 | Nowgong Palera Road To Chandrpura | 10.15 | Gsb
70 | PMGSY | V | CGM II | Chhatarpur | Nowgaon | MP 0617 | Sunati To Machha | 2.3 | Gsb
71 | ADB | II | CGm II | Damoh | Damoh | MP 0851 | SH-37(Abhana) to Ranjra | 10.1 | G2
72 | ADB | II | CGm II | Damoh | Damoh | MP 0851 | Ranjara-Jhukhar road to Khanchari pati | 7.85 | GSB
73 | ADB | II | CGm II | Damoh | Damoh | MP 0851 | Abhana Ranjra road to Patna Khurd | 2.4 | Earth Work
74 | ADB | II | CGm II | Damoh | Damoh | MP 0851 | Ranjra to Pati | 1.85 | Not Start
75 | ADB | II | CGm II | Damoh | Hatta | MP 0851 | Madiyadoh Bardha road to Malwara | 3.35 | GSB
76 | ADB | II | CGm II | Damoh | Hatta | MP 0851 | Madiyado Rajpura road to Puranakheda | 2.4 | Preparatory
77 | ADB | II | CGm II | Damoh | Hatta | MP 0851 | Purenakheda App. road to Tigra Fatehpur | 3.1 | Preparatory
78 | ADB | III | CGM II | Damoh | Damoh | MP 0852 | Damoh-Hatta Road to Rusalli | 6 | Earth work
79 | ADB | III | CGM II | Damoh | Damoh | MP 0852 | Hatta-Sagoni Road to Gadaghat | 2.4 | Earth work
80 | ADB | III | CGM II | Damoh | Damoh | MP 0852 | Hatta-Patera Road to Kuwakheda Baji | 0.75 | Earth work
81 | PMGSY | II | CGM II | Damoh | Batiyagarh | MP 0802 | Aanjani to Agara App. Road | 3.62 | G3
82 | PMGSY | III | CGM II | Damoh | Pathariya | MP 0810 | Pathriya to Sasa | 14.2 | BT
83 | PMGSY | IV | CGM II | Damoh | Batiyagrh | MP 0812 | Chainpura to Hingwani | 4.9 | Earth Work
84 | PMGSY | IV | CGM II | Damoh | Damoh | MP 0812 | Bandkpur to Saliya | 6.55 | BT
85 | PMGSY | IV | CGM II | Damoh | Hatta | MP 0814 | Hatta Gasibed road to Tewraiya | 3.6 | G3
86 | PMGSY | IV | CGM II | Damoh | Hatta | MP 0814 | Rameh Bijwar road to Bandha | 4.65 | G2
87 | PMGSY | IV | CGM II | Damoh | Jabera | MP 0813 | Dhunginala 0 Ghatera to Badguwan | 1.15 | Earth Work (forest )
88 | PMGSY | IV | CGM II | Damoh | Patera | MP 0814 | SH014 to Kuluwa Kumhari | 4 | G3
89 | PMGSY | IV | CGM II | Damoh | Pathariya | MP 0812 | Khiriya to Piprodha Chhakka | 6.15 | G3
90 | PMGSY | IV | CGM II | Damoh | Pathariya | MP 0812 | SH014 to Bardhari | 7.1 | Earth Work
91 | PMGSY | IV | CGM II | Damoh | Pathariya | MP 0812 | Damoh Pathariya road to Sadguwan | 2.6 | GSB
92 | PMGSY | IV | CGM II | Damoh | Pathariya | MP 0812 | Narsingarh Sitanagar road to Khejrakala | 3.9 | G3
93 | PMGSY | IV | CGM II | Damoh | Pathariya | MP 0812 | Damoh Pathariya road to Samera Bujarg | 1.3 | GSB
94 | PMGSY | IV | CGM II | Damoh | Tendukheda | MP 0813 | Mohra to Mohad | 5.9 | Forest
95 | PMGSY | IV | CGM II | Damoh | Tendukheda | MP 0813 | Abhana0Pendukheda Patan Road to Hardua Panji | 3.8 | Forest
96 | PMGSY | V | CGM II | Damoh | Batiyagarh | MP 0815 | Kaithora to Sihera | 2.35 | G2
97 | PMGSY | V | CGM II | Damoh | Batiyagarh | MP 0815 | Hingwani to Nibora Kalan | 9 | Gsb
98 | PMGSY | V | CGM II | Damoh | Batiyagarh | MP 0815 | SH-37 to Khiriya Asli | 2.05 | G3
99 | PMGSY | V | CGM II | Damoh | Jabera | MP 0816 | SH-37 (Dhunginala-Ghatera Road) to Paraswaha Junction | 20.25 | G2
100 | PMGSY | V | CGM II | Damoh | Jabera | MP 0816 | Dhunginala Ghatera Road to Paraswaha | 1.2 | G2
101 | PMGSY | V | CGM II | Damoh | Jabera | MP 0816 | Dhunginala Ghatera Road to Lakhni | 4.3 | Earth work
102 | PMGSY | V | CGM II | Damoh | Jabera | MP 0816 | SH-37 (Dhunginala-Ghatera Road) to Pipariya Naval | 2.45 | Earth work
103 | PMGSY | V | CGM II | Damoh | Jabera | MP 0816 | Dhunginala Ghatera Road to Khamariya | 1 | Gsb
104 | PMGSY | V | CGM II | Damoh | Pathariya | MP 0815 | Damoh-Pathariya Road to Bakeni | 2.95 | Earth work
105 | PMGSY | V | CGM II | Damoh | Pathariya | MP 0815 | Pathariya Kindraho-Jerat Road to Suhave | 1.9 | G2
106 | PMGSY | V | CGM II | Damoh | Pathariya | MP 0815 | Pathariya-Kerbana Road to Jakhtar | 0.63 | Not start
107 | PMGSY | V | CGM II | Damoh | Pathariya | MP 0815 | Sagar-Damoh Road to Hinota Narsingarh | 3.15 | Not start
108 | ADB | II | CGM II | Panna | Gunour | MP 2851 | MDR-Saleha-Nagod-Ganj to Nachne | 2 | GSB
109 | ADB | II | CGM II | Panna | Gunour | MP 2851 | ODR-Saleha Nagod Road | 7 | G2
110 | ADB | II | CGM II | Panna | Gunour | MP 2851 | ODR-Saleha Nagod Road to Bhatia | 2 | G2
111 | ADB | II | CGM II | Panna | Gunour | MP 2852 | SH-49 Panna-Amanganj Km. 36/10 to Siri | 4.3 | G2
112 | ADB | II | CGM II | Panna | Gunour | MP 2852 | SH-10 Km. 49/6 Katni-Kishangarh to Bamhori | 4.14 | G2
113 | ADB | II | CGM II | Panna | Gunour | MP 2852 | 1.5th km of Bamhori App. Road to Jharkua | 1.5 | Not Start
114 | ADB | II | CGM II | Panna | Panna | MP 2851 | NH-75 From Phulwari to Bhilsayan. | 3.013 | G2
115 | ADB | II | CGM II | Panna | Panna | MP 2851 | MDR-11 Panna-Pahadikhera to Ahirgawan | 2.6 | G3
116 | ADB | II | CGM II | Panna | Panna | MP 2851 | MDR-11 Panna-Pahadikhera to Tilgaon | 1.05 | G3
117 | ADB | II | CGM II | Panna | Panna | MP 2851 | ODR-Laxmipur-devendrangar marg to Basai | 2.5 | G2
118 | ADB | II | CGM II | Panna | Panna | MP 2851 | ODR-Laxmipur-devendrangar marg | 15.25 | G2
119 | ADB | II | CGM II | Panna | Pawai | MP 2852 | MDR-Saleha-Pawai-Mohandra to Simra Khurd | 3 | GSB
120 | ADB | II | CGM II | Panna | Pawai | MP 2852 | SH-10-52/10 Katni-Kishangarh to Tai | 5.6 | G3
121 | ADB | II | CGM II | Panna | Shahnagar | MP 2852 | MDR-Simariya-Raipura to Bhagwarkala | 4 | GSB
122 | ADB | II | CGM II | Panna | Shahnagar | MP 2852 | MDR-Simariya-Raipura to Bugraur | 2 | GSB
123 | ADB | II | CGM II | Panna | Shahnagar | MP 2852 | MDR-Shahnagar-Raipura to Pondi | 12.05 | G2
124 | PMGSY | I | CGM II | Panna | Ajaygarh | MP 40 01 | App. Road Khora | 5 | G3
125 | PMGSY | I | CGM II | Panna | Ajaygarh | MP 40 01 | App. Road Pista | 3 | G3
126 | PMGSY | I | CGM II | Panna | Ajaygarh | MP 40 01 | App. Road Majhgny | 6 | G3
127 | PMGSY | I | CGM II | Panna | Gunor | MP 40 01 | App. Road Kathwariya | 2.8 | G3
128 | PMGSY | II | CGM II | Panna | Pawai | MP 2802 | App. Road Khora Mudwari | 8.6 | G3
129 | PMGSY | II | CGM II | Panna | Pawai | MP 2802 | App. Road Kamtana Sunwanikila | 6.75 | G3
130 | PMGSY | II | CGM II | Panna | Pawai | MP 2802 | App. Road Banoli | 8 | G3
131 | PMGSY | II | CGM II | Panna | Shah Nagar | MP 2803 | Bisani App. Road | 2.6 | GSB
132 | PMGSY | III | CGM II | Panna | Ajaygarh | MP 2805 | App.Road Chandroa | 3 | G2
133 | PMGSY | III | CGM II | Panna | Gunour | MP 2806 | App.Road Dharwara | 5.25 | G3
134 | PMGSY | III | CGM II | Panna | Panna | MP 2806 | App.Road Barbaspura | 7.9 | G3
135 | PMGSY | III | CGM II | Panna | Pawai | MP 2806 | App.Road Kriya | 6.8 | G3
136 | PMGSY | III | CGM II | Panna | Shanagar | MP 2807 | App.Road Khamaria | 7 | G3
137 | PMGSY | IV | CGM II | Panna | Ajaygarh | MP 2808 | Panna Chirkat Rd. (SH049) to Taroni | 2 | Earthwork
138 | PMGSY | IV | CGM II | Panna | Ajaygarh | MP 2808 | Ajaygarh0Kaliger rd to Amarchhi | 3.65 | G3
139 | PMGSY | IV | CGM II | Panna | Ajaygarh | MP 2808 | Barriyapur Canal Rd. to Padarha | 7.025 | BT
140 | PMGSY | IV | CGM II | Panna | Ajaygarh | MP 2808 | Ajaygarh Chandro to Lolas | 3.95 | G2
141 | PMGSY | IV | CGM II | Panna | Gunour | MP 2809 | Devendran Nagar Saleha Road to shyam Mardenda | 6.3 | G3
142 | PMGSY | IV | CGM II | Panna | Gunour | MP 2809 | Amarganj Gunnor rd to Patna kalan | 3.35 | G2
143 | PMGSY | IV | CGM II | Panna | Gunour | MP 2810 | Saleha Pawai to Chhijora | 1 | G2
144 | PMGSY | IV | CGM II | Panna | Panna | MP 2809 | Akola Gounor road to Deori | 8.35 | GSB
145 | PMGSY | IV | CGM II | Panna | Panna | MP 2809 | Akola Gounor road to Bakhtari | 5.45 | GSB
146 | PMGSY | IV | CGM II | Panna | Panna | MP 2809 | Devandranagar Saleha rd. to Raigarh | 3.82 | GSB
147 | PMGSY | IV | CGM II | Panna | Pawai | MP 2810 | SH049 to Mahodkala | 5.1 | BT
148 | PMGSY | IV | CGM II | Panna | Pawai | MP 2810 | Pawai0Kishangarh Rd. to Kupna | 5.2 | G3
149 | PMGSY | IV | CGM II | Panna | Shahnagar | MP 2810 | Banoli Changeri rd. to Chandrawal | 6.4 | G2
150 | PMGSY | IV | CGM II | Panna | Shahnagar | MP 2811 | SH010 to Amma | 3.75 | G3
151 | PMGSY | IV | CGM II | Panna | Shahnagar | MP 2811 | SH014 to Pipariyakala | 11.75 | GSB
152 | PMGSY | IV | CGM II | Panna | Shahnagar | MP 2811 | Khamariya to Atharhai | 2.3 | G3
153 | PMGSY | IV | CGM II | Panna | Shahnagar | MP 2811 | Sudour to Tunda | 6.3 | G3
154 | PMGSY | V | CGM II | Panna | Ajaygarh | MP 2812 | MDR-05 Ajaygarh-Touriya-Bariyarpur to Bhapatpur kurmiyan | 2.55 | GSB
155 | PMGSY | V | CGM II | Panna | Ajaygarh | MP 2812 | MDR-05 Ajaygarh-Touriya-Bariyarpur to Devra Bhapatpur | 4.9 | Not start
156 | PMGSY | V | CGM II | Panna | Ajaygarh | MP 2812 | MDR-02 Ajaygarh-Siddhapur-Kalingar to Sidhhapur | 4.5 | Earthwork
157 | PMGSY | V | CGM II | Panna | Ajaygarh | MP 2812 | ODR-Singhpur Kalinger Marg | 23.4 | BT
158 | PMGSY | V | CGM II | Panna | Ajaygarh | MP 2812 | ODR-Singhpur Kalinger Marg to Chhataini | 4.4 | Earthwork
159 | ADB | III | CGM II | Raisen | Begumganj | MP 2952 | Bhopal Sagar Road to Khajuriya Baramadgarhi | 3.45 | Not start
160 | ADB | III | CGM II | Raisen | Begumganj | MP 2952 | Chandora Gulwada to Naigadiya | 1.5 | Not start
161 | ADB | III | CGM II | Raisen | Begumganj | MP 2952 | Bhopal Sagar Road to Mahuakheda | 9.7 | Preparatory
162 | ADB | III | CGM II | Raisen | Gairatganj | MP 2953 | Bhopal Sagar Road to Tehri Mudpar | 4.15 | Not start
163 | ADB | III | CGM II | Raisen | Gairatganj | MP 2953 | Bhopal Sagar Road to Rajpura | 10.7 | Earth work
164 | ADB | III | CGM II | Raisen | Silwani | MP 2951 | SH-15 to Pradariakalan | 2.65 | GSB
165 | ADB | III | CGM II | Raisen | Silwani | MP 2951 | SH-15 to Siyalwada | 5.1 | Earth work
166 | ADB | III | CGM II | Raisen | Silwani | MP 2951 | Silwani Udaipura Road to Patha Pondi | 0.6 | GSB
167 | PMGSY | III | CGM II | Raisen | Begamganj | MP 2907 | Chandora to Gulwada | 6.5 | BT
168 | PMGSY | III | CGM II | Raisen | Silwani | MP 2907 | Silwani Bamhori road to Mankwada | 5.45 | BT
169 | PMGSY | IV | CGM II | Raisen | Bari | MP 2913 | Gadarwas to Goramachwai | 4.5 | G3
170 | PMGSY | IV | CGM II | Raisen | Udaipura | MP 2913 | NH 0 12 to Ketaghon | 15.475 | BT
171 | PMGSY | V | CGM II | Raisen | Badi | MP 2915 | N.H. 12 to Dimada | 9.1 | Earthwork
172 | PMGSY | V | CGM II | Raisen | Badi | MP 2915 | Semri Ghat to Motilsir | 8.8 | Earthwork
173 | PMGSY | V | CGM II | Raisen | Badi | MP 2915 | Motalsir to Bamanbada | 2.25 | Preparatory
174 | PMGSY | V | CGM II | Raisen | Badi | MP 2915 | Dimada Motalsir to Semri Ghat | 1.45 | Preparatory
175 | PMGSY | V | CGM II | Raisen | O-ganj | MP 2917 | Noorganj Dahod Rd. to Jabara malkhar | 7.25 | Not start
176 | PMGSY | V | CGM II | Raisen | O-ganj | MP 2917 | Jabramalkhar to Bagwani | 2.9 | Not start
177 | PMGSY | V | CGM II | Raisen | Sanchi | MP 2914 | Raisen Sagar Road to Kanphora | 14.1 | Earthwork
178 | PMGSY | V | CGM II | Raisen | Sanchi | MP 2914 | Raisen Sagar Road Murelkhurd | 2 | Earthwork
179 | PMGSY | V | CGM II | Raisen | Sanchi | MP 2914 | Raisen Sagar Road to Sangrampur | 0.6 | Not start
180 | PMGSY | V | CGM II | Raisen | Sanchi | MP 2914 | Raisen Sagar Road to Karhod | 2.5 | Earthwork
181 | PMGSY | V | CGM II | Raisen | Udaipura | MP 2916 | NH-12 to Noniyabareli | 5.6 | G3
182 | PMGSY | V | CGM II | Raisen | Udaipura | MP 2916 | Noniya Bareli to Pipaliya-kewat | 3.2 | GSB
183 | PMGSY | V | CGM II | Raisen | Udaipura | MP 2916 | Pipaliya kewat to Ghant Khedi | 3.45 | GSB
184 | ADB | III | CGM II | Sagar | Kesli | MP 3351 | Barkoti-Bhusora road (Medki) to Bilahri | 1.3 | G2
185 | ADB | III | CGM II | Sagar | Kesli | MP 3351 | Bilhahri Medki road to Patna Deori | 3.2 | Earth work
186 | ADB | III | CGM II | Sagar | Kesli | MP 3351 | Barkoti-Bhusora road (Kariya Tola) to Mohasa | 8.6 | Earth work
187 | ADB | III | CGM II | Sagar | Kesli | MP 3351 | MDR (Jaitpur) to Doma | 2.1 | Not start
188 | ADB | III | CGM II | Sagar | Khurai | MP 3354 | MDR to Malasuneti | 1 | Not start
189 | ADB | III | CGM II | Sagar | Khurai | MP 3354 | MDR to Ghorat | 3 | Earth work
190 | ADB | III | CGM II | Sagar | Khurai | MP 3354 | SH14 to Semra ganpat | 6.45 | Earth work
191 | ADB | III | CGM II | Sagar | Khurai | MP 3354 | Semra Ganpat to Bamori Khandera | 2.15 | Not start
192 | ADB | III | CGM II | Sagar | Khurai | MP 3354 | Magardha to Mahera | 2.2 | Not start
193 | ADB | III | CGM II | Sagar | Khurai | MP 3354 | SH42 to Gwari | 3.5 | Earth work
194 | ADB | III | CGM II | Sagar | Khurai | MP 3354 | Gwari to Korsa | 0 | Earth work
195 | ADB | III | CGM II | Sagar | Rahatgarh | MP 3352 | SH14 (Km. 29) to Semra Lahariya | 5.3 | Preparatory
196 | ADB | III | CGM II | Sagar | Rahatgarh | MP 3352 | Semra Lahariya to Barodiya Ballabh (subsidiary link) | 0 | Preparatory
197 | ADB | III | CGM II | Sagar | Rahatgarh | MP 3352 | Khurai-Sagar road (Khurai Tigdda) to Hanota Parichhat | 3.3 | Preparatory
198 | ADB | III | CGM II | Sagar | Rahatgarh | MP 3352 | NH86 to Menwara Kalan | 4.95 | Preparatory
199 | ADB | III | CGM II | Sagar | Rahatgarh | MP 3352 | Mardanpur to Mohasa | 2 | Preparatory
200 | ADB | III | CGM II | Sagar | Shahgarh | MP 3353 | SH37 to Garroli | 0.8 | Earth work
201 | ADB | III | CGM II | Sagar | Shahgarh | MP 3353 | Jasoda to Datya | 2.8 | Earth work
202 | ADB | III | CGM II | Sagar | Shahgarh | MP 3353 | MDR (Banda-Barayatha road) to Mahuna | 4 | Earth work
203 | ADB | III | CGM II | Sagar | Shahgarh | MP 3353 | Mahuna to Ratanpur | 1.65 | Earth work
204 | PMGSY | III | CGM II | Sagar | Banda | MP 3311 | Patan to MDR | 11.99 | BT
205 | PMGSY | III | CGM II | Sagar | Deori | MP 3314 | Jaitpur to Mangela | 1.95 | G3
206 | PMGSY | III | CGM II | Sagar | Deori | MP 3314 | Simariya (Harrakheda) to Anantpur | 4.24 | G3
207 | PMGSY | III | CGM II | Sagar | Keshli | MP 3314 | Bamhani to Patanakhurd | 2.35 | G3
208 | PMGSY | III | CGM II | Sagar | Keshli | MP 3314 | Naya Nagar to MDR | 2.17 | BT
209 | PMGSY | III | CGM II | Sagar | Malthon | MP 3310 | Sewan to Bandari | 17.5 | BT
210 | PMGSY | III | CGM II | Sagar | Rahatgarh | MP 3313 | Khejra Mafi to Bahadurpur | 7.25 | Cancel
211 | PMGSY | III | CGM II | Sagar | Rahli | MP 3312 | Rampur to Jamghat | 11.265 | BT
212 | PMGSY | IV | CGM II | Sagar | Banda | MP 3316 | Singarahan to MDR | 6.62 | G2
213 | PMGSY | IV | CGM II | Sagar | Khurai | MP 3315 | Binayth to Ujneth | 5.55 | G2
214 | PMGSY | IV | CGM II | Sagar | Khurai | MP 3315 | Kumrel to Dhanera | 5.72 | BT
215 | PMGSY | IV | CGM II | Sagar | Malthone | MP 3315 | Maduwan Gouri to Barodiya | 8 | GSB
216 | PMGSY | IV | CGM II | Sagar | Rahli | MP 3317 | Gada kota to Pipariya Gopal | 4.9 | BT
217 | PMGSY | IV | CGM II | Sagar | Sagar | MP 3316 | Bhaiswahi to Girwar | 1.85 | G2
218 | PMGSY | IV | CGM II | Sagar | Sagar | MP 3316 | NH86 to Muhli | 2.25 | BT
219 | PMGSY | IV | CGM II | Sagar | Shahgarh | MP 3316 | Bagrodha to Baraytha MDR | 3.5 | G2
220 | PMGSY | IV | CGM II | Sagar | Shahgarh | MP 3316 | Ludyara to NH86 | 5.7 | BT
221 | PMGSY | V | CGM II | Sagar | Banda | MP 3320 | MDR to Bamhori jagdish | 9.4 | Earth work
222 | PMGSY | V | CGM II | Sagar | Banda | MP 3320 | MDR Bamhori jagdish road (Pidaruwa) to Sagoriya | 3.17 | Earth work
223 | PMGSY | V | CGM II | Sagar | Bina | MP 3318 | Dehrai to Semer Khedi | 3.5 | Earth work
224 | PMGSY | V | CGM II | Sagar | Bina | MP 3318 | Semer Khedi to Hadkal Jain | 7.6 | Earth work
225 | PMGSY | V | CGM II | Sagar | Bina | MP 3318 | Berkhedi mafi to Bedai | 4.2 | Earth work
226 | PMGSY | V | CGM II | Sagar | Bina | MP 3318 | SH14 to Padariya | 2.65 | GSB
227 | PMGSY | V | CGM II | Sagar | Bina | MP 3318 | Padariya to Gada | 3 | GSB
228 | PMGSY | V | CGM II | Sagar | Deori | MP 3323 | NH26 Deori to Silari | 1.8 | Earth work
229 | PMGSY | V | CGM II | Sagar | Deori | MP 3323 | NH26 (Km. 251/6) to Charguwan | 2.3 | GSB
230 | PMGSY | V | CGM II | Sagar | Deori | MP 3323 | NH26 (Maharajpur) to Panari | 1.5 | GSB
231 | PMGSY | V | CGM II | Sagar | Deori | MP 3323 | NH26 (Km. 243) to Khamkheda | 1.95 | G2
232 | PMGSY | V | CGM II | Sagar | Jaisinagar | MP 3321 | NH86 to Tahra Tahri | 3.35 | G2
233 | PMGSY | V | CGM II | Sagar | Jaisinagar | MP 3321 | MDR to Dewal chauri | 3 | Earth work
234 | PMGSY | V | CGM II | Sagar | Jaisinagar | MP 3321 | Dewal chauri to Tajpur | 4.1 | Earth work
235 | PMGSY | V | CGM II | Sagar | Jaisinagar | MP 3321 | Dewal chauri to Semra Ghana | 1.15 | Earth work
236 | PMGSY | V | CGM II | Sagar | Malthone | MP 3319 | MDR Malthone-Khimlasa road (Besra Tigdda) to Dugaha Kalan | 20.5 | GSB
237 | PMGSY | V | CGM II | Sagar | Malthone | MP 3319 | Dugaha Kalan to Dugaha Khurd | 1.8 | Earthwork
238 | PMGSY | V | CGM II | Sagar | Malthone | MP 3319 | Dugaha Kalan road (T09) to Kherai | 1.1 | Earth work
239 | PMGSY | V | CGM II | Sagar | Malthone | MP 3319 | Dugaha Kalan road (T09) to Jholsi | 1.5 | Earth work
240 | PMGSY | V | CGM II | Sagar | Rehli | MP 3322 | Garhakota Baleh Road(T04) to Pipriya Digrra | 4.47 | Earth work
241 | PMGSY | V | CGM II | Sagar | Rehli | MP 3322 | Garhakota to Gunjora | 11.225 | G2
242 | PMGSY | V | CGM II | Sagar | Rehli | MP 3322 | Pipariya Digrra to Nareta | 4.15 | GSB
243 | PMGSY | V | CGM II | Sagar | Sagar | MP 3321 | SH14 to Apchand | 3.35 | Earth work
244 | PMGSY | V | CGM II | Sagar | Sagar | MP 3321 | Rajuwa to Amet | 4.1 | Earth work
245 | ADB | I | CGM II | Sehore | Ichhawar | MP 3551 | Ichhawar to Dhablamata | 7.05 | G2
246 | ADB | I | CGM II | Sehore | Ichhawar | MP 3551 | Ichhawar Nadan road to Kalapipal | 3.75 | G2
247 | ADB | I | CGM II | Sehore | Nasrullaganj | MP 3551 | Hameedganj to Piplani | 11.65 | G2
248 | ADB | I | CGM II | Sehore | Sehore | MP 3551 | Jatakheda to Satpipaliya | 3.64 | G2
249 | ADB | III | CGM II | Sehore | Ashta | MP 3553 | Ashta to Mugli | 5.55
250 | ADB | III | CGM II | Sehore | Ashta | MP 3553 | Kachrod Siddiganj road to Jasmat | 2.3
251 | ADB | III | CGM II | Sehore | Ashta | MP 3553 | Khajuriya Kasam to Neelbad | 4.05
252 | ADB | III | CGM II | Sehore | Ashta | MP 3553 | Siddhiganj Main road to Shyampur Magarda | 9.95
253 | ADB | III | CGM II | Sehore | Sehore | MP 3552 | Duraha Ahmedpur road to Mahukheda | 2.2
254 | ADB | III | CGM II | Sehore | Sehore | MP 3552 | Shyampur road Sarkheda | 8.3
255 | ADB | III | CGM II | Sehore | Sehore | MP 3552 | Sehore Shyampur road to Muhali | 4.7
256 | PMGSY | II | CGM II | Sehore | Ashta | MP 05/3502 | Guradiya Verma to Main road | 6.65 | BT 3.9 km
257 | PMGSY | II | CGM II | Sehore | Ichhawar | MP 05/3502 | Dhablarai to Ramnagar | 3 | G3
258 | PMGSY | III | CGM II | Sehore | Budni | MP 3506 | Budni Shahganj road to Bagwada | 0.54 | Not Start
259 | PMGSY | III | CGM II | Sehore | Ichhawar | MP 3505 | Dhablamata to Semlijadeed | 6.5 | G3
260 | PMGSY | IV | CGM II | Sehore | Ashta | MP 3507 | Siddiqganj Main Road to Nowgon | 2.7 | G3
261 | PMGSY | IV | CGM II | Sehore | Ashta | MP 3507 | Indore Road to Fudra | 2.75 | G3
262 | PMGSY | IV | CGM II | Sehore | Ashta | MP 3507 | Astha to khajuriya Kasam | 12.84 | G2
263 | PMGSY | IV | CGM II | Sehore | Ashta | MP 3507 | Khuchrod to Pagaria hat | 5.15 | Earthwork
264 | PMGSY | IV | CGM II | Sehore | Budni | MP 3509 | Amon to Gadar | 2.3 | Earthwork
265 | PMGSY | IV | CGM II | Sehore | Budni | MP 3509 | Baktara Road to Khabada | 3.575 | Earthwork
266 | PMGSY | IV | CGM II | Sehore | Budni | MP 3509 | Baneta plat to Baneta | 1.5 | GSB
267 | PMGSY | IV | CGM II | Sehore | Ichhawar | MP 3508 | Diwadiya to Ramdasi | 3 | GSB
268 | PMGSY | IV | CGM II | Sehore | Nasrullaganj | MP 3508 | Balagaon to Borkheda Kala | 6 | GSB
269 | PMGSY | IV | CGM II | Sehore | Nasrullaganj | MP 3508 | Singpur to Basantpur | 11.5 | GSB
270 | PMGSY | IV | CGM II | Sehore | Nasrullganj | MP 3510 (Sp.) | Rehti main road Kalwana Via Digwad, Shyamgaon, Babri, Dimavar, Chhidgaon Kachi, Chamethi to Chich | 28.552 | G2
271 | PMGSY | IV | CGM II | Sehore | Nasrullganj | MP 3511 (Sp.) | Nasrulla ganj Khategaon rd Via Balagaon, Shohan Khedi, Satdeo, Tingali Mandi, Antraliya to Main rd | 31.86 | G2
272 | PMGSY | IV | CGM II | Sehore | Sehore | MP 3507 | Nipayaniya Kala to Shampur road | 1.83 | G3
273 | PMGSY | IV | CGM II | Sehore | Sehore | MP 3507 | Bamuliya to Shikarpur | 4.3 | Earthwork
274 | PMGSY | IV | CGM II | Sehore | Sehore | MP 3507 | NH0.0012 to Jamoniya khurd | 3.5 | G2
275 | PMGSY | IV | CGM II | Sehore | Sehore | MP 3507 | Barkhedi to Bijlon | 1.65 | GSB
276 | PMGSY | V | CGM II | Sehore | Ashta | MP 3513 | NH-86 to Karman Khedi | 11.55 | G2
277 | PMGSY | V | CGM II | Sehore | Ashta | MP 3513 | Arniya Gaji to Harnawada | 7.3 | G2
278 | PMGSY | V | CGM II | Sehore | Budni | MP 3514 | NH-69 to Maukala | 3.9 | Earth work
279 | PMGSY | V | CGM II | Sehore | Budni | MP 3514 | Rehti to Gondiguradiya | 4.65 | Earth work
280 | PMGSY | V | CGM II | Sehore | Ichhawar | MP 3515 | Ramdasi to Bawdiya gosai | 2.3 | Not start
281 | PMGSY | V | CGM II | Sehore | Ichhawar | MP 3515 | Ichhawar to Divadiya | 11.45 | Earth work
282 | PMGSY | V | CGM II | Sehore | Sehore | MP 3512 | Kachnariya to Dhankhedi | 1 | Not start
283 | PMGSY | V | CGM II | Sehore | Sehore | MP 3512 | Charnal Ahmadpur road (MDR) to Tinoniya | 2.4 | Earth work
284 | PMGSY | V | CGM II | Sehore | Sehore | MP 3512 | Ahmadpur road (MDR) to Charnal | 6.1 | Not start
285 | PMGSY | V | CGM II | Sehore | Sehore | MP 3512 | Charnal Road to Sankla | 2.85 | Earth work
286 | ADB | II | CGM II | Tikamgarh | Jatara | MP 4251 | Jatara-Palera Road to Tanga | 8.5 | Preparatory
287 | ADB | II | CGM II | Tikamgarh | Jatara | MP 4251 | Jatara- Jhansi Road to Varana | 1.26 | GSB
288 | ADB | II | CGM II | Tikamgarh | Jatara | MP 4251 | Varana to Firozpura | 1.2 | GSB
289 | ADB | II | CGM II | Tikamgarh | Jatara | MP 4251 | Lidhora-Digoda Road to Marguvan | 0.75 | GSB
290 | ADB | II | CGM II | Tikamgarh | Jatara | MP 4251 | Lidhora-Digoda Road | 12.4 | Earth Work
291 | ADB | II | CGM II | Tikamgarh | Jatara | MP 4251 | Lidhora-Digoda Road to Matol | 1.38 | GSB
292 | ADB | II | CGM II | Tikamgarh | Jatara | MP 4251 | Lidhora-Digoda Road to Vedau | 2.71 | Not Start
293 | ADB | II | CGM II | Tikamgarh | Jatara | MP 4251 | Lidhora-Digoda Road to Vaidora | 2.8 | GSB
294 | ADB | III | CGM II | Tikamgarh | Jatara | MP 4251 | Kanjna to Udaypura | 9.49 | GSB
295 | ADB | III | CGM II | Tikamgarh | Jatara | MP 4251 | Mauranipur-Jatara Road to Kanjana | 2.6 | GSB
296 | ADB | III | CGM II | Tikamgarh | Jatara | MP 4251 | Kanjana to Babai | 7.2 | Earth work
297 | ADB | III | CGM II | Tikamgarh | Jatara | MP 4251 | Pachora to Pahadi Buzurg | 6.45 | Preparatory
298 | PMGSY | IV | CGM II | Tikamgarh | Jatara | MP 4211 | TKG0Mohangarh road to Madkhera | 3.1 | BT
299 | PMGSY | IV | CGM II | Tikamgarh | Niwari | MP 4212 | Ghugua0Sendri road to Thona | 1.56 | G3
300 | PMGSY | IV | CGM II | Tikamgarh | Niwari | MP 4212 | Mudara Sandri Rado to Kudar | 0.708 | G2
301 | PMGSY | IV | CGM II | Tikamgarh | Niwari | MP 4212 | Gugwa raod to Bhitri | 13.159 | BT
302 | PMGSY | IV | CGM II | Tikamgarh | Palera | MP 4211 | Pahari Bujurg to Veerpur | 2.42 | G3
303 | PMGSY | IV | CGM II | Tikamgarh | Palera | MP 4211 | Nowgaon Rd to Kalora | 3.89 | G3
304 | PMGSY | IV | CGM II | Tikamgarh | Prithvipur | MP 4211 | Birora Khas to Parakhera | 3.8 | BT
305 | PMGSY | V | CGM II | Tikamgarh | Baldeogarh | MP 4215 | Khargapur-Heerapur Road to Patharai | 4.04 | GSB
306 | PMGSY | V | CGM II | Tikamgarh | Baldeogarh | MP 4215 | Khargapur to Kudila | 10.25 | Earth work
307 | PMGSY | V | CGM II | Tikamgarh | Baldeogarh | MP 4215 | Khargapur-Heerapur Road to Manpasar | 2.88 | GSB
308 | PMGSY | V | CGM II | Tikamgarh | Baldeogarh | MP 4215 | Patharai Road to Pharka | 1.75 | GSB
309 | PMGSY | V | CGM II | Tikamgarh | Niwari | MP 4214 | Mudara-Sendri (Ubora) Road to Chachawali | 4.9 | G2
310 | PMGSY | V | CGM II | Tikamgarh | Niwari | MP 4214 | Rprithvipur Orchha Raod to Kummaraha Khas | 5.15 | GSB
311 | PMGSY | V | CGM II | Tikamgarh | Prithvipur | MP 4214 | Prithvipur to Bachhoda | 8.1 | GSB
312 | PMGSY | V | CGM II | Tikamgarh | Tikamgarh | MP 4213 | TKG-Jatara Road to Mamon | 0.81 | GSB
313 | PMGSY | V | CGM II | Tikamgarh | Tikamgarh | MP 4213 | Baldeogarh-Kakarwaha Road to Bhaiswari | 1.75 | Earth work
314 | PMGSY | V | CGM II | Tikamgarh | Tikamgarh | MP 4213 | Dhonga to Maughat | 5.53 | G2
315 | PMGSY | V | CGM II | Tikamgarh | Tikamgarh | MP 4213 | Dhonga Maughat To Hanuman Sagar | 2.85 | Earth work
316 | PMGSY | V | CGM II | Tikamgarh | Tikamgarh | MP 4213 | Hanuman Sagar To Bauri | 1 | Earth work
317 | PMGSY | V | CGM II | Tikamgarh | Tikamgarh | MP 4213 | Baldeogarh-Kakarwaha Road to Umri | 2.66 | Preparatory
318 | PMGSY | V | CGM II | Tikamgarh | Tikamgarh | MP 4213 | Baldeogarh-Kakarwaha Road to Parakhas | 1.47 | Earth work
319 | PMGSY | V | CGM II | Tikamgarh | Tikamgarh | MP 4213 | Tikamgarh Chhatarpur Road to Ranipura | 2.37 | G2
320 | ADB | II | CGM II | Vidisha | Gyaraspur | MP 4551 | NH86 to Sihod | 12 | Earth Work
321 | ADB | II | CGM II | Vidisha | Gyaraspur | MP 4551 | Sihod to Puragusain | 3.5 | Earth Work
322 | ADB | II | CGM II | Vidisha | Gyaraspur | MP 4551 | Siyasi to Gundai | 2.05 | Earth Work
323 | ADB | II | CGM II | Vidisha | Gyaraspur | MP 4551 | Siyasi to Kanjela | 1.25 | Earth Work
324 | ADB | II | CGM II | Vidisha | Nateran | MP 4551 | Phupher to Pairwasa | 6.85 | Preparatory
325 | ADB | II | CGM II | Vidisha | Nateran | MP 4551 | Pairwasa to Rajoda | 2.8 | Preparatory
326 | ADB | II | CGM II | Vidisha | Sironj | MP 4552 | SH-23 TO GARETHA | 16 | Earth Work
327 | ADB | II | CGM II | Vidisha | Sironj | MP 4552 | GARETHA TO PARDHA | 6.2 | Earth Work
328 | ADB | II | CGM II | Vidisha | Sironj | MP 4552 | Korwasa-Banskhedigogal | 2.5 | Earth Work
329 | ADB | III | CGM II | Vidisha | Basoda | MP 4553 | Sh19 To Arnot | 4.75 | Earth work
330 | ADB | III | CGM II | Vidisha | Basoda | MP 4553 | Mdr To Delwara | 1.58 | Preparatory
331 | ADB | III | CGM II | Vidisha | Basoda | MP 4553 | Nh86 To Karari | 10.05 | Preparatory
332 | ADB | III | CGM II | Vidisha | Nateran | MP 4554 | Nateran Golna Rd. To Pipariya | 3.25 | Earth work
333 | ADB | III | CGM II | Vidisha | Nateran | MP 4554 | Sh23 - Karaiya | 1.95 | Earth work
334 | ADB | III | CGM II | Vidisha | Nateran | MP 4554 | Nayagola To Mahukheda | 3.35 | Preparatory
335 | ADB | III | CGM II | Vidisha | Nateran | MP 4554 | Satpada Hat To Lakhar | 4.5 | Earth work
336 | ADB | III | CGM II | Vidisha | Nateran | MP 4554 | Sh 23 To Sadher | 9.6 | Not start
337 | ADB | III | CGM II | Vidisha | Nateran | MP 4554 | Hinotiya Mali To Bader | 7.6 | Not start
338 | PMGSY | IV | CGM II | Vidisha | Lateri | MP 4512 | Moraria to Sherkheda | 7.75 | G3
339 | PMGSY | IV | CGM II | Vidisha | Nateran | MP 4511 | SH019 to Phupher | 9.6 | BT
340 | PMGSY | IV | CGM II | Vidisha | Vidisha | MP 4511 | Pipelkheda to Sanoti | 4.9 | BT
341 | PMGSY | V | CGM II | Vidisha | Karkeli | MP 4405 | NH 78 to Pathari | 2.9 | Preparatory
342 | PMGSY | V | CGM II | Vidisha | Karkeli | MP 4405 | Umariya to Kachharwar | 11.75 | G2
343 | PMGSY | V | CGM II | Vidisha | KURWAI | MP 4514 | Sh-19 to karai Berkhedi | 5.5 | Earth work
344 | PMGSY | V | CGM II | Vidisha | KURWAI | MP 4514 | Malhargarh Rd. to Naukund | 1.1 | GSB
345 | PMGSY | V | CGM II | Vidisha | KURWAI | MP 4514 | Kulhan to Pitholi | 4.1 | Earth work
346 | PMGSY | V | CGM II | Vidisha | KURWAI | MP 4514 | Kulhan to Pitholi | 4.1 | Earth work
347 | PMGSY | V | CGM II | Vidisha | LATERI | MP 4513 | SH-14 to Kachikheda | 11.03 | Earth work
348 | PMGSY | V | CGM II | Vidisha | Vidisha | MP 4513 | MDR(T08) to Dhamnoda | 10.3 | Earth work
349 | PMGSY | V | CGM II | Vidisha | Vidisha | MP 4513 | Dhamnoda to Pauwanala | 2 | Earth work
350 | PMGSY | V | CGM II | Vidisha | VIDISHA | MP 4514 | Shamshabad rd. to Sejakhedi | 3.65 | GSB
Total II
1 | ADB | II | CGM III | Barwani | Niwali | MP 0252 | A.B. Road to Pipaldhar | 3.25 | Preparatory
2 | ADB | II | CGM III | Barwani | Niwali | MP 0252 | Sendhwa - Niwali Road to Kannadgaon | 3.38 | G2
3 | ADB | II | CGM III | Barwani | Niwali | MP 0252 | Sendhwa - Palsud Road to Bhulgaon | 4.105 | G2
4 | ADB | II | CGM III | Barwani | Pansemal | MP 0252 | Pansemal Ghtya Road to Bandhara Khurd | 4 | Earth Work
5 | ADB | II | CGM III | Barwani | Pansemal | MP 0252 | Pansemal to Ghtya (Bandhara Khurd Fata ) | 3 | Earth Work
6 | ADB | II | CGM III | Barwani | Sendhwa | MP 0251 | Sendhwa - Verla Road to Mordad | 7.4 | G2
7 | ADB | II | CGM III | Barwani | Sendhwa | MP 0251 | A.B. Road (Mehatgaon) to Ramkola Fata | 16.5 | Not Start
8 | ADB | II | CGM III | Barwani | Sendhwa | MP 0251 | Ramkola Fata to Ramkola | 3.63 | G2
9 | ADB | II | CGM III | Barwani | Sendhwa | MP 0251 | Dhanora to Ralawati | 4.15 | GSB
10 | ADB | III | CGM III | Barwani | Pati | MP 0254 | Barwani Pati Bokrata Road to Kalakhet | 4.5 | Not start
11 | ADB | III | CGM III | Barwani | Pati | MP 0254 | Gnadhaval Ranipura Road to Berda | 7.31 | Earth work
12 | ADB | III | CGM III | Barwani | Pati | MP 0254 | Palvat Gnandhaval Road to Chikalkunwavadi | 5.55 | Earth work
13 | ADB | III | CGM III | Barwani | Pati | MP 0254 | Valan Mosvara Phata to Mosvara | 4 | Not start
14 | ADB | III | CGM III | Barwani | Pati | MP 0254 | Pati to Valan | 4.8 | Preparatory
15 | ADB | III | CGM III | Barwani | Pati | MP 0254 | Kiradi Phata to Kiradi | 1.5 | Not start
16 | ADB | III | CGM III | Barwani | Pati | MP 0254 | Dongargaon to Panchgaon | 4.2 | Not start
17 | ADB | III | CGM III | Barwani | Sendhwa | MP 0255 | Sendhwa to Navalpura | 2.12 | GSB
18 | ADB | III | CGM III | Barwani | Sendhwa | MP 0255 | Jhapdi Padla to Pipliya Deb | 7.65 | Not start
19 | ADB | III | CGM III | Barwani | Sendhwa | MP 0255 | G.K. Road Phata to Thigli | 2.4 | Preparatory
20 | ADB | III | CGM III | Barwani | Sendhwa | MP 0255 | Dhavli to Panjriya | 5 | GSB
21 | ADB | III | CGM III | Barwani | Thikri | MP 0253 | Mandil to Sakad | 1.4 | GSB
22 | ADB | III | CGM III | Barwani | Thikri | MP 0253 | Devli to Ghatti | 0.88 | GSB
23 | ADB | III | CGM III | Barwani | Thikri | MP 0253 | A.B. Road to Golaniya | 3.39 | Earth work
24 | ADB | III | CGM III | Barwani | Thikri | MP 0253 | Khurampura to Devada | 3.64 | Earth work
25 | ADB | III | CGM III | Barwani | Thikri | MP 0253 | ATT Road to Umarda | 1.81 | GSB
26 | PMGSY | III | CGM III | Barwani | Rajpur | MP 0206 | Matli to Upla Fata Road | 8.6 | MPM/MSS in progress
27 | PMGSY | IV | CGM III | Barwani | Barwani | MP 0210 | Manimata to Sustikheda Road | 5.1 | BT 3km
28 | PMGSY | IV | CGM III | Barwani | Niwali | MP 0209 | Godiya Pani to Zirimata Road | 4.9 | G2
29 | PMGSY | IV | CGM III | Barwani | Pansemal | MP 0209 | Junction ODR Rakhi Khurd | 1.7 | GSB
30 | PMGSY | IV | CGM III | Barwani | Rajpur | MP 0209 | Chotariya App. Road | 2.75 | G3
31 | PMGSY | IV | CGM III | Barwani | Rajpur | MP 0209 | Nandgaon to Sewai Road | 2.88 | G3
32 | PMGSY | IV | CGM III | Barwani | Sendhwa | MP 0208 | Bharampura to Julbaniya Road | 5.85 | Deleted
33 | PMGSY | V | CGM III | Barwani | Barwani | MP 0211 | Barwani Pati Rad to Amlyapani | 1.8 | Gsb
34 | PMGSY | V | CGM III | Barwani | Barwani | MP 0211 | Silawad Palsud Road to Rehgun (Silawad) | 3.15 | G2
35 | PMGSY | V | CGM III | Barwani | Rajpur | MP 0211 | A.B. Road (Lingwa) to Kusmari | 3.35 | G2
36 | PMGSY | V | CGM III | Barwani | Rajpur | MP 0211 | Nagalwadi Segaon Road to Nagal wadi Khurd | 1.22 | Gsb
37 | PMGSY | V | CGM III | Barwani | Rajpur | MP 0211 | Khandwa Baroda Road to Mandil | 1.5 | Gsb
38 | ADB | II | CGM III | Dewas | Kannod | MP 1052 | MDR (T-01) to Heerapur | 4.4 | Not Start
39 | ADB | II | CGM III | Dewas | Kannod | MP 1052 | MDR to Balya | 4 | GSB
40 | ADB | II | CGM III | Dewas | Khategaon | MP 1052 | Khategaon to Barchha Buzurg | 2.8 | G2
41 | ADB | II | CGM III | Dewas | Khategaon | MP 1052 | MDR to Rajor | 9.593 | G2
42 | ADB | II | CGM III | Dewas | Sonkachh | MP 1051 | Ghichalai to Jolay | 6.5 | GSB
43 | ADB | II | CGM III | Dewas | Sonkachh | MP 1051 | Anabad to Bhutiya Khurd | 5.63 | G2
44 | ADB | III | CGM III | Dewas | Bagli | MP 1053 | Ratanpur to Nimanpur | 4.1 | Earth work
45 | ADB | III | CGM III | Dewas | Bagli | MP 1053 | Ismaikhedi to Kanjhar | 4.25 | Earth work
46 | ADB | III | CGM III | Dewas | Bagli | MP 1053 | Nawari Rd. to Rojadi | 2.55 | Earth work
47 | ADB | III | CGM III | Dewas | Bagli | MP 1053 | Bagli to Guwadi | 9 | Earth work
48 | ADB | III | CGM III | Dewas | Kannod | MP 1053 | Ratway to Dokakoi | 2.85 | Earth work
49 | ADB | III | CGM III | Dewas | Kannod | MP 1053 | Panigaon to Mawada | 5.33 | Preparatory
50 | ADB | III | CGM III | Dewas | Kannod | MP 1053 | MDR to Bamnikhurd | 3 | Preparatory
51 | PMGSY | V | CGM III | Dewas | Bagli | MP 1011 | Bagli to Dhavdiya | 8.6 | BT
52 | PMGSY | V | CGM III | Dewas | Bagli | MP 1011 | Pipri to Potla | 5 | GSB
53 | PMGSY | V | CGM III | Dewas | Dewas | MP 1010 | Vijayagang Mandi (T-03) Road to Sindni | 3.1 | BT
54 | PMGSY | V | CGM III | Dewas | Dewas | MP 1010 | NH-89 To Awilya Pipliya | 5.3 | BT
55 | PMGSY | V | CGM III | Dewas | Dewas | MP 1010 | Awliya Pipliya to Pipliya Rao | 2.28 | Gsb
56 | PMGSY | V | CGM III | Dewas | Dewas | MP 1010 | Vijayagang Mandi (T-03) Road to Barkheda Kayam | 2.9 | Earthwork
57 | PMGSY | V | CGM III | Dewas | TonkKhurd | MP 1010 | Eklara to Mundla Dangi | 5.35 | Gsb
58 | PMGSY | V | CGM III | Dewas | TonkKhurd | MP 1010 | Illaiskhedi to Balon | 4.9 | Earthwork
59 | PMGSY | V | CGM III | Dewas | TonkKhurd | MP 1010 | NH-3 to Fatanpur | 5.2 | BT
60 | ADB | II | CGM III | Dhar | Badnawar | MP 1151 | Indrawal Bidwal Road(T-07) to Chirakhan | 9.3 | Earth Work
61 | ADB | II | CGM III | Dhar | Badnawar | MP 1151 | T-01(Badnawar to Kachibadod) to Karoda | 13.75 | Earth Work
62 | ADB | II | CGM III | Dhar | Sardarpur | MP 1152 | Jolana to Dedla | 9 | Earth Work
63 | ADB | II | CGM III | Dhar | Sardarpur | MP 1152 | Rajod to Runni | 7.1 | GSB
64 | ADB | II | CGM III | Dhar | Sardarpur | MP 1152 | Hanumantiya (Sajod) to Kherkheda | 3.2 | Earth Work
65 | ADB | III | CGM III | Dhar | Badnawar | MP 1158 | Mogrwa to Amkho | 10.2
66 | ADB | III | CGM III | Dhar | Bagh | MP 1153 | Kukshi Ragarh road to kudujitta to Pipri | 5.05
67 | ADB | III | CGM III | Dhar | Bagh | MP 1153 | Jamniyapura to Abalda Jobat road | 3.4
68 | ADB | III | CGM III | Dhar | Bagh | MP 1153 | Rjgarh Kukshi road to jali | 5.85
69 | ADB | III | CGM III | Dhar | Bagh | MP 1153 | Tanda jirabad road to Magdi | 2.1
70 | ADB | III | CGM III | Dhar | Bagh | MP 1153 | Rajgarh Kukshi road to Dobni | 5
71 | ADB | III | CGM III | Dhar | Bagh | MP 1153 | Rajgarh Kukshi road toTanda Barda | 2.25
72 | ADB | III | CGM III | Dhar | Dhar | MP 1157 | Gola to Rampur | 4
73 | ADB | III | CGM III | Dhar | Dhar | MP 1157 | Approach road to Khildi | 17.6
74 | ADB | III | CGM III | Dhar | Gandhwani | MP 1154 | Gandhwani to Soyala | 6
75 | ADB | III | CGM III | Dhar | Gandhwani | MP 1154 | Gandhwani kukshi road to Raipuriya | 3.9
76 | ADB | III | CGM III | Dhar | Gandhwani | MP 1154 | Abalda Bagh road to Malehra | 1.55
77 | ADB | III | CGM III | Dhar | Gandhwani | MP 1154 | Manawar Dehri road to Sendla | 3
78 | ADB | III | CGM III | Dhar | Gandhwani | MP 1154 | Jeera Bad Tanda Road to Puragram | 4.25
79 | ADB | III | CGM III | Dhar | Gandhwani | MP 1156 | Amjhera sardarpur rd to Panchpipliya | 6.5
80 | ADB | III | CGM III | Dhar | Gandhwani | MP 1156 | Amjhera sardarpur rd to Chalni | 4.21
81 | ADB | III | CGM III | Dhar | Nalcha | MP 1158 | NH 59 to Kumakaradiya | 4
82 | ADB | III | CGM III | Dhar | Nisarpur | MP 1154 | Kukshi Sighana road to Barda | 5.21
83 | ADB | III | CGM III | Dhar | Nisarpur | MP 1154 | Kukshi Sighana road to Dhukni | 3.78
84 | ADB | III | CGM III | Dhar | Sardarpur | MP 1156 | Sardarpur Badnabar rd to Molana | 2.1
85 | ADB | III | CGM III | Dhar | Sardarpur | MP 1156 | Labriya Dasai road to Sinduriya | 7.5
86 | ADB | III | CGM III | Dhar | Sardarpur | MP 1156 | Labriya Dasai road | 21.3
87 | ADB | III | CGM III | Dhar | Sardarpur | MP 1156 | Labriya Dasai road To Akoliya | 2.1
88 | ADB | III | CGM III | Dhar | Tirla | MP 1155 | Khedi kua to Latamali | 1.75
89 | ADB | III | CGM III | Dhar | Tirla | MP 1158 | Chandawead to Simlawada | 3.68
90 | ADB | III | CGM III | Dhar | Umarban | MP 1155 | Umarban Ukala road to Karodiyakhurd | 8.45
91 | ADB | III | CGM III | Dhar | Umarban | MP 1155 | Sakaldato Karodiya Mota | 3
92 | ADB | III | CGM III | Dhar | Umarban | MP 1155 | Pipliya Mota to Amsi | 4.6
93 | ADB | III | CGM III | Dhar | Umarban | MP 1155 | Narsingh fata to Chowki | 4.9
94 | ADB | III | CGM III | Dhar | Umarban | MP 1159 | Manawar Khalghat road to Dedgaon | 2.2
95 | ADB | III | CGM III | Dhar | Umarban | MP 1159 | Manawar Dhamnod road to Dhanora | 5.43
96 | ADB | III | CGM III | Dhar | Umarban | MP 1159 | Bhanpura to Kherwa Dasai | 9.35
97 | ADB | III | CGM III | Dhar | Umarban | MP 1159 | Bakaner to Dhankhedi | 4.65
98 | PMGSY | III | CGM III | Dhar | Nisarpur | MP 1113 | Bhawriya to SH26 Road | 1 | deleted
99 | PMGSY | IV | CGM III | Dhar | Bagh | MP 1119 | Khaniamba to Tanda Bori Road | 2.24 | G3
100 | PMGSY | IV | CGM III | Dhar | Bagh | MP 1119 | Padliya to Awalda Jobat Road | 6 | G3
101 | PMGSY | IV | CGM III | Dhar | Bagh | MP 1119 | Kati (Chijwa) Ghatbori Narwali Road | 5.4 | BT
102 | PMGSY | IV | CGM III | Dhar | Dahi | MP 1118 | Narjhali to Tanda Road | 4.5 | BT
103 | PMGSY | IV | CGM III | Dhar | Kukshi | MP 1118 | Ashapur to Kukshi Rajgarh Road | 5.83 | G2
104 | PMGSY | IV | CGM III | Dhar | Kukshi | MP 1118 | Jhardi to Longasari Road | 5.4 | G3
105 | PMGSY | IV | CGM III | Dhar | Nisarpur | MP 1118 | Chiprata Approach Road | 11.44 | BT
106 | PMGSY | IV | CGM III | Dhar | Tirla | MP 1116 | Ukala to Kheri Road | 8.61 | BT
107 | PMGSY | V | CGM III | Dhar | Dahi | MP 1122 | T-05 (Dahi Kharbat Road) to Devadha (Vya Kikarwas) | 5.15 | G2
108 | PMGSY | V | CGM III | Dhar | Dahi | MP 1122 | Timariya Fata (Dahi - Arada road) to Malpura | 6 | Earthwork
109 | PMGSY | V | CGM III | Dhar | Dahi | MP 1122 | T05 to Kotaba Road | 2.1 | Not start
110 | PMGSY | V | CGM III | Dhar | Dahi | MP 1122 | T05 to Khatami Road | 3 | Not start
111 | PMGSY | V | CGM III | Dhar | Dahi | MP 1122 | T05 to Panhal Road | 4.8 | Not start
112 | PMGSY | V | CGM III | Dhar | Dahi | MP 1122 | T05 to Chandiapipla | 2.15 | Earthwork
113 | PMGSY | V | CGM III | Dhar | Dharampuri | MP 1120 | Kachwaniya to Sarjapur | 2.6 | Gsb
114 | PMGSY | V | CGM III | Dhar | Dharampuri | MP 1120 | I. T. I.Dhamnod to Palasiya | 2.4 | Gsb
115 | PMGSY | V | CGM III | Dhar | Dharampuri | MP 1120 | A. B. Road to Lodhipura | 1.2 | Earthwork
116 | PMGSY | V | CGM III | Dhar | Dharampuri | MP 1120 | Dudhi(A.B. Road) to Kunda | 3 | Preparatory
117 | PMGSY | V | CGM III | Dhar | Kukshi | MP 1121 | Khandwa Baroda Road (SH26) to Haldi | 2.88 | Preparatory
118 | PMGSY | V | CGM III | Dhar | Kukshi | MP 1121 | SH26 to Aawali | 8.25 | Gsb
119 | PMGSY | V | CGM III | Dhar | Kukshi | MP 1121 | Kawadiyakheda to Akhada (T-06) | 9.85 | Earthwork
120 | PMGSY | V | CGM III | Dhar | Kukshi | MP 1121 | Kawadiyakheda Akhada (T06) to Kanheribhatyari | 1.05 | Preparatory
121 | PMGSY | V | CGM III | Dhar | Kukshi | MP 1121 | Kawadiyakheda Akhada (T06) to Jogardi | 0.9 | Preparatory
122 | PMGSY | V | CGM III | Dhar | Kukshi | MP 1121 | Kawadiyakheda Akhada (T06) to Khandlai | 4.13 | Preparatory
123 | PMGSY | V | CGM III | Dhar | Kukshi | MP 1121 | Kawadiyakheda Akhada (T06) to Kherwa | 6.63 | Gsb
124 | PMGSY | V | CGM III | Dhar | Manawar | MP 1120 | Tonki Rajukheri Road to Mohali | 3.53 | Earthwork
125 | PMGSY | V | CGM III | Dhar | Manawar | MP 1120 | T-01(Rajukhedi to Tonki Fata Road) | 3 | Earthwork
126 | PMGSY | V | CGM III | Dhar | Manawar | MP 1120 | Deora(Manawar - Mangod Road) to Sitapuri | 4.36 | Not start
127 | PMGSY | V | CGM III | Dhar | Manawar | MP 1120 | Khandlai to Udiapur | 2.2 | Not start
128 | PMGSY | IV | CGM III | Indore | Depalpur | MP 1708 | Katkoda0Karjoda to Banectya | 5.45 | Earth work
129 | PMGSY | V | CGM III | Indore | Depalpur | MP 1710 | Chandan Khedi to Rudrakhiya | 4.6 | Earthwork
130 | PMGSY | V | CGM III | Indore | Depalpur | MP 1710 | Depalpur -Gautampura Road to kai | 3.5 | Earthwork
131 | PMGSY | V | CGM III | Indore | Depalpur | MP 1710 | Depalpur to Bhidota | 8.6 | Earthwork
132 | PMGSY | V | CGM III | Indore | Indore | MP 1709 | Bada Bangarda to Palakhedi ( upto Industrial area ) | 10.22 | GSB
133 | PMGSY | V | CGM III | Indore | Indore | MP 1709 | Nemawar Road to Gehli | 0.9 | Earthwork
134 | PMGSY | V | CGM III | Indore | Sanwer | MP 1709 | Kachhaliya to Khalkhala | 6.2 | Preparatory
135 | PMGSY | V | CGM III | Indore | Sanwer | MP 1709 | Sanwer to Kachaliya | 13.2 | Preparatory
136 | ADB | I | CGM III | Jhabua | Jhabua | MP 1951 | Kothada Bhoiara App. Road | 3.75 | GSB
137 | ADB | I | CGM III | Jhabua | Jhabua | MP 1951 | Jhayada App. Road | 2.5 | G2
138 | ADB | I | CGM III | Jhabua | Jhabua | MP 1952 | Gopalpura App. Road | 2 | G2
139 | ADB | I | CGM III | Jhabua | Jhabua | MP 1952 | Bisoli App. Road | 3.5 | G3
140 | ADB | I | CGM III | Jhabua | Meghnagar | MP 1952 | Talai App. Road | 5.2 | GSB
141 | ADB | I | CGM III | Jhabua | Meghnagar | MP 1952 | Rajpura App. Road | 7.05 | G2
142 | ADB | I | CGM III | Jhabua | Meghnagar | MP 1952 | S. H. 18 to Pach Pipliya App. Road | 4.35 | Earth work
143 | ADB | I | CGM III | Jhabua | Rama | MP 1951 | Piliya Khandan App. Road | 3.55 | BT
144 | ADB | I | CGM III | Jhabua | Rama | MP 1952 | Kakadua App. Road | 4.6 | G2
145 | ADB | I | CGM III | Jhabua | Ranapur | MP 1951 | Padlwa App. Road | 1.85 | GSB
146 | ADB | I | CGM III | Jhabua | Ranapur | MP 1951 | Agera Digi Dholiyawad App. Road | 12.35 | G3
147 | ADB | III | CGM III | Jhabua | Alirajpur | MP 1954 | S.H.26 to Morasa | 4.65 | Earth work
148 | ADB | III | CGM III | Jhabua | Alirajpur | MP 1954 | Alirajpur Dahod Road to Bund | 10.525 | Earth work
149 | ADB | III | CGM III | Jhabua | Alirajpur | MP 1954 | Jobat Nanpur to Machhliya Road | 5.9 | Earth work
150 | ADB | III | CGM III | Jhabua | Alirajpur | MP 1954 | Machhliya App. Road to Dholkheda road | 0.75 | Not start
151 | ADB | III | CGM III | Jhabua | Alirajpur | MP 1954 | S.H. 26 to Kharkua Road | 6.962 | GSB
152 | ADB | III | CGM III | Jhabua | Alirajpur | MP 1954 | Laxmani Fata Road | 3.802 | Earth work
153 | ADB | III | CGM III | Jhabua | Jobat | MP 1955 | Jobat Kadawal Road To Nehtada | 5.75 | Earth work
154 | ADB | III | CGM III | Jhabua | Jobat | MP 1955 | Jobat Kadawal Road | 6.95 | Earth work
155 | ADB | III | CGM III | Jhabua | Jobat | MP 1955 | Jobat Kadwal Road To Wagdi | 1.895 | Earth work
156 | ADB | III | CGM III | Jhabua | Kathiwada | MP 1953 | SH 26 to Mordhi | 2.901 | GSB
157 | ADB | III | CGM III | Jhabua | Kathiwada | MP 1953 | Alirajpur Mathwad Road To Phoolmal | 19.401 | Earth work
158 | ADB | III | CGM III | Jhabua | Meghnagar | MP 1958 | Thandla Limdi Road To Itawa | 1.6 | Preparatory
159 | ADB | III | CGM III | Jhabua | Meghnagar | MP 1958 | Meghnagar Madrani Road to Dhadhniya | 8.829 | Preparatory
160 | ADB | III | CGM III | Jhabua | Meghnagar | MP 1958 | Meghnagar Madrani Road 0 To 10 km (Improvement) | 11.275 | Not start
161 | ADB | III | CGM III | Jhabua | Meghnagar | MP 1958 | Meghnagar Madrani Road to Jharadabar | 2.1 | Earth work
162 | ADB | III | CGM III | Jhabua | Meghnagar | MP 1958 | Meghnagar Madrani Road to Bada Ghosliya | 5.615 | Earth work
163 | ADB | III | CGM III | Jhabua | Petlawad | MP 1959 | SH 18 To Naharpura | 3.441 | Earth work
164 | ADB | III | CGM III | Jhabua | Petlawad | MP 1959 | Bani To Samli | 2.901 | Earth work
165 | ADB | III | CGM III | Jhabua | Petlawad | MP 1959 | Umarkot - Tarkhedi Raipuriya Road Km 24/10 To Panas | 3.301 | Preparatory
166 | ADB | III | CGM III | Jhabua | Rama | MP 1957 | NH - 59 (Kali Devi) To Bochka | 12.2 | Earth work
167 | ADB | III | CGM III | Jhabua | Rama | MP 1957 | Bochka App. Road To Mrigaruadi | 4.925 | Not start
168 | ADB | III | CGM III | Jhabua | Rama | MP 1957 | Ranapur Datigati Road to Mahudipada | 1.05 | Not start
169 | ADB | III | CGM III | Jhabua | Rama | MP 1957 | Umarkot road to Amlipada | 5.31 | Not start
170 | ADB | III | CGM III | Jhabua | Rama | MP 1957 | Dattigaon to Umarkot Road | 8 | Not start
171 | ADB | III | CGM III | Jhabua | Ranapur | MP 1956 | Ranapur Dattighati Road To Waglawat Mohaniya | 6.95 | Earth work
172 | ADB | III | CGM III | Jhabua | Ranapur | MP 1956 | Ranapur Dattighati Road | 1.95 | Not start
173 | ADB | III | CGM III | Jhabua | Ranapur | MP 1956 | Kanjawani App. Road to Mandlinathu | 1.775 | Not start
174 | ADB | III | CGM III | Jhabua | Ranapur | MP 1956 | Mandlinathu App. Road to Sotiyajalam | 3 | Not start
175 | ADB | III | CGM III | Jhabua | Ranapur | MP 1956 | Jhabua- Jobat Road | 2.76 | Not start
176 | ADB | III | CGM III | Jhabua | Ranapur | MP 1956 | Ranapur Dattighati Road To Bhurimati | 2.3 | Not start
177 | ADB | III | CGM III | Jhabua | Ranapur | MP 1956 | Bhurimati app. Road to Dhamnikatara | 1.2 | Earth work
178 | ADB | III | CGM III | Jhabua | Sondwa | MP 1953 | Moraji App. Road | 3 | Earth work
179 | ADB | III | CGM III | Jhabua | Sondwa | MP 1953 | Temla Approach Road | 5.251 | GSB
180 | ADB | III | CGM III | Jhabua | Sondwa | MP 1953 | Bicholi Approch Road | 5.0751 | Earth work
181 | ADB | III | CGM III | Jhabua | Udaygarh | MP 1955 | Alirajpur Dahod Road to Tokariya Ziran | 5 | Not start
182 | ADB | III | CGM III | Jhabua | Udaygarh | MP 1955 | Behadwa Tokriya Ziran Road To Katkuan | 3.45 | Not start
183 | ADB | III | CGM III | Jhabua | Udaygarh | MP 1955 | Akoli Barjhard road to Chota Itara | 1.885 | Not start
184 | ADB | III | CGM III | Jhabua | Udaygarh | MP 1955 | Akoli Barjhard road | 2.552 | not start
185 | ADB | III | CGM III | Jhabua | Udaygarh | MP 1955 | Para Bori road to Ambha Khedi | 2.4 | Not start
186 | ADB | III | CGM III | Jhabua | Udaygarh | MP 1955 | Para Bori road to Budkui Badi | 2.5753 | Not start
187 | ADB | III | CGM III | Jhabua | Udaygarh | MP 1955 | Udayagarh Bhabra road to Talawad | 2.793 | Not start
188 | PMGSY | IV | CGM III | Jhabua | Alirajpur | MP 1910 | Gawahan to Chichalguda road | 4.68 | GSB
189 | PMGSY | IV | CGM III | Jhabua | Jhabua | MP 1912 | Negadla to Antarvelia fata | 7.1 | GSB
190 | PMGSY | IV | CGM III | Jhabua | Jobat | MP 1911 | Indvan to Salkheda Road | 2.73 | G2
191 | PMGSY | IV | CGM III | Jhabua | Jobat | MP 1911 | Ranjitgarh to Bagh Jobat Ambua Road | 6.21 | Forest
192 | PMGSY | IV | CGM III | Jhabua | Meghnagar | MP 1912 | Satsera to Gwali Meghnagar road | 6.29 | BT
193 | PMGSY | IV | CGM III | Jhabua | Petlawad | MP 1913 | Devali to Petlawad Raod | 21.82 | BT
194 | PMGSY | IV | CGM III | Jhabua | Rama | MP 1912 | Bawdi to Amba Dattighati road | 2 | GSB
195 | PMGSY | IV | CGM III | Jhabua | Sondwa | MP 1910 | Keldi Ki mal to Alirajpur Mathwad Rd. | 4.32 | BT
196 | PMGSY | IV | CGM III | Jhabua | Thandla | MP 1913 | Latpura to Morjhari Road | 1.7 | G2
197 | PMGSY | V | CGM III | Jhabua | Bhabra | MP 1915 | Barjhar To Mahendra | 3.2 | Earthwork
198 | PMGSY | V | CGM III | Jhabua | Bhabra | MP 1915 | Barjhar Mahendra Rd. To Borkundiya | 3.85 | Preparatory
199 | PMGSY | V | CGM III | Jhabua | Bhabra | MP 1915 | Alirajpur -Dahod To Girdha | 3.5 | GSB
200 | PMGSY | V | CGM III | Jhabua | Bhabra | MP 1915 | Girdha App. Road To Mayawat | 8.9 | Earthwork
201 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1916 | NH - 59 to Bheem Falia | 1.25 | Preparatory
202 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1916 | NH - 59 to Parwat | 4.73 | G3
203 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1916 | NH - 59 - Parwat Road To Hadmatia | 1.1 | Gsb
204 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1916 | Jhabua Jobat Road to Sajwani Chhoti | 9.19 | Earthwork
205 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1917 | SH - 18 To Mohanpura | 2.6 | GSB
206 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1917 | SH - 18 To Jousar | 2.55 | G2
207 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1917 | Bamniya - Petlawad Raipuriya Road To Asaliya | 4.28 | G2
208 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1917 | karwad - Ratlam To Mor | 0.97 | Preparatory
209 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1917 | Bamniya to Talawada Road | 19.45 | Preparatory
210 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1917 | Bamniya Talawada Road to Kukdi Pada Road | 1.35 | Preparatory
211 | PMGSY | V | CGM III | Jhabua | Jhabua | MP 1917 | Bamniya Talawada Road to Naharpura Road | 4.6 | Gsb
212 | PMGSY | V | CGM III | Jhabua | Sondwa | MP 1914 | Walpur Phadtala road to Bhordiya | 13.18 | Earthwork
213 | PMGSY | V | CGM III | Jhabua | Sondwa | MP 1914 | Choti Hatwi App Road to Ravdi | 3.225 | Earthwork
214 | PMGSY | V | CGM III | Jhabua | Sondwa | MP 1914 | Walpur Delwani Road to Bhordiya Soliya | 4 | Earthwork
215 | PMGSY | V | CGM III | Jhabua | Sondwa Alirajpur | MP 1914 | Walpur Delwani Alirajpur Road to Choti Hathwi | 7.7 | Earthwork
216 | PMGSY | III | CGM III | Khandwa | Burhanpur | MP 2104 | Dhuwati to Amba | 11.35 | G3
217 | PMGSY | IV | CGM III | Khandwa | Baldi | MP 2108 | Pam Khedi Approach Road | 2.8 | GSB
218 | PMGSY | IV | CGM III | Khandwa | Baldi | MP 2108 | Kukshi Ryt. Approach Road | 4.8 | G2
219 | PMGSY | IV | CGM III | Khandwa | Burhanpur | MP 2109 | Dhamngaon Borsal Road | 3.15 | G2
220 | PMGSY | IV | CGM III | Khandwa | Burhanpur | MP 2109 | Badziri Approach Road | 2.2 | G3
221 | PMGSY | IV | CGM III | Khandwa | Harsud | MP 2108 | Rampuri Ryt.Approach Road | 3 | G2
222 | PMGSY | IV | CGM III | Khandwa | Harsud | MP 2108 | Saktapur0Chhanera Road | 3.1 | G3
223 | PMGSY | IV | CGM III | Khandwa | Khaknar | MP 2109 | Rangai to Temri Road | 5.45 | G2
224 | PMGSY | IV | CGM III | Khandwa | Khaknar | MP 2109 | Nawatha to Ambda Road | 9.25 | G2
225 | PMGSY | IV | CGM III | Khandwa | Khalwa | MP 2108 | Karpur 0Zirpa Road | 8.45 | Not started
226 | PMGSY | IV | CGM III | Khandwa | Khalwa | MP 2108 | Gogai Pura Approach Road | 1.2 | GSB
227 | PMGSY | IV | CGM III | Khandwa | Khandwa | MP 2107 | Bijora Bhil Dhoudhwada | 2.55 | Earth work
228 | PMGSY | IV | CGM III | Khandwa | Pandhana | MP 2109 | Jamli Rajgarh to Diwal Road | 2.85 | G2
229 | PMGSY | IV | CGM III | Khandwa | Punasa | MP 2107 | Jamny(Mundi) Dhudwasa | 4.1 | G2
230 | PMGSY | IV | CGM III | Khandwa | Punasa | MP 2107 | Gulgaon Ryt.Approach Road | 3.6 | G3
231 | PMGSY | V | CGM III | Khandwa | Burhanpur | MP 2111 | Indore-Icchapur Road(from Machal) to Khamla | 14.4 | G2
232 | PMGSY | V | CGM III | Khandwa | Burhanpur | MP 2111 | Machalpur Khamla road to Badi | 2.6 | Earthwork
233 | PMGSY | V | CGM III | Khandwa | Burhanpur | MP 2111 | Jhiri to Jhanjhar | 1.6 | Preparatory
234 | PMGSY | V | CGM III | Khandwa | Burhanpur | MP 2111 | Bori Bujrg to Rohni | 2.8 | Preparatory
235 | PMGSY | V | CGM III | Khandwa | Khaknar | MP 2111 | Dahinda to Ramkheda Kalan | 2.1 | G2
236 | PMGSY | V | CGM III | Khandwa | Khaknar | MP 2111 | Ramkheda Kalan-Badikheda Road to Amulla Kalan | 4.15 | Preparatory
237 | PMGSY | V | CGM III | Khandwa | Khaknar | MP 2111 | Dabali Ryt to Amullakala phata | 6.3 | GsB
238 | PMGSY | V | CGM III | Khandwa | Khandwa | MP 2110 | Khandwa-Hoshangabad Road to Benipura Kunwada | 5.75 | Preparatory
239 | PMGSY | V | CGM III | Khandwa | Khandwa | MP 2112 | Khalwa-Kerwani to Kumhar Kheda | 3 | Preparatory
240 | PMGSY | V | CGM III | Khandwa | Khandwa | MP 2112 | Khalwa to Kerwani | 13.85 | Preparatory
241 | PMGSY | V | CGM III | Khandwa | Khandwa | MP 2112 | Khalwa-Kerwani to Khota Ryt | 1.1 | Preparatory
242 | PMGSY | V | CGM III | Khandwa | Khandwa | MP 2112 | Khalwa-Kerwani to Khari | 2.5 | Preparatory
243 | PMGSY | V | CGM III | Khandwa | Punasa | MP 2110 | Dhamangaon No.1 Road (PMGSY) to Makadkachha | 2.7 | Earthwork
244 | PMGSY | V | CGM III | Khandwa | Punasa | MP 2110 | Dhamangaon No.1 to Bijapur | 3.55 | Preparatory
245 | PMGSY | V | CGM III | Khandwa | Punasa | MP 2110 | Dhamangaon No.1 to Badnagar Ryt. | 4.67 | Preparatory
246 | PMGSY | V | CGM III | Khandwa | Punasa | MP 2110 | Mundi-Punasa Road (from Bangarda) to Rohni | 5.48 | GsB
247 | PMGSY | V | CGM III | Khandwa | Punasa | MP 2110 | Rohni to Utadi | 2 | GsB
248 | PMGSY | V | CGM III | Khandwa | Punasa | MP 2110 | Bangarda-Rohni Road to Palsood Ryt. | 2.5 | GsB
249 | ADB | III | CGM III | Khargone | Bhagwanpura | MP 2251 | Mohanpura to Heerapur Road | 6 | Preparatory
250 | ADB | III | CGM III | Khargone | Bhagwanpura | MP 2251 | Sarvardevla to Garhi Road | 2.85 | GSB
251 | ADB | III | CGM III | Khargone | Bhagwanpura | MP 2251 | Pipaljhopa to Gopalpura Road | 2 | Not start
252 | ADB | III | CGM III | Khargone | Bhagwanpura | MP 2251 | Sarvardevla to Borkhedi Road | 4.1 | GSB
253 | ADB | III | CGM III | Khargone | Bhikangaon | MP 2252 | Selda to Reydor Road | 6.6 | Preparatory
254 | ADB | III | CGM III | Khargone | Bhikangaon | MP 2252 | Rehgaon to Sirlay Bujurg Road | 2.04 | G3
255 | ADB | III | CGM III | Khargone | Bhikangaon | MP 2252 | Birul to Ektasa Road | 3.35 | GSB
256 | ADB | III | CGM III | Khargone | Kasrawad | MP 2253 | Multhan to Hirapur Road | 0.75 | Preparatory
257 | ADB | III | CGM III | Khargone | Kasrawad | MP 2253 | Multhan to Kirgaon Road | 4.5 | GSB
258 | ADB | III | CGM III | Khargone | Kasrawad | MP 2253 | Pipri Nayder Road to Bhaisawad Road | 5.6 | GSB
259 | ADB | III | CGM III | Khargone | Segaon | MP 2251 | Panali to Upadi Road | 1.95 | Preparatory
260 | ADB | III | CGM III | Khargone | Segaon | MP 2251 | Sangvi to Panali Road | 5.2 | Preparatory
261 | ADB | III | CGM III | Khargone | Zirniya | MP 2252 | Neemsethi to Berchha Road | 3.52 | Preparatory
262 | ADB | III | CGM III | Khargone | Zirniya | MP 2252 | Abhapuri to Gawal Road | 7.4 | GSB
263 | ADB | III | CGM III | Khargone | Zirniya | MP 2252 | Neemsethi to Punasala Road | 2.88 | Preparatory
264 | PMGSY | III | CGM III | Khargone | Jhirnia | MP 2206 | Bilkhed to Dhupi Road | 3.2 | Forest land
265 | PMGSY | III | CGM III | Khargone | Maheshwar | MP 2206 | Satgoradia to Bablai Road | 1.15
266 | PMGSY | IV | CGM III | Khargone | Barwaha | MP 2212 | Bhogawa Nipani to Sipani Road | 5.8 | BT
267 | PMGSY | IV | CGM III | Khargone | Bhikangaon | MP 2212 | Sirali to Chiragpura Road | 10.8 | G2
268 | PMGSY | IV | CGM III | Khargone | Maheshwar | MP 2209 | Gangatkhedi to Bardiya Road | 5.4 | Preparatory
269 | PMGSY | V | CGM III | Khargone | Barwaha | MP 2213 | Bangarda to Bhomwara Road | 4.1 | Not Start
270 | PMGSY | V | CGM III | Khargone | Barwaha | MP 2213 | Bediya Kasrawad Road to Mogawa Road | 5.8 | Notstart
271 | PMGSY | V | CGM III | Khargone | Barwaha | MP 2213 | Sanawad Bhikangaon Rd. to Sala Road | 1.6 | GsB
272 | PMGSY | V | CGM III | Khargone | Barwaha | MP 2213 | Sanawad Khargone Rd. to Gawal Road | 2.3 | GsB
273 | PMGSY | V | CGM III | Khargone | Barwaha | MP 2213 | Amba to Nalwat Road | 2.6 | GsB
274 | PMGSY | V | CGM III | Khargone | Barwaha | MP 2213 | Barwaha to Rupabedi Road | 3 | GsB
275 | PMGSY | V | CGM III | Khargone | Bhagwanpura | MP 2214 | Thardarpura to Ambakheda Road | 3.25 | Not Start
276 | PMGSY | V | CGM III | Khargone | Bhagwanpura | MP 2214 | Anakwadi Bhagwanpura to Thardarpura Road | 13.9 | GSB
277 | PMGSY | V | CGM III | Khargone | Bhikangaon | MP 2215 | Khargone Sanawad Road to Bilkhed Khurd App. Road | 1.415 | GSB
278 | PMGSY | V | CGM III | Khargone | Bhikangaon | MP 2215 | Rehgaon to Balkhadiya Road | 3.1 | Not Start
279 | PMGSY | V | CGM III | Khargone | Bhikangaon | MP 2218 | Dondwa to Borgaon Road | 6 | GSB
280 | PMGSY | V | CGM III | Khargone | Gogawa | MP 2214 | Ghughriyakhedi Gadaghat Rd. Rupkheda Road | 2.2 | Preparatory
281 | PMGSY | V | CGM III | Khargone | Gogawa | MP 2214 | Ghughriyakhedi to Gadaghat Road | 7.4 | GSB
282 | PMGSY | V | CGM III | Khargone | Maheshwar | MP 2216 | Bhogawa Sipani to Bhogawa Nipani Road | 7.3 | BT
283 | PMGSY | V | CGM III | Khargone | Maheshwar | MP 2219 | Melkhedi to Maksi Road | 1.5 | Earthwork
284 | PMGSY | V | CGM III | Khargone | Maheshwar | MP 2219 | Garhi to Melkhedi Road | 3 | GSB
285 | PMGSY | V | CGM III | Khargone | Zirniya | MP 2217 | Gorakhpur Satwada to Ghori Bujurg Raod | 7.5 | Not Start
286 | PMGSY | V | CGM III | Khargone | Zirniya | MP 2217 | Gorakhpur Satwada Road (Up to Kakariya Phata) | 8.5 | GSB
287 | PMGSY | V | CGM III | Khargone | Zirniya | MP 2217 | Gorakhpur Satwada Road to Kakariya App. Road) | 1.25 | Earthwork
288 | ADB | II | CGM III | Mandsaur | Garoth | MP 2451 | Garoth - Boliya road to Chikniya | 4.25 | GSB
289 | ADB | II | CGM III | Mandsaur | Garoth | MP 2451 | Chandawasa to Bardiya Uncha | 3.45 | G2
290 | ADB | II | CGM III | Mandsaur | Garoth | MP 2451 | Chandawasa to Kherkhedi | 3.45 | G2
291 | ADB | II | CGM III | Mandsaur | Malhargarh | MP 2452 | Garnai to Tidwas | 4.9 | Earth Work
292 | ADB | II | CGM III | Mandsaur | Malhargarh | MP 2452 | Garnai to Chayan | 5.15 | G3
293 | ADB | II | CGM III | Mandsaur | Malhargarh | MP 2452 | Garnai to Sanjeet | 2.25 | G2
294 | ADB | II | CGM III | Mandsaur | Malhargarh | MP 2452 | Sanjeet to Abdapur | 1 | GSB
295 | ADB | II | CGM III | Mandsaur | Mandsaur | MP 2452 | Bhalot to Badakhedi | 4.825 | BT
296 | ADB | II | CGM III | Mandsaur | Mandsaur | MP 2452 | Jawasiya to Karnakhedi | 7.25 | G2
297 | ADB | II | CGM III | Mandsaur | Sitamou | MP 2451 | Nahargarh to Khajuri Chandrawat | 2.7 | BT
298 | ADB | II | CGM III | Mandsaur | Sitamou | MP 2451 | Kachanara to Nahargarh | 4.05 | G2
299 | ADB | III | CGM III | Mandsaur | Mandsaur | MP 2453 | NH-79 to Rinchalalmunha | 4.6 | Earth work
300 | ADB | III | CGM III | Mandsaur | Mandsaur | MP 2453 | SH-14 to Lodh | 7.4 | Preparatory
301 | ADB | III | CGM III | Mandsaur | Sitamou | MP 2453 | Laduna-jaora rd to Khajurinag | 1.9 | GSB
302 | ADB | III | CGM III | Mandsaur | Sitamou | MP 2453 | Laduna-jaora rd to Nakadiya | 4.75 | BT
303 | ADB | III | CGM III | Mandsaur | Sitamou | MP 2453 | Laduna-jaora rd to Sagor | 10.55 | G2
304 | PMGSY | IV | CGM III | Mandsaur | Bhanpura | MP 2405 | Dhawad Bujurg Approch Road | 7.1 | Earth work
305 | PMGSY | IV | CGM III | Mandsaur | Bhanpura | MP 2405 | Garoth Bhanpura Rd. To Arniyabhau. | 2.6 | BT
306 | PMGSY | IV | CGM III | Mandsaur | Garoth | MP 2405 | Chandawasa to Tolkhedi | 8.515 | BT
307 | PMGSY | IV | CGM III | Mandsaur | Malhargarh | MP 2406 | Billod Rd. to Magrana | 12.55 | BT
308 | PMGSY | IV | CGM III | Mandsaur | Mandsaur | MP 2406 | Bhawgarh 0 Sitamou Rd to Jhawal | 7.2 | G2
309 | PMGSY | IV | CGM III | Mandsaur | Sitamou | MP 2406 | Kheda to Chikla | 5.5 | G3
310 | PMGSY | IV | CGM III | Mandsaur | Sitamou | MP 2406 | Sitamou 0 Basai Rd. to Kachariya | 7.78 | G3
311 | PMGSY | V | CGM III | Mandsaur | Bhanpura | MP 2407 | Lotkheri - Bhansoda Road to Panga | 2.5 | G3
312 | PMGSY | V | CGM III | Mandsaur | Bhanpura | MP 2407 | Lotkheri to Mitthankhedi | 6.3 | Earthwork
313 | PMGSY | V | CGM III | Mandsaur | Bhanpura | MP 2407 | Lotkheri to Harnawada | 4.225 | G2
314 | PMGSY | V | CGM III | Mandsaur | Bhanpura | MP 2407 | Lotkheri - Khajuria Road to Rehtdi | 4.1 | GSB
315 | PMGSY | IV | CGM III | Neemuch | Jawad | MP 2705 | Dhaba to Arniya Mamadev | 3.33 | BT
316 | PMGSY | IV | CGM III | Neemuch | Manasa | MP 2705 | Kanjarda to Chokdi | 5.95 | GSB
317 | PMGSY | IV | CGM III | Neemuch | Neemuch | MP 2705 | NH79 to Arniyaborana | 4.53 | G2
318 | PMGSY | V | CGM III | Neemuch | Jawad | MP 2706 | Neemuch-Singoli road to Bhadawa | 2.535 | Earth work
319 | PMGSY | V | CGM III | Neemuch | Jawad | MP 2706 | Alori road to Luhariya | 5.175 | Earth work
320 | PMGSY | V | CGM III | Neemuch | Jawad | MP 2706 | Ratangarh Alori rd Km. 1 to 7 | 7.3 | G1
321 | PMGSY | V | CGM III | Neemuch | Manasa | MP 2706 | Devri-Antri road Chaplana | 3.98 | Earth work
322 | PMGSY | V | CGM III | Neemuch | Manasa | MP 2706 | Lorkiya to Devri | 4 | G3
323 | PMGSY | V | CGM III | Neemuch | Manasa | MP 2706 | Devri to Khajuri | 3.95 | G2
324 | PMGSY | V | CGM III | Neemuch | Manasa | MP 2707 | Bamora - Bamori | 2.8 | G3
325 | PMGSY | V | CGM III | Neemuch | Neemuch | MP 2707 | Neemuch to Jaisingh pura | 0.75 | G3
326 | PMGSY | V | CGM III | Neemuch | Neemuch | MP 2707 | Neemuch - Cheetakheda rd to Lakhmi | 3.55 | G3
327 | PMGSY | V | CGM III | Neemuch | Neemuch | MP 2707 | Neemuch - Cheetakheda rd to Rabadiya | 3.7 | G3
328 | PMGSY | V | CGM III | Neemuch | Neemuch | MP 2707 | Neemuch - Cheetakheda rd to Gwal Deveriya | 4.4 | G3
329 | PMGSY | V | CGM III | Neemuch | Neemuch | MP 2707 | Neemuch - Cheetakheda rd to Gwal talab | 3.4 | GSB
330 | ADB | III | CGM III | Ratlam | Alote | MP 3151 | Alote Barod to Bhim | 6 | Earth work
331 | ADB | III | CGM III | Ratlam | Alote | MP 3151 | Jaora Tal Road to Dhudiya | 3.1 | Preparatory
332 | ADB | III | CGM III | Ratlam | Alote | MP 3151 | Gogapur Nagda Road to Minawada | 3.4 | Preparatory
333 | ADB | III | CGM III | Ratlam | Bajna | MP 3152 | Raoti Ajabgarh Road to Jabad | 1.45 | Preparatory
334 | ADB | III | CGM III | Ratlam | Bajna | MP 3152 | Dewla to Raoti | 5.95 | Preparatory
335 | ADB | III | CGM III | Ratlam | Bajna | MP 3152 | Harthal to Mahudi Ka Mal | 5.85 | Preparatory
336 | ADB | III | CGM III | Ratlam | Jaora | MP 3151 | Jaora Tal Road to Bamankhedi | 1.33 | Preparatory
337 | ADB | III | CGM III | Ratlam | Jaora | MP 3151 | Dudha Khedi to Lasudiya Jangli | 5.5 | Preparatory
338 | ADB | III | CGM III | Ratlam | Jaora | MP 3151 | Raja Khada to Rehwas | 2.58 | Preparatory
339 | ADB | III | CGM III | Ratlam | Jaora | MP 3151 | Kerwas to Dodiyana | 2.63 | Preparatory
340 | ADB | III | CGM III | Ratlam | Jaora | MP 3151 | Bhuteda to Kerwasa | 5 | Preparatory
341 | PMGSY | III | CGM III | Ratlam | Bajna | MP 3104 | Chickni to Devipada | 3.97 | GSB
342 | PMGSY | III | CGM III | Ratlam | Mahdipur | MP 4307 (Sp.) | Pat Dongarkheda to Ghonsla Mahidpur rd. | 22.3 | BT
343 | PMGSY | III | CGM III | Ratlam | Sailana | MP 3104 | Ambapada to Ratlam Banswada road | 13.11 | BT
344 | PMGSY | V | CGM III | Ratlam | Alote | MP 3108 | Jaora Tal road to Negroon | 6.38 | Preparatory
345 | PMGSY | V | CGM III | Ratlam | Alote | MP 3108 | Piploda Sisodiya to Jamuniya Shankar | 3 | Earth work
346 | PMGSY | V | CGM III | Ratlam | Alote | MP 3108 | Alote to Barkheda kala Road to | 1.18 | Not start
347 | PMGSY | V | CGM III | Ratlam | Alote | MP 3108 | Pipliyapeetha to Alote Berkheda kala Road | 1.25 | Earth work
348 | PMGSY | V | CGM III | Ratlam | Bajna | MP 3107 | Tamboliya to Kothada | 2.55 | Preparatory
349 | PMGSY | V | CGM III | Ratlam | Bajna | MP 3107 | Nayan to Semalkhedi | 3.85 | Not start
350 | PMGSY | V | CGM III | Ratlam | Bajna | MP 3107 | Raoti Nayan Road to Gangayata Pada | 2.35 | Earthwork
351 | PMGSY | V | CGM III | Ratlam | Piploda | MP 3108 | Panchewa to Jethana | 2.7 | Earth work
352 | PMGSY | V | CGM III | Ratlam | Piploda | MP 3108 | Jaora Piploda road to Pancheva | 3.4 | Preparatory
353 | PMGSY | V | CGM III | Ratlam | Piploda | MP 3108 | Panchewa to Bhatkhedi | 3.45 | Preparatory
354 | PMGSY | V | CGM III | Ratlam | Ratlam | MP 3107 | Bilpak to Dhikawa | 8.75 | Earthwork
355 | PMGSY | V | CGM III | Ratlam | Ratlam | MP 3107 | Mhow Neemuch Road to Bilpak | 1.45 | Earthwork
356 | PMGSY | V | CGM III | Ratlam | Sailana | MP 3107 | Berda to Jambudiya | 2.4 | Earthwork
357 | PMGSY | V | CGM III | Ratlam | Sailana | MP 3107 | Berda to Ballikheda | 13.05 | GSB
358 | PMGSY | IV | CGM III | Ratlam | Alote |  | Gadbawadiya to Tambodiya Rd | 0 | Forest
359 | ADB | II | CGM III | Shajapur | Moman Badodia | MP 3951 | Agar Sarangpur Road To Choma | 1.35 | Not Start
360 | ADB | II | CGM III | Shajapur | Moman Badodia | MP 3951 | Moman Barodiya Nalkheda To Nipaniya | 1.15 | Earth Work
361 | ADB | II | CGM III | Shajapur | Moman Badodia | MP 3951 | Bolai Akodiya To Kethalai | 6.625 | Earth Work
362 | ADB | II | CGM III | Shajapur | Moman Badodia | MP 3951 | Sarangpur Akodiya Rd. To Murlai | 0.55 | Earth Work
363 | ADB | II | CGM III | Shajapur | Moman Badodia | MP 3951 | Bolai Akodiya Rd. To Palsawad | 1.25 | Earth Work
364 | ADB | II | CGM III | Shajapur | Moman Badodia | MP 3951 | Sarangpur Akodiya Rd. To Budlay | 3 | Earth Work
365 | ADB | II | CGM III | Shajapur | Shajapur | MP 3951 | Maksi To Siroliya | 7.1 | Earth Work
366 | ADB | II | CGM III | Shajapur | Shajapur | MP 3951 | Shajapur Road To Hirpur Taka | 6.65 | Preparatory
367 | ADB | II | CGM III | Shajapur | Shujalpur | MP 3951 | Shujalpur Kalapipal Rd. To Chakrod | 4.1 | Earth Work
368 | ADB | II | CGM III | Shajapur | Shujalpur | MP 3951 | Maherkhedi To Jhadla | 2.124 | Earth Work
369 | ADB | II | CGM III | Shajapur | Shujalpur | MP 3951 | Shujalpur Kalapipal Rd. (Intervention) | 7.91 | Earth Work
370 | ADB | III | CGM III | Shajapur | Agar | MP 3953 | SH-27 (Tanodiya) to Malwasa | 5.3 | Preparatory
371 | ADB | III | CGM III | Shajapur | Agar | MP 3953 | Malwasa to Lingoda | 2.25 | Preparatory
372 | ADB | III | CGM III | Shajapur | Agar | MP 3953 | Agar Sarangpur Road to Nanyakhedi | 0.8 | G2
373 | ADB | III | CGM III | Shajapur | Agar | MP 3953 | Bhyana to Gurasia | 5.34 | GSB
374 | ADB | III | CGM III | Shajapur | Agar | MP 3953 | Agar Bhyana Road to Bhadwa | 6.1 | Earth work
375 | ADB | III | CGM III | Shajapur | Nalkheda | MP 3953 | Banjaro ka Kheda to Gujarkhedi | 7.5 | Earth work
376 | ADB | III | CGM III | Shajapur | Nalkheda | MP 3953 | Banjaro Ka Kheda to Gudravan | 0.93 | Earth work
377 | ADB | III | CGM III | Shajapur | Nalkheda | MP 3953 | Gujar kheri to Laturigahlot | 3.25 | Earth work
378 | ADB | III | CGM III | Shajapur | Shujalpur | MP 3952 | Shujalpur Akodia - Uchod | 7.5 | GSB
379 | ADB | III | CGM III | Shajapur | Shujalpur | MP 3952 | Awantipur Barodiya Rd. - Salia | 4 | Preparatory
380 | ADB | III | CGM III | Shajapur | Shujalpur | MP 3952 | Shujalpur Akodiya Rd. - Patlawada Junction | 0.9 | GSB
381 | ADB | III | CGM III | Shajapur | Shujalpur | MP 3952 | Patlawada Junction - Patlawada | 3 | GSB
382 | PMGSY | IV | CGM III | Shajapur | Kalapipal | MP 3911 | Dhabla Dhir Sehore Kalapipal Road | 2.4 | G2
383 | PMGSY | IV | CGM III | Shajapur | Kalapipal | MP 3911 | Bhainsigadda Kurawar0kalpipal Road | 2 | G2
384 | PMGSY | IV | CGM III | Shajapur | Momman Barodiya | MP 3911 | Bhainsrod to Akodiya Sarangpur rd | 2.4 | G3
385 | PMGSY | IV | CGM III | Shajapur | Momman Barodiya | MP 3911 | Borsali to Akodiya Sundarsi Road | 8.6 | G2
386 | PMGSY | IV | CGM III | Shajapur | Shajapur | MP 3911 | Ranth Bhanwar Berchha Sundarsi Road | 0.75 | G3
387 | PMGSY | IV | CGM III | Shajapur | Shajapur | MP 3911 | Magria A.B.Road | 2.4 | G3
388 | PMGSY | IV | CGM III | Shajapur | Shujalpur | MP 3911 | Khatsur to Akodiya Sundersi Road | 4 | G3
389 | PMGSY | IV | CGM III | Shajapur | Shujalpur | MP 3911 | Magrola Mayapur to Shujalpur Pachor Rd | 1.6 | G3
390 | PMGSY | IV | CGM III | Shajapur | Shujalpur | MP 3911 | Mitera Akodiya Sarangpur Road | 9.1 | G2
391 | PMGSY | IV | CGM III | Shajapur | Shujalpur | MP 3911 | Raipur Shujalpur Road | 3.35 | GSB
392 | PMGSY | V | CGM III | Shajapur | Barod | MP 3913 | Agar Barod Rd. to Narella | 7.6 | G2
393 | PMGSY | V | CGM III | Shajapur | Barod | MP 3913 | Agar Dug Rd. to Madkota | 1 | Bt
394 | PMGSY | V | CGM III | Shajapur | Barod | MP 3913 | Jhonta Choki Jaishingpura to Harnawad | 1.9 | BT
395 | PMGSY | V | CGM III | Shajapur | Barod | MP 3913 | Jhonta Choki to Harnawad Road | 6.5 | G2
396 | PMGSY | V | CGM III | Shajapur | Barod | MP 3913 | Jhonta Choki Jaishingpura Rd. to Chikli Sondhiya | 1.45 | G2
397 | PMGSY | V | CGM III | Shajapur | Kalapipal | MP 3912 | Shujalpur To Astha Road To Arniyakhurd | 4 | GSB
398 | PMGSY | V | CGM III | Shajapur | Kalapipal | MP 3912 | Arniyakhurd To Salkon Khedi | 0.9 | Preparatory
399 | PMGSY | V | CGM III | Shajapur | Kalapipal | MP 3912 | Main Road To Dhablaghosi | 8.95 | G3
400 | PMGSY | V | CGM III | Shajapur | Kalapipal | MP 3912 | Nipaniya Khurd To Jabariya Dharwas | 4 | G3
401 | PMGSY | V | CGM III | Shajapur | Susner | MP 3913 | Guradiya to Barai | 3.5 | Preparatory
402 | PMGSY | V | CGM III | Shajapur | Susner | MP 3913 | Modi Soyat to Kawra Khedi | 0.9 | Earth work
403 | PMGSY | V | CGM III | Shajapur | Susner | MP 3913 | Indore Kota Road to Lalakhedi | 2.15 | G2
404 | ADB | I | CGM III | Ujjain | Barnagar | MP 4351 | Kantharkhedi to Kanjad | 8.25 | G3
405 | ADB | I | CGM III | Ujjain | Barnagar | MP 4351 | Runija Unhel road to Ajdawada | 2.9 | GSB
406 | ADB | I | CGM III | Ujjain | Ghattiya | MP 4351 | Pipliyahama to Ujjain Unhel Road | 11.55 | G2
407 | ADB | I | CGM III | Ujjain | Khachrod | MP 4351 | Khachrod to Bhikampur | 9.05 | G2
408 | ADB | I | CGM III | Ujjain | Mahidpur | MP 4351 | Madhipur Gogapur Road to Isankhedi | 3.5 | G3
409 | ADB | I | CGM III | Ujjain | Mahidpur | MP 4351 | Jharda to Kundikheda | 10.056 | Earth work
410 | ADB | I | CGM III | Ujjain | Tarana | MP 4351 | Tarana to Kharpa | 7.25 | G2
411 | ADB | I | CGM III | Ujjain | Tarana | MP 4351 | Kyatha Dewas road to Bhatuni | 0.78 | Preparatory
412 | ADB | I | CGM III | Ujjain | Ujjain | MP 4351 | Ujjain Fatehabad road to Takwasa | 3.05 | Earth work
413 | ADB | I | CGM III | Ujjain | Ujjain | MP 4351 | Karohan to Jharkhoda | 5 | GSB
414 | ADB | III | CGM III | Ujjain | Barnagar | MP 4352 | Barnagar Runija road to Birakhedi | 4.45 | Earth work
415 | ADB | III | CGM III | Ujjain | Khachrod | MP 4352 | Azimabad Pardi to Bhatisuda | 2.75 | Earth work
416 | ADB | III | CGM III | Ujjain | Khachrod | MP 4352 | Badagaon to Sandla | 5.8 | Preparatory
417 | ADB | III | CGM III | Ujjain | Khachrod | MP 4352 | Sandla Badagaon road to Sandawada | 1.1 | Preparatory
418 | PMGSY | III | CGM III | Ujjain | Badnagar | MP 4306 | Umariya to Badnagar kaisor road | 4.273 | BT
419 | PMGSY | IV | CGM III | Ujjain | Alote | MP 3105 | Gadawadiya to tambodiya | Deleted
420 | PMGSY | V | CGM III | Ujjain | Barnagar | MP 4312 | Amla to Bhidawad | 7.5 | GSB
421 | PMGSY | V | CGM III | Ujjain | Barnagar | MP 4312 | Barnagar Badnawar road to Amala | 6.1 | Preparatory
422 | PMGSY | V | CGM III | Ujjain | Ghatiya | MP 4310 | Guradiya Gujar to Khajuriya Sadar | 3.45 | GSB
423 | PMGSY | V | CGM III | Ujjain | Ghatiya | MP 4310 | Najarpur to Bichrod | 12.88 | GSB
424 | PMGSY | V | CGM III | Ujjain | Karkeli | MP 4405 | NH 78 to Pathari | 2.9 | Preparatory
425 | PMGSY | V | CGM III | Ujjain | Khachrod | MP 4312 | Nagda (Birla Gram) to Nayan | 3.3 | Earth work
426 | PMGSY | V | CGM III | Ujjain | Khachrod | MP 4312 | Chapakheda to Mokdi | 4.28 | G2
427 | PMGSY | V | CGM III | Ujjain | Khachrod | MP 4312 | Mokdi to Barchha | 7.38 | GSB
428 | PMGSY | V | CGM III | Ujjain | Mahidpur | MP 4311 | Katan to Makla Fanta | 6.9 | BT
429 | PMGSY | V | CGM III | Ujjain | Mahidpur | MP 4311 | Makla to Nagguradiya | 5.48 | GSB
430 | PMGSY | V | CGM III | Ujjain | Tarana | MP 4311 | Tarana to Siddhipur Nipaniya | 5.98 | Earth work
431 | PMGSY | V | CGM III | Ujjain | Tarana | MP 4311 | Makdon to Bhodliya | 3.83 | Earth work
432 | PMGSY | V | CGM III | Ujjain | Tarana | MP 4311 | Rupakhedi to Makdon | 6.9 | G3
433 | PMGSY | V | CGM III | Ujjain | Ujjain | MP 4310 | Ujjain Maxi road to Jaiwantpur | 0.65 | Earth work
434 | PMGSY | V | CGM III | Ujjain | Ujjain | MP 4310 | Fathabad to Nilkanth | 1.18 | G2
435 | PMGSY | V | CGM III | Ujjain | Ujjain | MP 4310 | Ujjain to Fatehabad | 6.85 | Not start
436 | PMGSY | V | CGM III | Ujjain | Ujjain | MP 4310 | Umariya to Kandariya | 3.73 | GSB
437 | PMGSY | V | CGM III | Ujjain | Ujjain | MP 4310 | Kandaryia road to Erwas | 1.3 | GSB
Total III
1 | ADB | III | CGM IV | Balaghat | Baihar | MP 0151 | Gadhi Balgaon | 1.9 | GSB
2 | ADB | III | CGM IV | Balaghat | Kirnapur | MP 0151 | Dundaseoni Kunde | 5.2 | GSB
3 | ADB | III | CGM IV | Balaghat | Kirnapur | MP 0151 | Saleteka Dundaseoni Bhalwa | 16.9 | Earth work
4 | ADB | III | CGM IV | Balaghat | Kirnapur | MP 0151 | Bhalwa Kariyadand | 3.75 | Earth work
5 | PMGSY | IV | CGM IV | Balaghat | Baihar | MP 0113 | Gogatola Pola | 7.25 | BT
6 | PMGSY | IV | CGM IV | Balaghat | Kirnapur | MP 0114 | Khara Mohgaon | 2.1 | Earth work
7 | PMGSY | IV | CGM IV | Balaghat | Lanji | MP 0114 | Itora Pathargaon | 3.85 | GSB
8 | PMGSY | IV | CGM IV | Balaghat | Paraswara | MP 0113 | Kumadehi Sarekha | 5.55 | G2
9 | PMGSY | V | CGM IV | Balaghat | Baihar | MP 0116 | Ukwa to Dabri (Km 0 to 30.00) | 30 | G2
10 | PMGSY | V | CGM IV | Balaghat | Balaghat | MP 0121 | Lohara - Hardoli | 1.6 | G2
11 | PMGSY | V | CGM IV | Balaghat | Balaghat | MP 0121 | Navegaon - Linga | 4.725 | Earth work
12 | PMGSY | V | CGM IV | Balaghat | Balaghat | MP 0121 | Linga-Paraswada | 1.2 | Earth work
13 | PMGSY | V | CGM IV | Balaghat | Balaghat | MP 0121 | Lohara Keshlewara | 8.4 | Gsb
14 | PMGSY | V | CGM IV | Balaghat | Birsa | MP 0117 | Ukwa to Dabri (km 30 to 43.80) | 13.8 | Gsb
15 | PMGSY | V | CGM IV | Balaghat | Birsa | MP 0117 | Dabri - Dadkasa | 8.7 | Earth work
16 | PMGSY | V | CGM IV | Balaghat | Birsa | MP 0118 | Mohgaon - Janpur | 6.15 | G2
17 | PMGSY | V | CGM IV | Balaghat | Birsa | MP 0118 | Chakarwahi - Bhandarpur | 5.73 | Gsb
18 | PMGSY | V | CGM IV | Balaghat | Birsa | MP 0118 | Banjaritola - Chakarwahi to Mandai | 12 | G2
19 | PMGSY | V | CGM IV | Balaghat | Katangi | MP 0120 | Katangi Nandlesara | 9.475 | G2
20 | PMGSY | V | CGM IV | Balaghat | Katangi | MP 0120 | Khajari choukhandi | 4.13 | G2
21 | PMGSY | V | CGM IV | Balaghat | Khairlanji | MP 0120 | Kothurana to Kanhargaon | 9.8 | Gsb
22 | PMGSY | V | CGM IV | Balaghat | Khairlanji | MP 0120 | Gunai Approach Road | 2.03 | Earth work
23 | PMGSY | V | CGM IV | Balaghat | Lalburra | MP 0119 | Mohgaon - Dhapera | 2.55 | Gsb
24 | PMGSY | V | CGM IV | Balaghat | Lalburra | MP 0119 | Babariya Approach | 3.05 | Gsb
25 | PMGSY | V | CGM IV | Balaghat | Lalburra | MP 0119 | Newargaon - Bandri | 2.325 | G2
26 | PMGSY | V | CGM IV | Balaghat | Lanji | MP 0122 | km 9 of Lanji -Durg Road - Sawri | 3.1 | Gsb
27 | PMGSY | V | CGM IV | Balaghat | Lanji | MP 0122 | Mohjhari - Binjhalgaon | 5.65 | Gsb
28 | PMGSY | V | CGM IV | Balaghat | Lanji | MP 0122 | Sadra to Dighori | 4.7 | Gsb
29 | PMGSY | V | CGM IV | Balaghat | Lanji | MP 0122 | KM 11 of Lanji-Durg Road - Wari | 1.9 | G2
30 | PMGSY | V | CGM IV | Balaghat | Paraswada | MP 0119 | Pondi - Thema - Korja | 12.25 | G2
31 | PMGSY | V | CGM IV | Balaghat | Waraseoni | MP 0121 | Sarandi Approach | 1.17 | Gsb
32 | PMGSY | V | CGM IV | Balaghat | Waraseoni | MP 0121 | Basi -Bodalkasa | 3.95 | G2
33 | ADB | III | CGM IV | Chhindwara | Chhindwara | MP 0751 | Chhindwara-Nagpur Rd. to Bisapur Khurd | 5.13
34 | ADB | III | CGM IV | Chhindwara | Chourai | MP 0751 | Chandangaon to Titri | 1.2
35 | ADB | III | CGM IV | Chhindwara | Chourai | MP 0751 | Lalgaon to Rampuri | 4.9
36 | ADB | III | CGM IV | Chhindwara | Chourai | MP 0751 | Chand to Patlon | 14.9
37 | ADB | III | CGM IV | Chhindwara | Harrai | MP 0753 | BCKH Road to Churi Sajwa | 5
38 | ADB | III | CGM IV | Chhindwara | Harrai | MP 0753 | Churi Sajwa to Gangai | 5
39 | ADB | III | CGM IV | Chhindwara | Junnardeo | MP 0754 | Khumkal to Morchhi | 10.05
40 | ADB | III | CGM IV | Chhindwara | Junnardeo | MP 0754 | Navegaon to Khumkal | 4.75
41 | ADB | III | CGM IV | Chhindwara | Mohkhed | MP 0752 | S.H.-26 to Mahlari Bakul | 16.1
42 | ADB | III | CGM IV | Chhindwara | Parasia | MP 0751 | Manegaon Rd. to Bandra | 3.15
43 | ADB | III | CGM IV | Chhindwara | Parasia | MP 0751 | Chhindwara-Nagpur Rd. to Badgona Joshi | 4.65
44 | ADB | III | CGM IV | Chhindwara | Sousar | MP 0751 | Chhindwara-Narsingpur Rd. to Manegaon | 11.85
45 | ADB | III | CGM IV | Chhindwara | Sousar | MP 0751 | Manegaon Rd. to Pipariya Gumani | 2.3
46 | ADB | III | CGM IV | Chhindwara | Sousar | MP 0752 | Chhindwara-Nagpur Rd. to Rohnakala | 1.6
47 | ADB | III | CGM IV | Chhindwara | Sousar | MP 0752 | Chhindwara-Nagpur Rd. to Kajalwani | 0.8
48 | ADB | III | CGM IV | Chhindwara | Sousar | MP 0752 | Khutama to Navthal | 3.7
49 | ADB | III | CGM IV | Chhindwara | Tamiya | MP 0753 | Chhindi-Khulshan to Babai Pathar | 8.7
50 | ADB | III | CGM IV | Chhindwara | Tamiya | MP 0753 | S.H.-19 to Pratapgarhbadla | 2.04
51 | ADB | III | CGM IV | Chhindwara | Tamiya | MP 0753 | Nagri to Jhirpani | 4.2
52 | ADB | III | CGM IV | Chhindwara | Tamiya | MP 0753 | Chhindi-Khulshan Road to Mordhana | 6.75
53 | PMGSY | III | CGM IV | Chhindwara | Amarwara | MP 0709 | Pipariya (Raigura) Barahira Main RD Km 12/4 to Dhasanwara rd. | 1.5 | GSB
54 | PMGSY | III | CGM IV | Chhindwara | Amarwara | MP 0709 | Amarwara Urariya RD To Kahua | 15 | G2
55 | PMGSY | III | CGM IV | Chhindwara | Harrai | MP 0709 | Dhanora Damkhah Rd to Mankawadi | 1.85 | G3
56 | PMGSY | IV | CGM IV | Chhindwara | Junnerdeo | MP 0716 | Rampur to Batri | 14.05 | Deleted
57 | PMGSY | V | CGM IV | Chhindwara | Bichhua | MP 0721 | Kunda Ryt To Khadbeli | 4.025 | G2
58 | PMGSY | V | CGM IV | Chhindwara | Bichhua | MP 0721 | Bichhua to Loharbatri | 4.7 | G2
59 | PMGSY | V | CGM IV | Chhindwara | Chhindwara | MP 0721 | Chargaon Pahlad to Jhirlinga | 2.1 | Preparatory
60 | PMGSY | V | CGM IV | Chhindwara | Chhindwara | MP 0721 | Biskhan - Sarna Road, To Kevlari | 2.45 | Preparatory
61 | PMGSY | V | CGM IV | Chhindwara | Chhindwara | MP 0721 | Chhindwara -Sonpur Rd., To Saraswara | 0.85 | Preparatory
62 | PMGSY | V | CGM IV | Chhindwara | Chhindwara | MP 0721 | Chhindwara Seoni Rd (S.H.-26) to Ranginkhapa | 2.4 | Gsb
63 | PMGSY | V | CGM IV | Chhindwara | Chhindwara | MP 0721 | Chhindwara Seoni Road(S.H.-26) to Marai | 4.25 | G2
64 | PMGSY | V | CGM IV | Chhindwara | Harrai | MP 0722 | SH 47 Pathara to Sukhapura | 12.5 | Gsb
65 | PMGSY | V | CGM IV | Chhindwara | Junnardeo | MP 0723 | Navegaon to Badnoor | 3.3 | Earth work
66 | PMGSY | V | CGM IV | Chhindwara | Junnardeo | MP 0723 | Navegaon Badnoor Road to Malini | 5 | Gsb
67 | PMGSY | V | CGM IV | Chhindwara | Junnardeo | MP 0723 | Navegaon Malini Road to Nirama | 1.8 | Gsb
68 | PMGSY | V | CGM IV | Chhindwara | Junnardeo | MP 0723 | Navegaon Malini Road to Bordehi Khas (Khurd) | 2.17 | Gsb
69 | PMGSY | V | CGM IV | Chhindwara | Pandhurna | MP 0723 | Ambada to Dhanora | 11.85 | BT
70 | PMGSY | V | CGM IV | Chhindwara | Pandhurna | MP 0723 | Nandanwari Ambada Road | 0.92 | Preparatory
71 | PMGSY | V | CGM IV | Chhindwara | Parasia | MP 0721 | Umreth to Kachram | 3 | Preparatory
72 | PMGSY | V | CGM IV | Chhindwara | Parasia | MP 0722 | Pagara Paijanwara Road to Dhamaniya | 9.4 | G2
73 | ADB | III | CGM IV | Dindori | Amarpur | MP 1251 | Bichhiya samnapur dindori road to junwani | 1.05
74 | ADB | III | CGM IV | Dindori | Amarpur | MP 1251 | sakka amarpur road to hatkata | 11.4
75 | ADB | III | CGM IV | Dindori | Amarpur | MP 1251 | Mandla dindori raod to chargaon | 1.98
76 | ADB | III | CGM IV | Dindori | Bajag | MP 1252 | Dindori amarkantak road to pindrukhi | 3
77 | ADB | III | CGM IV | Dindori | Bajag | MP 1252 | dindori amarkantak (paraswah ) to shobhapurmal | 6.45
78 | ADB | III | CGM IV | Dindori | Bajag | MP 1252 | dindori amarkantak road to sunhadadar | 4
79 | ADB | III | CGM IV | Dindori | Bajag | MP 1252 | Bajag chanda raod to midli | 2.87
80 | ADB | III | CGM IV | Dindori | Dindori | MP 1254 | dindori mandla raod to keolari | 3.4
81 | ADB | III | CGM IV | Dindori | Dindori | MP 1254 | jabalpur dindori road to vidaypur | 6.65
82 | ADB | III | CGM IV | Dindori | Dindori | MP 1254 | jabalpur dindori road to dhamangaon | 1.5
83 | ADB | III | CGM IV | Dindori | Karanjiya | MP 1253 | Dindori amarkantak road to pakri ryt | 3.3
84 | ADB | III | CGM IV | Dindori | Karanjiya | MP 1253 | Senguda to Bijori | 9.9
85 | ADB | III | CGM IV | Dindori | shahpura | MP 1254 | Bilgaon to dhudha | 1.8
86 | ADB | III | CGM IV | Dindori | shahpura | MP 1254 | Shahpura raipura road to tikariya | 2.87
87 | ADB | III | CGM IV | Dindori | shahpura | MP 1254 | Tikariya to dharegoan | 3.95
88 | PMGSY | III | CGM IV | Dindori | Bajag | MP 1205 | Bajag Mohti Road to Bonamal | 3.8 | Gsb
89 | PMGSY | IV | CGM IV | Dindori | Mehandwani | MP 1208 | Mehandwani 0Shahpura Rd to Jaitpuri | 7 | BT
90 | PMGSY | IV | CGM IV | Dindori | Samnapur | MP 1209 | Titrahi to Larwani | 7.6 | BT
91 | PMGSY | IV | CGM IV | Dindori | Shahpura | MP 1207 | Indorimal to Chandwahimal | 5.56 | BT
92 | PMGSY | V | CGM IV | Dindori | Dindori | MP 1210 | Dindori to Mudki Junction | 3.55 | G2
93 | PMGSY | V | CGM IV | Dindori | Dindori | MP 1210 | Mudki to Padariya | 5.23 | Gsb
94 | PMGSY | V | CGM IV | Dindori | Dindori | MP 1210 | Saratal to Ramguda | 6 | Earthwork
95 | PMGSY | V | CGM IV | Dindori | Mehandwani | MP 1213 | Chabi Mehandwani Road to Dhamnimal | 8.25 | G3
96 | PMGSY | V | CGM IV | Dindori | Mehandwani | MP 1213 | Mehandwani Shahpura Road to Kosamghat | 1.35 | Gsb
97 | PMGSY | V | CGM IV | Dindori | Mehandwani | MP 1213 | Chabi Mehandwani Road to Chatamal Via Kathotiya | 8.4 | G3
98 | PMGSY | V | CGM IV | Dindori | Samnapur | MP 1212 | Jatadongari to Azgar | 36.6 | G3
99 | PMGSY | V | CGM IV | Dindori | Shahpura | MP 1211 | Jabalpur Shahpura Road to Marwari | 4.6 | G2
100 | PMGSY | V | CGM IV | Dindori | Shahpura | MP 1211 | Raipura Manikpur Road to Moharkala | 7.15 | G2
101 | ADB | III | CGM IV | Jabalpur | Kundam | MP 1851 | Rosara Sarond Road to Kanehri | 22.5 | Not start
102 | ADB | III | CGM IV | Jabalpur | Patan | MP 1851 | Shahdra Road to Baroda | 1.65 | Earth work
103 | PMGSY | II | CGM IV | Jabalpur | Majholi | MP 1804 | NH 7 to Mahgawa | 3.998 | G2 3.5 km
104 | PMGSY | II | CGM IV | Jabalpur | Patan | MP 1804 | Patan Mankhedi Road to Udna Karaiya | 6.313 | Earth work
105 | PMGSY | II | CGM IV | Jabalpur | Shahpura | MP 1804 | Belkheda to Gubrakala | 4.55 | GSB 4.3 km
106 | PMGSY | III | CGM IV | Jabalpur | Jabalpur | MP 1807 | Rewa to Bargi Dam Rd | 4.446 | BT
107 | PMGSY | III | CGM IV | Jabalpur | Panagaar | MP 1807 | Dumna to Gadheri | 3.56 | G2
108 | PMGSY | III | CGM IV | Jabalpur | Patan | MP 1810 | Basan to Pondi (Kala) | 12.34 | BT 12 km
109 | PMGSY | III | CGM IV | Jabalpur | Shahpura | MP 1811 | NH12 to Powal | 2.771 | BT
110 | PMGSY | III | CGM IV | Jabalpur | Shahpura | MP 1811 | Indra Nagar Bhairoghat | 26.637 | GSB
111 | PMGSY | IV | CGM IV | Jabalpur | Jabalpur | MP 1813 | Bargi to Rangajhori | 5.2 | G3
112 | PMGSY | IV | CGM IV | Jabalpur | Jabalpur | MP 1813 | Pahari Khera To Mahgaon | 5.85 | G2
113 | PMGSY | IV | CGM IV | Jabalpur | Jabalpur | MP 1813 | NH12 to Tilhari | 2.1 | G2
114 | PMGSY | IV | CGM IV | Jabalpur | Jabalpur | MP 1813 | Bargi Nagar Barela Road to Basha | 1.5 | Not started
115 | PMGSY | IV | CGM IV | Jabalpur | Patan | MP 1815 | Malakala to Malaghat | 2 | BT
116 | PMGSY | IV | CGM IV | Jabalpur | Shahpura | MP 1815 | SH12 to Kuda Kala | 4.5 | BT
117 | PMGSY | IV | CGM IV | Jabalpur | Shahpura | MP 1815 | SH12 to Basedi | 2 | G2
118 | PMGSY | IV | CGM IV | Jabalpur | Shahpura | MP 1815 | Bhero ghat to Pathoriya | 2.4 | GSB
119 | PMGSY | IV | CGM IV | Jabalpur | Shahpura | MP 1815 | Suwakheda (L043) to Hinotiya | 2.32 | G3
120 | PMGSY | V | CGM IV | Jabalpur | Jabalpur | MP 1817 | NH 7 to Pipariya Saliwara | 6.75 | G3
121 | PMGSY | V | CGM IV | Jabalpur | Jabalpur | MP 1817 | NH7 to Harrai | 2.7 | GSB
122 | PMGSY | V | CGM IV | Jabalpur | Majholi | MP 1818 | T04 to Changawa Via Bichi | 3.06 | GSB
123 | PMGSY | V | CGM IV | Jabalpur | Majholi | MP 1818 | T04 to Umaria | 3.175 | GSB
124 | PMGSY | V | CGM IV | Jabalpur | Majholi | MP 1820 | Majholi Indrana Road to Kakardehi | 1.5 | Not start
125 | PMGSY | V | CGM IV | Jabalpur | Majholi | MP 1820 | Sihora Gubra road to Padwar | 8.25 | Gsb
126 | PMGSY | V | CGM IV | Jabalpur | Panagar | MP 1818 | NH-7 to Barkheda (via Barkhedi ) | 4.385 | GSB
127 | PMGSY | V | CGM IV | Jabalpur | Panagar | MP 1818 | Kusner Umariya Road to Pathra | 2.229 | BT
128 | PMGSY | V | CGM IV | Jabalpur | Panagar | MP 1818 | Padariya Road to Nipaniya | 1 | GSB
129 | PMGSY | V | CGM IV | Jabalpur | Shahpura | MP 1819 | SH-22 Shahpura Gotagaon to Neemkheda | 1.73 | G3
130 | PMGSY | V | CGM IV | Jabalpur | Shahpura | MP 1819 | NH-12 to Jhalon | 6 | GSB
131 | PMGSY | V | CGM IV | Jabalpur | Shahpura | MP 1819 | NH12 to Belkhedi | 2.05 | Earth work
132 | PMGSY | V | CGM IV | Jabalpur | Sihora | MP 1818 | NH7 Agariya Road to Ranital (Via) Jhansi | 2.8 | Earth work
133 | PMGSY | V | CGM IV | Jabalpur | Sihora | MP 1820 | Sihora Silondi Road to Bhandra | 4.4 | G3
134 | PMGSY | V | CGM IV | Jabalpur | Sihora | MP 1820 | Sihora Panumariya Road to Hargarh | 1.8 | Preparatory
135 | PMGSY | V | CGM IV | Jabalpur | Sihora | MP 1820 | Sihora Silondi Road to Amgaon | 6 | Preparatory
136 | ADB | III | CGM IV | Katni | Bahoriband | MP 2051 | NH-7 to Gudari | 5.2 | Earth work
137 | ADB | III | CGM IV | Katni | Bahoriband | MP 2051 | Sihora Salaiya Rd to Khamtara | 1.1 | Preparatory
138 | ADB | III | CGM IV | Katni | Bahoriband | MP 2051 | Katni Salaiya Rd to Amoch | 8.8 | Preparatory
139 | ADB | III | CGM IV | Katni | Rithi | MP 2051 | Mohas Pali to Kena | 0.83 | Preparatory
140 | ADB | III | CGM IV | Katni | Rithi | MP 2051 | Deogaw to Simara | 2.15 | Preparatory
141 | ADB | III | CGM IV | Katni | Rithi | MP 2051 | Katni Salaiya Rd to Rudmud | 1.7 | Preparatory
142 | ADB | III | CGM IV | Katni | Rithi | MP 2051 | Rithi to Barheta | 2 | Preparatory
143 | ADB | III | CGM IV | Katni | Rithi | MP 2051 | Katni Salaiya Rd to Tahkari | 2.5 | Preparatory
144 | ADB | III | CGM IV | Katni | Rithi | MP 2051 | Mohas Pali Rd to Deori Khurd | 1.45 | Preparatory
145 | PMGSY | II | CGM IV | Katni | Badwara | MP 2801 | Barhi Khitouly Road to Baran Mohagwan | 5.3 | GSB
146 | PMGSY | II | CGM IV | Katni | Badwara | MP 2003 | Badwara Deori Hatai Rd to Badagaon | 4.5 | G3
147 | PMGSY | II | CGM IV | Katni | Bahoriband | MP 2002 a | Sindursi to Bachaiya | 11 | G3
148 | PMGSY | II | CGM IV | Katni | Bahoriband | MP 2002 a | Kuwa to Padwar | 11.67 | BT 6 km
149 | PMGSY | II | CGM IV | Katni | Katni | MP 2801 | Pahadi to Deorihatai | 12.9 | BT
150 | PMGSY | III | CGM IV | Katni | Badwara | MP 2006 | Nadawan to Sutri | 12.55 | BT
151 | PMGSY | III | CGM IV | Katni | V-Garh | MP 2006 | Barhi Road to KhirwaI | 4.99 | G2
152 | PMGSY | IV | CGM IV | Katni | Badwara | MP 2010 | SH-14 to Kannor | 3.2 | G3
153 | PMGSY | IV | CGM IV | Katni | D-Khera | MP 2008 | Sunarkhera to Kachargawn | 3.62 | G3
154 | PMGSY | V | CGM IV | Katni | Badwara | MP 2012 | Baggeia to Chhindai Pipariya | 3.48 | Preparatory
155 | PMGSY | V | CGM IV | Katni | Badwara | MP 2012 | Sutri to Baranmahgawa | 7.71 | GSB
156 | PMGSY | V | CGM IV | Katni | Badwara | MP 2012 | Khitoli Baggeia Rd to Mohani | 1.45 | Earthwork
157 | PMGSY | V | CGM IV | Katni | Dheemarkheda | MP 2011 | Sleemnabad Bandhi Rd to Imaliya | 1.8 | GSB
158 | PMGSY | V | CGM IV | Katni | Dheemarkheda | MP 2011 | Sleemnabad Bandhi Vilayatkala Rd to Pipariya Shukla | 1.014 | GSB
159 | PMGSY | V | CGM IV | Katni | Dheemarkheda | MP 2011 | Pipariya Shukl Rd to Barhi | 2.6 | GSB
160 | PMGSY | V | CGM IV | Katni | Dheemarkheda | MP 2011 | Pipariya Shukl Rd to Kachhargaon | 2.8 | GSB
161 | PMGSY | V | CGM IV | Katni | Dheemarkheda | MP 2011 | Simariya Rd to Thirri | 2.1 | GSB
162 | PMGSY | V | CGM IV | Katni | Dheemarkheda | MP 2011 | Thirri to Bihriya | 2.6 | GSB
163 | PMGSY | V | CGM IV | Katni | Dheemarkheda | MP 2011 | NH 7 to Gentra (Via Madhav Nagar Bahrali) | 2.93 | Earthwork
164 | PMGSY | V | CGM IV | Katni | Katni | MP 2013 | Katni V-Garh Rd to Pilinji | 3.6 | GSB
165 | PMGSY | V | CGM IV | Katni | Katni | MP 2013 | Pilonji to Khamtara | 3.9 | GSB
166 | PMGSY | V | CGM IV | Katni | Katni | MP 2013 | Katni V-Garh Rd to Podi Pipariya | 4.1 | Not Start
167 | PMGSY | V | CGM IV | Katni | V-Garh | MP 2013 | Durjanipur to Chari | 2 | G2
168 | PMGSY | V | CGM IV | Katni | V-Garh | MP 2013 | Paraswara to Durjanpur | 1.88 | Earthwork
169 | PMGSY | V | CGM IV | Katni | V-Garh | MP 2013 | NH 7 to Surma | 2.5 | G2
170 | PMGSY | V | CGM IV | Katni | V-Garh | MP 2013 | Kymore Maihar Rd to Dhamwahi | 2.85 | G2
171 | ADB | III | CGM IV | Mandla | Bichhiya | MP 2356 | Ghatiya dhutka road to katajar | 2.55
172 | ADB | III | CGM IV | Mandla | Bichhiya | MP 2356 | Chargaon to dutka | 3.75
173 | ADB | III | CGM IV | Mandla | Bichhiya | MP 2356 | Ghatiya to chargaon | 11
174 | ADB | III | CGM IV | Mandla | Bijadandi | MP 2351 | Medhi Pouniyamal to Chargaon kala | 3.18
175 | ADB | III | CGM IV | Mandla | Bijadandi | MP 2351 | Udaypur Budra Road to Deori | 14.15
176 | ADB | III | CGM IV | Mandla | Ghughari | MP 2352 | Ghutas umariya(MDR) road to salheghori | 2.75
177 | ADB | III | CGM IV | Mandla | Ghughari | MP 2352 | Ghughari salwaha to dadi bhanpur to Kataideeh | 3.1
178 | ADB | III | CGM IV | Mandla | Ghughari | MP 2352 | Ghughari salwaha to dadi bhanpur (upto paraswah) | 11.6
179 | ADB | III | CGM IV | Mandla | Ghughari | MP 2352 | Ghughari salwaha dadi bhanpur road to kisli | 2.58
180 | ADB | III | CGM IV | Mandla | Ghughari | MP 2352 | Gajraj to Piperdoni | 3.05
181 | ADB | III | CGM IV | Mandla | Ghughari | MP 2352 | Chabi surehli road to lodha | 2.55
182 | ADB | III | CGM IV | Mandla | Ghughari | MP 2352 | chabi surehli road to duladar | 5.05
183 | ADB | III | CGM IV | Mandla | Mawai | MP 2353 | Pakwar to Basni | 3.6
184 | ADB | III | CGM IV | Mandla | Mawai | MP 2353 | Bichhiya dindori road to pipri Ryt | 1.48
185 | ADB | III | CGM IV | Mandla | Mawai | MP 2353 | Sakwah dadi bhanpur road to samnapur | 3.75
186 | ADB | III | CGM IV | Mandla | Mawai | MP 2353 | NH 12A Indri | 2.5
187 | ADB | III | CGM IV | Mandla | Mawai | MP 2353 | parsatola to harratola | 5.5
188 | ADB | III | CGM IV | Mandla | Mawai | MP 2353 | Ghutas to parsatola road Junction | 13.25
189 | ADB | III | CGM IV | Mandla | Mohgaon | MP 2354 | Karegoan-theba | 8
190 | ADB | III | CGM IV | Mandla | Mohgaon | MP 2354 | Ghughari mungwani road to pondi | 6.5
191 | ADB | III | CGM IV | Mandla | Narayanganj | MP 2355 | Narayanganj babaliyamal to chandehra road | 1.05
192 | ADB | III | CGM IV | Mandla | Narayanganj | MP 2355 | Tikariya to Patehra | 1.18
193 | ADB | III | CGM IV | Mandla | Narayanganj | MP 2355 | Lalipur to amdara | 8.05
194 | PMGSY | IV | CGM IV | Mandla | Mohgaon | MP 2312 | Mandla Dindori road to Aurarhi | 16.45 | BT
195 | PMGSY | IV | CGM IV | Mandla | Nainpur | MP 2311 | Nainpur Rd to Gonghi | 3.25 | Delete alignment disput
196 | PMGSY | IV | CGM IV | Mandla | Narayanganj | MP 2313 | Padariya to Bhanpur | 4.85 | BT
197 | PMGSY | IV | CGM IV | Mandla | Narayanganj | MP 2313 | Phoolsagar Niwas Rd to Babaliyamal | 1 | Road Cancel
198 | PMGSY | V | CGM IV | Mandla | Bichhiya | MP 2314 | NH12A to Khalodi | 5.95 | G3
199 | PMGSY | V | CGM IV | Mandla | Bichhiya | MP 2314 | NH12A to Narenimal | 1.8 | GSB
200 | PMGSY | V | CGM IV | Mandla | Bichhiya | MP 2314 | Harrabhat to Bhima | 4 | G2
201 | PMGSY | V | CGM IV | Mandla | Mandla | MP 2315 | Padmi Ghughari Road to Mungli | 2.35 | GSB
202 | PMGSY | V | CGM IV | Mandla | Mandla | MP 2315 | Ahmadpur to Salhedanda | 6.95 | GsB
203 | PMGSY | V | CGM IV | Mandla | Nainpur | MP 2316 | Bamhni to Jaideopur | 5.01 | G3
204 | PMGSY | V | CGM IV | Mandla | Nainpur | MP 2316 | Subhewada to Maldha | 4.3 | Preparatory
205 | PMGSY | V | CGM IV | Mandla | Nainpur | MP 2316 | Chiraidongari to Subhewada | 12.9 | GSB
206 | ADB | III | CGM IV | Narsinghpur | Chichli | MP 2652 | Sukhakhari To Baglai | 5.01 | Preparatory
207 | ADB | III | CGM IV | Narsinghpur | Chichli | MP 2652 | Barha Road To Dhana | 0.63 | Preparatory
208 | ADB | III | CGM IV | Narsinghpur | Chichli | MP 2652 | Salichhoka To Arjungaon | 6.28 | Earth work
209 | ADB | III | CGM IV | Narsinghpur | Kareli | MP 2651 | Barman NH 26 To Manegaon | 2.16 | Preparatory
210 | ADB | III | CGM IV | Narsinghpur | Kareli | MP 2651 | NH 12 To Bichhua | 4 | Not start
211 | PMGSY | II | CGM IV | Narsinghpur | Chawarpatha | MP 2604 | Gadarwara to Tendukhera MDR to Bikor | 4.6 | G2 1 km
212 | PMGSY | II | CGM IV | Narsinghpur | Chichli | MP 2605 | Hirapur to Raipur | 3.5 | G1
213 | PMGSY | II | CGM IV | Narsinghpur | Sainkhera | MP 2607 | Gardha to bamohri | 4.6 | GSB
214 | PMGSY | II | CGM IV | Narsinghpur | Sainkhera | MP 2607 | Gadarwara Sailkheka Rd to Khursipar | 3.2 | GSB
215 | PMGSY | II | CGM IV | Narsinghpur | Sainkhera | MP 2607 | Kheri Tiraha to Puloha | 4.5 | GSB
216 | PMGSY | II | CGM IV | Narsinghpur | Sainkhera | MP 2607 | Bamhoroi Khurd Rd to Rampura | 4 | GSB
217 | PMGSY | II | CGM IV | Narsinghpur | Sainkhera | MP 2607 | Sainkhera Jhinkoli Rd to Tumda | 1.6 | GSB
218 | PMGSY | IV | CGM IV | Narsinghpur | Chawarpatha | MP 2612 | Bohani (sh 22 to ) Ghatpipariya | 4.7 | G2
219 | PMGSY | IV | CGM IV | Narsinghpur | Chichli | MP 2612 | Batesara Khamariya | 4.3 | BT
220 | PMGSY | IV | CGM IV | Narsinghpur | Gotegaon | MP 2611 | Gotegaon Chargaon Rd Pipariya (Mawai) | 2.49 | G3
221 | PMGSY | IV | CGM IV | Narsinghpur | Gotegaon | MP 2611 | Kunda Rd to Nagwara | 4.3 | BT
222 | PMGSY | IV | CGM IV | Narsinghpur | Kareli | MP 2611 | Dewakachhar to Chinki Road | 8.53 | G3
223 | PMGSY | IV | CGM IV | Narsinghpur | N'pur | MP 2611 | Nayagoan Ghat Piparia | 5.31 | BT
224 | PMGSY | IV | CGM IV | Narsinghpur | N'pur | MP 2611 | Tindani Karhaiya Road | 4.38 | BT
225 | PMGSY | IV | CGM IV | Narsinghpur | Saikheda | MP 2612 | Chirhakalan Bagdara | 4.16 | G3
226 | PMGSY | IV | CGM IV | Narsinghpur | Saikheda | MP 2612 | Sirsiri to Muar | 2.2 | G3
227 | PMGSY | IV | CGM IV | Narsinghpur | Saikheda | MP 2612 | Gadarwara to Bodri | 1.65 | G3
228 | PMGSY | IV | CGM IV | Narsinghpur | Saikheda | MP 2612 | Gadarwara Saikheda rd to Pithwani | 2.33 | G3
229 | PMGSY | IV | CGM IV | Narsinghpur | Saikheda | MP 2612 | Jhinkoli to Niwawar | 2.2 | G3
230 | PMGSY | IV | CGM IV | Narsinghpur | Saikheda | MP 2612 | Bamhani kala to Mudgula | 2.65 | GSB
231 | PMGSY | V | CGM IV | Narsinghpur | ChawarPatha | MP 2615 | NH 26 (Lingha) To Imghiri Road | 8.4 | Earthwork
232 | PMGSY | V | CGM IV | Narsinghpur | ChawarPatha | MP 2615 | NH 12 To Bandhi Road | 6.09 | Earthwork
233 | PMGSY | V | CGM IV | Narsinghpur | Gotegaon | MP 2614 | Sankal Gotegaon To Khobi Road | 9 | GSB
234 | PMGSY | V | CGM IV | Narsinghpur | Gotegaon | MP 2617 | Dhamna To Sankal | 13.55 | G2
235 | PMGSY | V | CGM IV | Narsinghpur | Gotegaon | MP 2618 | Khobi To Sankal Road | 6 | GSB
236 | PMGSY | V | CGM IV | Narsinghpur | Gotegaon | MP 2618 | Khobi To Mohas | 4.08 | GSB
237 | PMGSY | V | CGM IV | Narsinghpur | Narsinghpur | MP 2613 | Narsinghpur Sankal Road To Machwara | 3.5 | GSB
238 | PMGSY | V | CGM IV | Narsinghpur | Narsinghpur | MP 2613 | Narsinghpur Sankal Road To Dhamna | 11 | G2
239 | PMGSY | V | CGM IV | Narsinghpur | Saikheda | MP 2616 | Bamhorikala To Pipariyakala Road | 6.12 | Earthwork
240 | PMGSY | V | CGM IV | Narsinghpur | Saikheda | MP 2619 | Gadarwara Pipariya (SH 22) Road To Gardha | 6 | Preparatory
241 | PMGSY | V | CGM IV | Narsinghpur | Saikheda | MP 2619 | Saikheda To Bamhorikhurd Road | 0.95 | Notstart
242 | ADB | III | CGM IV | Rewa | Hanumana | MP 3253 | Hanumana to Bahuti | 22.5
243 | ADB | III | CGM IV | Rewa | Hanumana | MP 3255 | Shahpur to Hardi | 2.425
244 | ADB | III | CGM IV | Rewa | Hanumana | MP 3255 | Charaiya to Tatihara | 4.05
245 | ADB | III | CGM IV | Rewa | Hanumana | MP 3255 | Pahadi Gada Road to Bhamra Bhagadeva | 4.8
246 | ADB | III | CGM IV | Rewa | Jawa | MP 3252 | Jawa Dabhoura Road to Ghooman | 12.1
247 | ADB | III | CGM IV | Rewa | Jawa | MP 3254 | Raghunathganj to Madna | 13.25
248 | ADB | III | CGM IV | Rewa | Rewa | MP 3251 | Nh-75 to jori | 4.7
249 | ADB | III | CGM IV | Rewa | Rewa | MP 3251 | Nh-7 to gadariya | 3.2
250 | ADB | III | CGM IV | Rewa | Rewa | MP 3251 | Rewa semariya road to puraini jagir via puraini kothar | 4.25
251 | PMGSY | II | CGM IV | Rewa | Naigarhi | MP 3204 | Rampur Approach road | 0.85 | G3
252 | PMGSY | II | CGM IV | Rewa | Raipur (K) | MP 3205 | Lohandwar Approach road | 4 | G3
253 | PMGSY | II | CGM IV | Rewa | Rewa | MP 3205 | Beerkham Gautman tola to Chaura | 4.05 | G3
254 | PMGSY | II | CGM IV | Rewa | Sirmour | MP 3205 | Dadhiya to Kushwar | 3.64 | G3
255 | PMGSY | III | CGM IV | Rewa | Mauganj | MP 3209 | Dighoul to Hatwa Saraihan | 2.5 | G3
256 | PMGSY | III | CGM IV | Rewa | Raipur Karchuliyan | MP 3209 | NH7 to Nawahoan Kothar | 5.74 | G3
257 | PMGSY | III | CGM IV | Rewa | Tyonthar | MP 3208 | Deeh to Amiliya Korown Mangi | 6 | G3
258 | PMGSY | III | CGM IV | Rewa | Tyonthar | MP 3208 | Sonauri to Chaura Nankar | 6.14 | G2
259 | PMGSY | IV | CGM IV | Rewa | Gangeo | MP 3213 | Pool01 to Sansarpur | 2.05 | G2
260 | PMGSY | IV | CGM IV | Rewa | Gangeo | MP 3213 | Barrehi to Mauhariya | 3.55 | Not started
261 | PMGSY | IV | CGM IV | Rewa | Gangeo | MP 3213 | Gadhawa to Rampurwa | 2.4 | Earthwork
262 | PMGSY | IV | CGM IV | Rewa | Hanumana | MP 3216 | Paipkhar to Phool Bajarang Singh | 2.88 | Not started
263 | PMGSY | IV | CGM IV | Rewa | Hanumana | MP 3216 | Shahpur to Belaunhikala | 1.88 | Not started
264 | PMGSY | IV | CGM IV | Rewa | Hanumana | MP 3216 | Ghogham to Gada | 7.5 | G3
265 | PMGSY | IV | CGM IV | Rewa | Jawa | MP 3213 | Rambag Rimari to Khajha | 3.7 | Not started
266 | PMGSY | IV | CGM IV | Rewa | Mauganj | MP 3214 | Dhera to Majhigawan | 5 | G3
267 | PMGSY | IV | CGM IV | Rewa | Mauganj | MP 3214 | Farahada to Hardi | 2.4 | G2
268 | PMGSY | IV | CGM IV | Rewa | Mauganj | MP 3214 | Raipur Sitapur Road to Badakhara | 2 | G2
269 | PMGSY | IV | CGM IV | Rewa | Naigarhi | MP 3215 | Senua Paharakha Road to Baijala | 2 | Not started
270 | PMGSY | IV | CGM IV | Rewa | Raipur (K) | MP 3214 | Raghurajgarh to Ulhikala | 7.2 | G2
271 | PMGSY | IV | CGM IV | Rewa | Rewa | MP 3212 | Tamara Road to Deora | 2.85 | G2
272 | PMGSY | IV | CGM IV | Rewa | Rewa | MP 3212 | Govindgarh Road to Raura | 1.55 | GSB
273 | PMGSY | IV | CGM IV | Rewa | Teonthar | MP 3215 | Chaura to kakaraha No.1 | 6.1 | G3
274 | PMGSY | V | CGM IV | Rewa | Gangeo | MP 3222 | Sirsa to Baseda | 4.6 | G2
275 | PMGSY | V | CGM IV | Rewa | Gangeo | MP 3222 | NH-27 Adhiha No.2 to Bela | 3.9 | Earth work
276 | PMGSY | V | CGM IV | Rewa | Gangeo | MP 3222 | NH-7 Tikuri to Sathini | 3.1 | GSB
277 | PMGSY | V | CGM IV | Rewa | Mauganj | MP 3217 | Raipur Sitapur Road to Khaira Kankesara | 3.9 | G2
278 | PMGSY | V | CGM IV | Rewa | Mauganj | MP 3217 | NH-7 to Mudariya Chauban | 3.75 | G2
279 | PMGSY | V | CGM IV | Rewa | Raipur Karchuliyan | MP 3218 | Ajgaraha to Itaha | 5.25 | G2
280 | PMGSY | V | CGM IV | Rewa | Raipur Karchuliyan | MP 3219 | Raghurajgarh to Pathraha | 10.4 | Earth work
281 | PMGSY | V | CGM IV | Rewa | Sirmour | MP 3218 | Rewa Sirmour Road to Khair | 6.25 | Not start
282 | PMGSY | V | CGM IV | Rewa | Sirmour | MP 3218 | Majhigawan to Majhiyar (Chaman Chauraha) | 3.85 | Not start
283 | PMGSY | V | CGM IV | Rewa | Sirmour | MP 3218 | Majhigawan Majhiyar Road to Labhouli | 2.3 | Not start
284 | PMGSY | V | CGM IV | Rewa | Teonther | MP 3220 | Chak to Sonauri (Kakaraha) | 22.4 | Earth work
285 | PMGSY | V | CGM IV | Rewa | Teonther | MP 3221 | Raipur Mod to Dhakra No.1 | 5.6 | Earth work
286 | PMGSY | V | CGM IV | Rewa | Teonther | MP 3221 | Raipur Mod to Bajra | 3.25 | Earth work
287 | PMGSY | V | CGM IV | Rewa | Teonther | MP 3221 | Bari to Barikala | 1 | Earth work
288 | PMGSY | V | CGM IV | Rewa | Teonther | MP 3221 | Bari to Noudhiya | 2.4 | GSB
289 | PMGSY | V | CGM IV | Rewa | Teonther | MP 3221 | Rajaha to Kaitha | 3.5 | Earth work
290 | ADB | I | CGM IV | Satna | Amarpatan | MP 3451 | Pagara App. Road | 3.56 | Earth work
291 | ADB | I | CGM IV | Satna | Amarpatan | MP 3451 | Kirhai-Ramnagar Road to Naugawan | 1.97 | GSB
292 | ADB | I | CGM IV | Satna | Maihar | MP 3451 | NH-7 to Kutai | 4.55 | GSB
293 | ADB | I | CGM IV | Satna | Maihar | MP 3451 | NH-7 to Bansipur | 9.82 | BT
294 | ADB | I | CGM IV | Satna | Majhagawan | MP 3452 | Jhari to Padri Road | 6.9 | G2
295 | ADB | I | CGM IV | Satna | Majhagawan | MP 3452 | Chaubepur to Sejwar kharha Road | 7.93 | G3
296 | ADB | I | CGM IV | Satna | Ramnagar | MP 3451 | SH-11 to Mankahri road | 2.5 | G2
297 | ADB | I | CGM IV | Satna | Ramnagar | MP 3451 | Karra App. Road | 2.15 | G2
298 | ADB | I | CGM IV | Satna | Rampur Baghelan | MP 3452 | Mahurachh to Badhaura Road | 2.87 | G3
299 | ADB | I | CGM IV | Satna | Unchehra | MP 3452 | Bharhut App. Road | 5.8 | G2
300 | ADB | III | CGM IV | Satna | Majhgawan | MP 3455 | Jaitwara Kulkadiya Rd | 15.23 | G2
301 | ADB | III | CGM IV | Satna | Majhgawan | MP 3455 | Jaitwara Kulkadiya Rd to Badkher | 2.2 | G2
302 | ADB | III | CGM IV | Satna | Majhgawan | MP 3455 | Jaitwara Kulkadiya Rd to Marwa | 1 | G2
303 | ADB | III | CGM IV | Satna | Majhgawan | MP 3455 | Jaitwara Kulkadiya Rd to Machkhada | 6.8 | G2
304 | ADB | III | CGM IV | Satna | Nagod | MP 3453 | NH-75 to Hada | 8.4 | G3
305 | ADB | III | CGM IV | Satna | Nagod | MP 3453 | Hada to Pakar | 2.2 | GSB
306 | ADB | III | CGM IV | Satna | Nagod | MP 3453 | Pakar Rd to Khakharaundha | 1.5 | G3
307 | ADB | III | CGM IV | Satna | Nagod | MP 3453 | Pakar Rd to Kota No. 1 | 4.5 | GSB
308 | ADB | III | CGM IV | Satna | Rampur Baghelan | MP 3454 | Rampur Chhibaura Rd to Tapa | 3.9 | Earth work
309 | ADB | III | CGM IV | Satna | Rampur Baghelan | MP 3454 | Satna Rewa Rd to Hinauti | 7.95 | G2
310 | ADB | III | CGM IV | Satna | Rampur Baghelan | MP 3454 | Tikuriya to Chakdahi | 7.12 | Earth work
311 | PMGSY | I | CGM IV | Satna | Ramnagar | MP 5002 | Satna Umariya roadto Sulkhama | 4 | G3
312 | PMGSY | III | CGM IV | Satna | Amarpatan | MP 3407 | Kathaha0to Majhgawan | 3 | G3
313 | PMGSY | III | CGM IV | Satna | Amarpatan | MP 3409 | Kirhai Ramgarh Rd to Chorkhari | 2.61 | G2
314 | PMGSY | III | CGM IV | Satna | Maihar | MP 3408 | NH070to Ludhauti Approach Road | 4.35 | G3
315 | PMGSY | III | CGM IV | Satna | Maihar | MP 3408 | NH070to Karaundi kap Nadan | 6.85 | G2
316 | PMGSY | III | CGM IV | Satna | Maihar | MP 3408 | Maihar0Kaimore Rd to Ghorbai | 0.6 | Earth work
317 | PMGSY | III | CGM IV | Satna | Majhgawan | MP 3412 | Galbal0to Bamhauri | 2.56 | G3
318 | PMGSY | III | CGM IV | Satna | Nagod | MP 3411 | Jaso0to surdaha khurd Approach Road | 16.45 | G2
319 | PMGSY | III | CGM IV | Satna | Ramnagar | MP 3409 | Marwar0Harrai Rd to Babupur | 3.05 | GSB
320 | PMGSY | III | CGM IV | Satna | Rampur Baghelan | MP 3409 | Satna Amatrpatan Rd. to Gohari | 4.5 | G2
321 | PMGSY | III | CGM IV | Satna | Sohawal | MP 3413 | Kothi0Singhpur Rd toKhangarh | 4.825 | G3
322 | PMGSY | III | CGM IV | Satna | Sohawal | MP 3413 | Kothi0Singhpur Rd to Bhanwar | 2.3 | BT
323 | PMGSY | III | CGM IV | Satna | Unchehra | MP 3410 | Kulgarhi-to Manikpur Road | 2.7 | G2
324 | PMGSY | III | CGM IV | Satna | Unchehra | MP 3410 | Maihar-Unchehra road to Kothi | 3.15 | G2
325 | PMGSY | IV | CGM IV | Satna | Maihar | MP 3416 | NH-7 to Hinauta kala | 7.545 | G3
326 | PMGSY | IV | CGM IV | Satna | Majhgawan | MP 3417 | Birsinghpur Road to Patna kala | 9.65 | G3
327 | PMGSY | IV | CGM IV | Satna | Ramnagar | MP 3415 | Rewa Shahdol road to Suhila | 5.35 | G3
328 | PMGSY | IV | CGM IV | Satna | Ramnagar | MP 3415 | Jigna Hinauti Road to Judwani | 3.23 | G3
329 | PMGSY | IV | CGM IV | Satna | Rampur Baghelan | MP 3417 | Jaitwara0.00Birsinghpur Road to Choond khurd | 3.2 | GSB
330 | PMGSY | IV | CGM IV | Satna | Sohawal | MP 3418 | Raigawan road to Dilaura | 10.65 | BT
331 | PMGSY | IV | CGM IV | Satna | Unchehra | MP 3416 | Satna0.00Unchehra rd to Pondi Garada | 9.37 | G3
332 | PMGSY | V | CGM IV | Satna | Amarpatan | MP 3419 | NH-7 to Dhaurahra | 3.84 | G2
333 | PMGSY | V | CGM IV | Satna | Amarpatan | MP 3419 | NH-7 to Raikwara | 2.23 | G2
334 | PMGSY | V | CGM IV | Satna | Amarpatan | MP 3419 | NH-7 to Barreh Bada | 2.1 | G2
335 | PMGSY | V | CGM IV | Satna | Maihar | MP 3420 | Deviji road to Udaypur | 1.45 | G2
336 | PMGSY | V | CGM IV | Satna | Maihar | MP 3420 | Delha Karaiya road to Madai | 0.6 | Earth work
337 | PMGSY | V | CGM IV | Satna | Maihar | MP 3420 | Delha Karaiya Road | 12.4 | Preparatory
338 | PMGSY | V | CGM IV | Satna | Maihar | MP 3420 | Delha Karaiya Road to Mantolwa | 1.3 | G2
339 | PMGSY | V | CGM IV | Satna | Maihar | MP 3420 | Delha Karaiya Road to Umari Fifri | 2.85 | G2
340 | PMGSY | V | CGM IV | Satna | Maihar | MP 3420 | Delha Karaiya Road to Tenduhata | 1.05 | GSB
341 | PMGSY | V | CGM IV | Satna | RamNagar | MP 3419 | Maryadpur to Deodahi Jattha tola | 4.53 | G2
342 | PMGSY | V | CGM IV | Satna | RamNagar | MP 3419 | Jigna-Kaitha road to Paipakhara | 3.5 | G2
343 | PMGSY | V | CGM IV | Satna | Sohawal | MP 3421 | Kothi-Jaitwara road to Nayagaon | 3.8 | G2
344 | PMGSY | V | CGM IV | Satna | Sohawal | MP 3421 | Satna-Kothi road to Ahirgaon | 6.275 | G2
345 | PMGSY | V | CGM IV | Satna | Sohawal | MP 3421 | Satna-Singhpur road to Tikar | 1.88 | G3
346 | PMGSY | V | CGM IV | Satna | Unchehra | MP 3421 | Podi Garada road to Karahi khurd | 1.35 | G2
347 | PMGSY | V | CGM IV | Satna | Unchehra | MP 3421 | Podi Garada road to Pathrahata | 6.8 | G3
348 | ADB | I | CGM IV | Seoni | Dhanora | MP 3652 | Dhanora to Gudhna | 12.85 | BT
349 | ADB | I | CGM IV | Seoni | Lakhnadone | MP 3652 | NH-7 to Dhankakri mal | 11 | BT
350 | ADB | III | CGM IV | Seoni | Chhapara | MP 3654 | Sarekha tola to Payli Koudiya Road | 2.15 | GSB
351 | ADB | III | CGM IV | Seoni | Chhapara | MP 3654 | Sadak Seoni to Paylikhurd Road | 5.15 | Not start
352 | ADB | III | CGM IV | Seoni | Chhapara | MP 3654 | Payli Khurd to Payli kalan road | 2.5 | GSB
353 | ADB | III | CGM IV | Seoni | Dhanora | MP 3656 | Dhanora - Sujawalpur Rd. (T02) Tua Ghoghra to Bhalpani | 3.15 | GSB
354 | ADB | III | CGM IV | Seoni | Dhanora | MP 3656 | Ganeshganj - Sunwara Rd.(T05) Lamta to Harrai Rd. | 3.98 | GSB
355 | ADB | III | CGM IV | Seoni | Dhanora | MP 3656 | Lamta -Sunwara - Amanala Rd. | 14.1 | GSB
356 | ADB | III | CGM IV | Seoni | Dhanora | MP 3656 | Gorakhpur to Balpura | 2.03 | GSB
357 | ADB | III | CGM IV | Seoni | Ghansore | MP 3656 | Baroda-Barda Road to Bineki khurd Road | 1 | Earth work
358 | ADB | III | CGM IV | Seoni | Ghansore | MP 3656 | Ghansore Mandla Road to Tindua | 1.85 | Not start
359 | ADB | III | CGM IV | Seoni | Ghansore | MP 3656 | Ghansore Kedarpur Road to Putrai | 3.4 | Earth work
360 | ADB | III | CGM IV | Seoni | Ghansore | MP 3656 | Shikara Ghansore Road to Samnapur | 1.65 | Not start
361 | ADB | III | CGM IV | Seoni | Ghansore | MP 3656 | Ghansore Kedarpur Road to Karithoon | 0.725 | Not start
362 | ADB | III | CGM IV | Seoni | Kurai | MP 3653 | NH7 (T09) Gopalganj to Amgaon Rd. | 2.7 | GSB
363 | ADB | III | CGM IV | Seoni | Kurai | MP 3653 | Suktara- Karmajhiri (T07) Badalpar to Dungariya Rd. | 3.2 | Not start
364 | ADB | III | CGM IV | Seoni | Kurai | MP 3653 | Suktara - Badalpar Rd. (T07) | 11 | Preparatory
365 | ADB | III | CGM IV | Seoni | Kurai | MP 3653 | Partapur to Lawesarra Road | 6.13 | GSB
366 | ADB | III | CGM IV | Seoni | Kurai | MP 3653 | Bakodi to Badgaon Road | 3.4 | GSB
367 | ADB | III | CGM IV | Seoni | Kurai | MP 3653 | Badalpar-Belpeth Road to Sagar | 1.9 | GSB
368 | ADB | III | CGM IV | Seoni | Kurai | MP 3653 | Belpeth to Ghoghari | 2.05 | Earth work
369 | ADB | III | CGM IV | Seoni | Kurai | MP 3653 | Badalpar-Belpeth Road to Kotkasa | 1.35 | GSB
370 | ADB | III | CGM IV | Seoni | Lakhnadone | MP 3654 | Dhooma - Rathi Rd. (T04) Jamunpani to Chargaon Road | 3.45 | Not start
371 | ADB | III | CGM IV | Seoni | Lakhnadone | MP 3654 | Dhooma to Jamunpani Road (T04) | 8 | GSB
372 | ADB | III | CGM IV | Seoni | Lakhnadone | MP 3655 | NH-26 (T12) Goura Bibi to Patharkathi Rd. | 3.05 | GSB
373 | ADB | III | CGM IV | Seoni | Lakhnadone | MP 3655 | Adegon Madhi to Khamariya Goojar Road | 1.6 | Earth work
374 | ADB | III | CGM IV | Seoni | Lakhnadone | MP 3655 | Adegoan Kohka Madhi Road | 19.6 | G2
375 | PMGSY | IV | CGM IV | Seoni | Chhapara | MP 3613 | Keolari to Bijadeori | 12.95 | Bt
376 | PMGSY | IV | CGM IV | Seoni | Kurai | MP 3612 | Kurai Pindrai Butte to Patan | 11 | GSB
377 | PMGSY | V | CGM IV | Seoni | Barghat | MP 3616 | Seoni - Katangi Rd. (T10) Ari to Sukla | 4.35 | G2
378 | PMGSY | V | CGM IV | Seoni | Barghat | MP 3616 | Barghat Kathi Road (Sarra) to Chirchira | 1.875 | G3
379 | PMGSY | V | CGM IV | Seoni | Barghat | MP 3616 | Barghat to Sarra Road | 7.5 | G2
380 | PMGSY | V | CGM IV | Seoni | Barghat | MP 3616 | Seoni Balaghat Rd. (T05) Pindrai to Budhenakhurd | 1.975 | G3
381 | PMGSY | V | CGM IV | Seoni | Chhapara | MP 3617 | Keolari -Bhedki Rd.(T05) Beejadeoari to Bari Rd. | 3.525 | G3
382 | PMGSY | V | CGM IV | Seoni | Chhapara | MP 3617 | NH-7 (Chhapara) to Chamari Khurd Road (Dongarwani tola) | 21.5 | G3
383 | PMGSY | V | CGM IV | Seoni | Ghansore | MP 3618 | Manegaon to Chargaon Road | 2.6 | G3
384 | PMGSY | V | CGM IV | Seoni | Ghansore | MP 3618 | Banjari to Shikara Road | 15.5 | BT
385 | PMGSY | V | CGM IV | Seoni | Seoni | MP 3616 | NH-7 (Bandol) to Bakhari road | 20 | BT
386 | ADB | III | CGM IV | Shahdol | Burhar | MP 3853 | Keshwahi to Jamuniha | 1.7 | Earth work
387 | ADB | III | CGM IV | Shahdol | Burhar | MP 3853 | Padkhuri Keshwahi to Tengha | 15.73 | Earth work
388 | ADB | III | CGM IV | Shahdol | Burhar | MP 3853 | Jaitpur to Galhata | 4.7 | Preparatory
389 | ADB | III | CGM IV | Shahdol | Gohparu | MP 3852 | RSA road to Barha | 2.04 | Earth work
390 | ADB | III | CGM IV | Shahdol | Gohparu | MP 3852 | RSA road to Barkoda | 13.2 | Earth work
391 | ADB | III | CGM IV | Shahdol | Gohparu | MP 3852 | Barkoda to Umariya | 1.63 | Not start
392 | ADB | III | CGM IV | Shahdol | Jaisingh Nagar | MP 3851 | SH 10 to Thengaraha | 2.48 | Preparatory
393 | ADB | III | CGM IV | Shahdol | Jaisingh Nagar | MP 3851 | BBS road to Pondi | 11.95 | Preparatory
394 | ADB | III | CGM IV | Shahdol | Jaisingh Nagar | MP 3851 | BBS road to Amdih | 3.48 | Preparatory
395 | ADB | III | CGM IV | Shahdol | Jaisingh Nagar | MP 3851 | SH 10 to Kanadikala | 1.55 | Not start
396 | ADB | III | CGM IV | Shahdol | Jaisingh Nagar | MP 3851 | BBS road to Nagnaudi | 1.95 | Not start
397 | ADB | III | CGM IV | Shahdol | Jaithari | MP 3854 | Khuta Tola to Nigaura | 4.33 | Not start
398 | ADB | III | CGM IV | Shahdol | Jaithari | MP 3854 | AJV road to Padariya | 1.65 | Not start
399 | ADB | III | CGM IV | Shahdol | Jaithari | MP 3854 | Sakara to Taradand | 4.48 | Not start
400 | ADB | III | CGM IV | Shahdol | Kotma | MP 3855 | Nigwani to Reusa | 7.4 | Earth work
401 | ADB | III | CGM IV | Shahdol | Kotma | MP 3855 | Nigwani Reusa road to Lalpur | 1.2 | Preparatory
402 | ADB | III | CGM IV | Shahdol | Kotma | MP 3855 | Nigwani road to Urtan | 4.83 | Earth work
403 | ADB | III | CGM IV | Shahdol | Puspraj garh | MP 3854 | SH 9 to Karanpathar | 4.1 | Not start
404 | ADB | III | CGM IV | Shahdol | Puspraj garh | MP 3854 | RSA road to Bahpur | 3.03 | Not start
405 | ADB | III | CGM IV | Shahdol | Puspraj garh | MP 3854 | Ledra to Chilhiyamar | 4.93 | Not start
406 | ADB | III | CGM IV | Shahdol | Sohagpur | MP 3852 | Kalyanpur Chunia to Majhgawan | 11.55 | Earth work
407 | PMGSY | III | CGM IV | Shahdol | Beohari | MP 3808 | Hirwar to Pathrehi | 11.63 | G3
408 | PMGSY | III | CGM IV | Shahdol | Burhar | MP 3807 | Galhatha to Balbadhrapur | 1.474 | G2
409 | PMGSY | III | CGM IV | Shahdol | Burhar | MP 3807 | Kaishori to Semreha | 6.1 | Earth work
410 | PMGSY | III | CGM IV | Shahdol | Gohparu | MP 3808 | Chhohari to Uchehara | 2.924 | G2
411 | PMGSY | III | CGM IV | Shahdol | Jaisinghnagar | MP 3808 | Tetka to Bansa | 8.438 | G2
412 | PMGSY | III | CGM IV | Shahdol | Sohagpur | MP 3807 | Kalyanpur to Sendurichuni | 4 | BT
413 | PMGSY | IV | CGM IV | Shahdol | Beohari | MP 3810 | SH 9 to Sukhad | 16.35 | G2
414 | PMGSY | IV | CGM IV | Shahdol | Burhar | MP 3809 | Keshwahi to Rupoula | 10.15 | Notstart
415 | PMGSY | IV | CGM IV | Shahdol | Gohparu | MP 3810 | Chuhari to Kanwahi | 14.83 | G2
416 | PMGSY | IV | CGM IV | Shahdol | Jaisingh Nagar | MP 3810 | SH 10 to Mohani | 8.006 | G2
417 | PMGSY | IV | CGM IV | Shahdol | Jaithari | MP 3811 | AJV Road to Sulkhari | 10.2 | BT
418 | PMGSY | V | CGM IV | Shahdol | Anuppur | MP 3814 | Cholna road to Ura | 2.7 | G3
419 | PMGSY | V | CGM IV | Shahdol | Anuppur | MP 3814 | Reula to Chappani | 8.5 | G2
420 | PMGSY | V | CGM IV | Shahdol | Beohari | MP 3812 | Sukhad Junction to Jhiriya | 2.73 | GSB
421 | PMGSY | V | CGM IV | Shahdol | Beohari | MP 3812 | Budwa to Kumhiya | 3.575 | G2
422 | PMGSY | V | CGM IV | Shahdol | Beohari | MP 3812 | Beohari to Bijaha | 3.8 | G2
423 | PMGSY | V | CGM IV | Shahdol | Gohparu | MP 3813 | RSA road to Khand | 5.3 | G3
424 | PMGSY | V | CGM IV | Shahdol | Gohparu | MP 3813 | Ashwari to Godaru | 13.55 | G2
425 | PMGSY | V | CGM IV | Shahdol | Jaithari | MP 3815 | AJV road to Sinduri | 2.35 | Preparatory
426 | PMGSY | V | CGM IV | Shahdol | Jaithari | MP 3815 | AJV road to Barri | 3.6 | Preparatory
427 | PMGSY | V | CGM IV | Shahdol | Jaithari | MP 3815 | Lapta road to Beed | 1.9 | GSB
428 | PMGSY | V | CGM IV | Shahdol | Jaithari | MP 3815 | AJV road to Pondi | 10.23 | GSB
429 | PMGSY | V | CGM IV | Shahdol | Puspraj Garh | MP 3815 | Rajendragram Karoundi to Majhgaon | 4.25 | G2
430 | PMGSY | V | CGM IV | Shahdol | Puspraj Garh | MP 3815 | ND road to Paraswar | 5.5 | Earth work
431 | PMGSY | V | CGM IV | Shahdol | Sohagpur | MP 3813 | Shahdol Kudari to Pongari | 9.275 | G2
432 | ADB | I | CGM IV | Sidhi | Majhauli | MP 4152 | Chamradol to Badkadol | 9.435 | Preparatory
433 | ADB | I | CGM IV | Sidhi | Rampur Naikin | MP 4151 | Katauli-Mamdar Gaddi Road | 22.223 | G2
434 | ADB | I | CGM IV | Sidhi | Rampur Naikin | MP 4151 | Main Road (Bahera) to Chorgadi | 7.415 | G2
435 | ADB | I | CGM IV | Sidhi | Sihawal | MP 4152 | Bahari Hanumana Road to Bithauli | 11.326 | G2
436 | ADB | III | CGM IV | Sidhi | Chitrangi | MP 4154 | Bagaiya to Kapurdehi | 7.9 | Not start
437 | ADB | III | CGM IV | Sidhi | Chitrangi | MP 4154 | Baidya Chauraha to Khokhwa | 13 | Earth work
438 | ADB | III | CGM IV | Sidhi | Deosar | MP 4155 | Atarwa to Khandauli | 12.75 | Not start
439 | ADB | III | CGM IV | Sidhi | Deosar | MP 4155 | Jiyawan to Atarwa | 9.35 | Not start
440 | ADB | III | CGM IV | Sidhi | Deosar | MP 4158 | Khairabada to Umarhar | 2 | Not start
441 | ADB | III | CGM IV | Sidhi | Deosar | MP 4158 | Deosar to Khairabada | 6.3 | Not start
442 | ADB | III | CGM IV | Sidhi | Deosar | MP 4158 | Jogini to Purwa Jagir | 5.65 | Preparatory
443 | ADB | III | CGM IV | Sidhi | Deosar | MP 4159 | Baghadeeh to Ujjaini | 3.6 | Not start
444 | ADB | III | CGM IV | Sidhi | Deosar | MP 4159 | Baghadeeh to Jobgarh | 2.85 | Not start
445 | ADB | III | CGM IV | Sidhi | Deosar | MP 4159 | Lohradol to Mahrail | 2.8 | Not start
446 | ADB | III | CGM IV | Sidhi | Kusmi | MP 4156 | Kusmi-Medra Road to Gajar | 6.2 | Not start
447 | ADB | III | CGM IV | Sidhi | Kusmi | MP 4156 | Kusmi (Bhagwawr) to Medra (Up to Rauhal) | 11 | Not start
448 | ADB | III | CGM IV | Sidhi | Sidhi | MP 4157 | Gandhigram-Hadbado Road to Bhatha | 7.6 | Earth work
449 | ADB | III | CGM IV | Sidhi | Sidhi | MP 4157 | Kham-Pathraula Road to Udaisa | 5 | Not start
450 | ADB | III | CGM IV | Sidhi | Sidhi | MP 4157 | Kham-Pathraula Road (Up to Barhai) | 6.2 | Not start
451 | ADB | III | CGM IV | Sidhi | Waidhan | MP 4153 | SH-6 to Chingi Tola | 4.05 | GSB
452 | ADB | III | CGM IV | Sidhi | Waidhan | MP 4153 | SH-6 to Teldah | 2.88 | Preparatory
453 | ADB | III | CGM IV | Sidhi | Waidhan | MP 4153 | Karaunti to Barahpan | 14.15 | GSB
454 | PMGSY | III | CGM IV | Sidhi | Majhauli | MP 4112 | Chamradol to Bodari Tola | 5 | BT
455 | PMGSY | IV | CGM IV | Sidhi | Kusmi | MP 4116 | Main Road to Katarwar | 4.7 | G3
456 | PMGSY | IV | CGM IV | Sidhi | Kusmi | MP 4116 | Haiki to Kota | 6.04 | GSB
457 | PMGSY | IV | CGM IV | Sidhi | Majhauli | MP 4116 | Main Road to Dhuandol | 2.2 | GSB
458 | PMGSY | IV | CGM IV | Sidhi | Majhauli | MP 4116 | Gijwar to Barseni | 3.9 | G3
459 | PMGSY | IV | CGM IV | Sidhi | Rampur Naikin | MP 4114 | Main Road to Jamuniha No. 2 | 2.09 | Deleted
460 | PMGSY | IV | CGM IV | Sidhi | Sidhi | MP 4115 | Main Road to Badhauna | 5 | BT
461 | PMGSY | IV | CGM IV | Sidhi | Sidhi | MP 4115 | Main Road to Chhuhiya | 6.9 | BT
462 | PMGSY | V | CGM IV | Sidhi | Chitrangi | MP 41219 | Karila Road to Barkoni | 3.5 | G2
463 | PMGSY | V | CGM IV | Sidhi | Chitrangi | MP 41219 | Churki to Chakariya | 4.15 | G2
464 | PMGSY | V | CGM IV | Sidhi | Chitrangi | MP 41219 | NH-75 to Bhalugarh | 3.75 | G2
465 | PMGSY | V | CGM IV | Sidhi | Majhauli | MP 4120 | Majhauli-Madwas-Mahkhor Road to Thonga | 4.265 | G2
466 | PMGSY | V | CGM IV | Sidhi | Majhauli | MP 4120 | Majhauli-Madwas-Mahkhor Road (Chuwahi to Majhauli College) | 6 | G2
467 | PMGSY | V | CGM IV | Sidhi | Majhauli | MP 4120 | Majhauli-Madwas Road to Diyadol | 2.45 | G3
468 | PMGSY | V | CGM IV | Sidhi | Majhauli | MP 4120 | Thonga to Joba | 5.2 | G3
469 | PMGSY | V | CGM IV | Sidhi | Rampur Naikin | MP 4122 | Churhat-Amiliya Main Road to Padkhuri 586 | 9.45 | G3
470 | PMGSY | V | CGM IV | Sidhi | Sihawal | MP 4121 | Bahari-Hanumana Road to Tilai | 5 | Preparatory
471 | PMGSY | V | CGM IV | Sidhi | Sihawal | MP 4121 | Bahari-Hanumana Road to Jethula | 8.4 | G3
472 | PMGSY | V | CGM IV | Sidhi | Waidhan | MP 4118 | Kumhiya to Malgotola | 10.8 | G3
473 | PMGSY | V | CGM IV | Sidhi | Waidhan | MP 4118 | Mada to Makrohar (Up to Dhodhitola) | 8 | G3
474 | ADB | III | CGM IV | Umaria | Manpur | MP 4451 | SH 10 to Padwar | 9.23 | Earth work
475 | PMGSY | III | CGM IV | Umaria | Manpur | MP 4403 | Sohagpur Manpur Rd. to Banraha | 8.6 | G3
476 | PMGSY | III | CGM IV | Umaria | Pali | MP 4403 | NH 78 to Salaiya | 5.8 | G3
477 | PMGSY | V | CGM IV | Umaria | Karkeli | MP 4405 | Chandiya Akhadar rd to Salaiya | 1.99 | Not start
478 | PMGSY | V | CGM IV | Umaria | Karkeli | MP 4405 | Umariya to Kachharwar | 11.75 | G2
479 | PMGSY | V | CGM IV | Umaria | Pali | MP 4405 | PAD road to Kurkucha | 1.78 | G3
480 | PMGSY | V | CGM IV | Umaria | Pali | MP 4405 | NH 78 to Barbaspur | 8.5 | G2
Total IV

## CGM MR
Format : CGM MR
Maintenance Report
Month |  | May06
S. N. | CGM | PIU | Total No. of completed packages upto date | Total No. of completed Roads upto date | No. of roads on which maintenance required | No. of roads on which maintenance work done | Estimate of expenditure incurred (i/c value of work done by the contractor in routine maintenance) Amount in Rs Lakhs | If there is gap between column 6 and column 7, No. of roads to be taken for maintenance in the next month | The name of the oldest road (with date of completion) still left without maintenance
[9 empty] | Name of Road | Date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | I | Betul
2 | I | Bhind
3 | I | Biaora
4 | I | Guna
5 | I | Gwalior
6 | I | Hoshangabad
7 | I | Morena
8 | I | Shivpuri
|  | Total | 0 | 0 | 0 | 0 | 0
9 | II | Bhopal
10 | II | Chhatarpur
11 | II | Damoh
12 | II | Panna
13 | II | Raisen
14 | II | Sagar
15 | II | Tikamgarh
16 | II | Vidisha
|  | Total | 0 | 0 | 0 | 0 | 0
17 | III | Barwani
18 | III | Dewas
19 | III | Dhar
20 | III | Indore
21 | III | Jhabua
22 | III | Khargone
23 | III | Mandsaur
24 | III | Ratlam
25 | III | Shajapur
26 | III | Ujjain
|  | Total | 0 | 0 | 0 | 0 | 0
27 | IV | Balaghat
28 | IV | Chhindwara
29 | IV | Dindori
30 | IV | Jabalpur
31 | IV | Katni
32 | IV | Mandla
33 | IV | Narsinghpur
34 | IV | Rewa
35 | IV | Satna
36 | IV | Seoni
37 | IV | Shahdol
38 | IV | Sidhi
|  | Total | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 0 | 0 | 0 | 0 | 0

## FinalBill
Complete Packages final Payment Details
S. No. | CGM | District | Name of completed Package | Final Payment made in the month Yes/No | If No, Status of final bill | Target month for final payment | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Yes | 2006-04-01
1 | I | Betul | MP 03 05 |  |  |  |  | No | 2006-05-01
2 | I | Betul | MP 0307 | [5 empty] | 2006-06-01
3 | I | Betul | MP 0308 | [5 empty] | 2006-07-01
4 | I | Betul | MP 0309 | [5 empty] | 2006-08-01
5 | I | Betul | MP 0312 | [5 empty] | 2006-09-01
6 | I | Guna | MP 1307 | [5 empty] | 2006-10-01
7 | I | Guna | MP 1312 | [5 empty] | 2006-11-01
8 | I | Guna | MP 1313 | [5 empty] | 2006-12-01
9 | I | Gwalior | MP 1405 | [5 empty] | 2007-01-01
10 | I | Morena | MP 2509 | [5 empty] | 2007-02-01
11 | I | Morena | MP 2511 | [5 empty] | 2007-03-01
12 | I | Bhind | MP 0411
13 | I | Vidisha | MP 6101
14 | I | Vidisha | MP 4506
15 | I | Vidisha | MP 4507
16 | I | Sheopur | MP 3702
17 | I | Sheopur | MP 3702 B
18 | I | Sheopur | MP 3705
19 | I | Shivpuri | MP 4012
20 | I | Shivpuri | MP 4013
21 | I | Shivpuri | MP 4015
| Total I |  |  | 0
1 | II | Sehore | MP 35 03
2 | II | Sehore | MP 35 04
3 | II | Raisen | MP 4301
4 | II | Raisen | MP 29 02
5 | II | Raisen | MP 29 05
6 | II | Raisen | MP 2906
7 | II | Raisen | MP 2908
8 | II | Chhatarpur | MP 06 02
9 | II | Chhatarpur | MP 06 07
10 | II | Tikamgarh | MP 4206
11 | II | Tikamgarh | MP 4207
12 | II | Tikamgarh | MP 4208
13 | II | Tikamgarh | MP 4209
14 | II | Sagar | MP 33 03
15 | II | Sagar | MP 33 13
| Total II |  |  | 0
1 | III | Dewas | MP 1007
2 | III | Dewas | MP 1008
3 | III | Dewas | MP 1009
4 | III | Shajapur | MP 3908
5 | III | Shajapur | MP 3909
6 | III | Shajapur | MP 3910
7 | III | Dhar | MP 1109
8 | III | Dhar | MP 1110
9 | III | Dhar | MP 1111
10 | III | Dhar | MP 1112
11 | III | Dhar | MP 1114
12 | III | Dhar | MP 1117
13 | III | Indore | MP 17 05
14 | III | Indore | MP 17 07
15 | III | Jhabua | MP 19 06
16 | III | Jhabua | MP 19 08
17 | III | Khargone | MP 22 03
18 | III | Khargone | MP 2207
19 | III | Khargone | MP 2208
20 | III | Barwani | MP 0205
21 | III | Barwani | MP 0207
22 | III | Barwani | MP 02-08
23 | III | Mandsaur | MP 24 03
24 | III | Neemuch | MP 27 03
25 | III | Ratlam | MP 3105
| Total III |  |  | 0
26 | IV | Balaghat | MP 0109
27 | IV | Balaghat | MP 0111
28 | IV | Balaghat | MP 0115
29 | IV | Chhindwara | MP 0713
30 | IV | Chhindwara | MP 0719
31 | IV | Jabalpur | MP 18 12
32 | IV | Jabalpur | MP 18 16
33 | IV | Katni | MP 20 02
34 | IV | Katni | MP 2005
35 | IV | Katni | MP 2007
36 | IV | Katni | MP 2009
37 | IV | Mandla | MP 23 11
38 | IV | Dindori | MP 12 04
39 | IV | Dindori | MP 12 05
40 | IV | Rewa | MP 32 06
41 | IV | Rewa | MP 32 07
42 | IV | Rewa | MP 32 11
43 | IV | Satna | MP 5001
44 | IV | Satna | MP 34 06a
45 | IV | Satna | MP 3414
46 | IV | Seoni | MP 3608
47 | IV | Seoni | MP 3610
48 | IV | Seoni | MP 3611
49 | IV | Seoni | MP 3614
50 | IV | Seoni | MP 3615
51 | IV | Narsinghpur | MP 26 02
52 | IV | Narsinghpur | MP 26 03
53 | IV | Narsinghpur | MP 26 06
54 | IV | Narsinghpur | MP 2608
55 | IV | Narsinghpur | MP 2610
56 | IV | Umaria | MP 44 04
57 | IV | Sidhi | MP 5702
58 | IV | Sidhi | MP 41 09
59 | IV | Sidhi | MP 4111
60 | IV | Sidhi | MP 4113
61 |  | Damoh | MP 08 06
62 |  | Damoh | MP 0811
| Total IV |  |  | 0
| Grand total |  |  | 0

## CGM PFB
Format : CGM PFB
Payment of Final Bills
Month |  | May06
S.N. | CGM | PIU | Total No. of completed packages upto date | No. of packages for which final payment have been made before the reporting month | Name of balance packages of which final payment not made before the reporting month | No. of package for which final payment made in the reporting month | Name of package for which final payment made in the reporting month | Total packages for which final payment cleared (Col 5 + Col 7) | If final payment not made reasons for delay | Name of completed packages targeted to for final payment in the next month | Name of the oldest completed package without final payment
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | I | Betul | [5 empty] | 0
2 | I | Bhind | [5 empty] | 0
3 | I | Biaora | [5 empty] | 0
4 | I | Guna | [5 empty] | 0
5 | I | Gwalior | [5 empty] | 0
6 | I | Hoshangabad | [5 empty] | 0
7 | I | Morena | [5 empty] | 0
8 | I | Shivpuri | [5 empty] | 0
|  | Total | 0 | 0 |  | 0 |  | 0
9 | II | Bhopal | [5 empty] | 0
10 | II | Chhatarpur | [5 empty] | 0
11 | II | Damoh | [5 empty] | 0
12 | II | Panna | [5 empty] | 0
13 | II | Raisen | [5 empty] | 0
14 | II | Sagar | [5 empty] | 0
15 | II | Tikamgarh | [5 empty] | 0
16 | II | Vidisha | [5 empty] | 0
|  | Total | 0 | 0 |  | 0 |  | 0
17 | III | Barwani | [5 empty] | 0
18 | III | Dewas | [5 empty] | 0
19 | III | Dhar | [5 empty] | 0
20 | III | Indore | [5 empty] | 0
21 | III | Jhabua | [5 empty] | 0
22 | III | Khargone | [5 empty] | 0
23 | III | Mandsaur | [5 empty] | 0
24 | III | Ratlam | [5 empty] | 0
25 | III | Shajapur | [5 empty] | 0
26 | III | Ujjain | [5 empty] | 0
|  | Total | 0 | 0 |  | 0 |  | 0
27 | IV | Balaghat | [5 empty] | 0
28 | IV | Chhindwara | [5 empty] | 0
29 | IV | Dindori | [5 empty] | 0
30 | IV | Jabalpur | [5 empty] | 0
31 | IV | Katni | [5 empty] | 0
32 | IV | Mandla | [5 empty] | 0
33 | IV | Narsinghpur | [5 empty] | 0
34 | IV | Rewa | [5 empty] | 0
35 | IV | Satna | [5 empty] | 0
36 | IV | Seoni | [5 empty] | 0
37 | IV | Shahdol | [5 empty] | 0
38 | IV | Sidhi | [5 empty] | 0
|  | Total | 0 | 0 |  | 0 |  | 0
|  | Grand Total | 0 | 0 |  | 0 |  | 0

## CGM PV
Format : CGM P V
Progress for PMGSY - Phase V
Month |  | May06
S.N. | CGM | PIU | Name of packages sanctioned | No. of roads in the package | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Physical progress in Kms / nos | [5 empty] | Expenditure made in the reporting month (Rs. Lakhs) | Total expenditure upto the reporting month | No. of roads on which work not started | Reasons for non start of the work
[9 empty] | E/W | GSB | G-2 | G-3 | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | [5 empty] | 11 | 12 | 13 | 14
[19 empty] | Balaghat | I
[19 empty] | Barwani | II
[19 empty] | Betul | III
[19 empty] | Bhind | IV
Bhopal
Biaora
Chhatarpur
Chhindwara
Damoh
Dewas
Dhar
Dindori
Guna
Gwalior
Hoshangabad
Indore
Jabalpur
Jhabua
Katni
Khargone
Mandla
Mandsaur
Morena
Narsinghpur
Panna
Raisen
Ratlam
Rewa
Sagar
Satna
Seoni
Shahdol
Shajapur
Shivpuri
Sidhi
Tikamgarh
Ujjain
Vidisha

## CGM ADB-I
Format : CGM ADB - I
Progress for PMGSY - ADB - I
Month |  | May06
S.N. | CGM | PIU | Name of packages sanctioned | No. of roads in the package | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Physical progress in Kms / nos | [5 empty] | Expenditure made in the reporting month (Rs. Lakhs) | Total expenditure upto the reporting month | No. of roads on which work not started | Reasons for non start of the work
[9 empty] | E/W | GSB | G-2 | G-3 | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | [5 empty] | 11 | 12 | 13 | 14
[19 empty] | Balaghat | I
[19 empty] | Barwani | II
[19 empty] | Betul | III
[19 empty] | Bhind | IV
Bhopal
Biaora
Chhatarpur
Chhindwara
Damoh
Dewas
Dhar
Dindori
Guna
Gwalior
Hoshangabad
Indore
Jabalpur
Jhabua
Katni
Khargone
Mandla
Mandsaur
Morena
Narsinghpur
Panna
Raisen
Ratlam
Rewa
Sagar
Satna
Seoni
Shahdol
Shajapur
Shivpuri
Sidhi
Tikamgarh
Ujjain
Vidisha

## CGM ADB-II
Format : CGM ADB - II
Progress for PMGSY - ADB - II
Month |  | May06
S.N. | CGM | PIU | Name of packages sanctioned | No. of roads in the package | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Physical progress in Kms / nos | [5 empty] | Expenditure made in the reporting month (Rs. Lakhs) | Total expenditure upto the reporting month | No. of roads on which work not started | Reasons for non start of the work
[9 empty] | E/W | GSB | G-2 | G-3 | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | [5 empty] | 11 | 12 | 13 | 14 | Balaghat | I
[19 empty] | Barwani | II
[19 empty] | Betul | III
[19 empty] | Bhind | IV
Bhopal
Biaora
Chhatarpur
Chhindwara
Damoh
Dewas
Dhar
Dindori
Guna
Gwalior
Hoshangabad
Indore
Jabalpur
Jhabua
Katni
Khargone
Mandla
Mandsaur
Morena
Narsinghpur
Panna
Raisen
Ratlam
Rewa
Sagar
Satna
Seoni
Shahdol
Shajapur
Shivpuri
Sidhi
Tikamgarh
Ujjain
Vidisha

## CGM ADB-III
Format : CGM ADB - III
Progress for PMGSY - ADB - III
Month |  | May06
S.N. | CGM | PIU | Name of packages sanctioned | No. of roads in the package | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Physical progress in Kms / nos | [5 empty] | Expenditure made in the reporting month (Rs. Lakhs) | Total expenditure upto the reporting month | No. of roads on which work not started | Reasons for non start of the work
[9 empty] | E/W | GSB | G-2 | G-3 | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | [5 empty] | 11 | 12 | 13 | 14 | Balaghat | I
[19 empty] | Barwani | II
[19 empty] | Betul | III
[19 empty] | Bhind | IV
Bhopal
Biaora
Chhatarpur
Chhindwara
Damoh
Dewas
Dhar
Dindori
Guna
Gwalior
Hoshangabad
Indore
Jabalpur
Jhabua
Katni
Khargone
Mandla
Mandsaur
Morena
Narsinghpur
Panna
Raisen
Ratlam
Rewa
Sagar
Satna
Seoni
Shahdol
Shajapur
Shivpuri
Sidhi
Tikamgarh
Ujjain
Vidisha

## CGM QC
Format: CGM QC
Quality Control
Month |  | May06
S.N | CGM | PIU | Total No. of roads |  | Ranking of completed roads |  |  |  | Ranking of incomplete roads |  |  |  | Number of roads inspected in the reporting month |  |  |  | No. of ATR pending | Rank of PIU for Quality of works on 1-5 scale (5 Excellent 1 poor)
|  |  | Complete | Under progres | Very good | good | Fair | Poor | Very good | good | Fair | Poor | GM | Consultant | CGM | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | I | Betul | [16 empty] | 1
2 | I | Bhind | [16 empty] | 2
3 | I | Biaora | [16 empty] | 3
4 | I | Guna | [16 empty] | 4
5 | I | Gwalior | [16 empty] | 5
6 | I | Hoshangabad
7 | I | Morena
8 | I | Shivpuri
Total
9 | II | Bhopal
10 | II | Chhatarpur
11 | II | Damoh
12 | II | Panna
13 | II | Raisen
14 | II | Sagar
15 | II | Tikamgarh
16 | II | Vidisha
Total
17 | III | Barwani
18 | III | Dewas
19 | III | Dhar
20 | III | Indore
21 | III | Jhabua
22 | III | Khargone
23 | III | Mandsaur
24 | III | Ratlam
25 | III | Shajapur
26 | III | Ujjain
Total
27 | IV | Balaghat
28 | IV | Chhindwara
29 | IV | Dindori
30 | IV | Jabalpur
31 | IV | Katni
32 | IV | Mandla
33 | IV | Narsinghpur
34 | IV | Rewa
35 | IV | Satna
36 | IV | Seoni
37 | IV | Shahdol
38 | IV | Sidhi
Total
Grand Total

## CGM MC
Format : CGM MC
Monitoring of Consultants' Work
Month |  | May06
S.N | CGM | PIU | Name of consultant | PMGSY / ADB | Performance of consultant in the reporting month |  |  | If unsatisfactory recommendation of CGM
[5 empty] | Good | Satisfactory | Unsatisfactory
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Balaghat | Archtech consultant, Bhopal | I | PMGSY
[9 empty] | Barwani | Artefact Projects, Nagpur | II | ADB
[9 empty] | Betul | Construma Consultancy | III
[9 empty] | Bhind | Consulting Engineers Group Jaipur | IV
[9 empty] | Bhopal | Data Technosys Lucknow
[9 empty] | Biaora | EMA Unihorn IndiaNew Delhi
[9 empty] | Chhatarpur | Gherzi Eastern Ltd., Mumbai
[9 empty] | Chhindwara | Gilcon Project Services Ltd.
[9 empty] | Damoh | High Point Rendel
[9 empty] | Dewas | Innovate Cadd Consultant
[9 empty] | Dhar | Krishna Consultant, Bhopal
[9 empty] | Dindori | Lea Associates, Bhopal
[9 empty] | Guna | Lion Engg Consultant
[9 empty] | Gwalior | Meinhardt Singapur Pvt. Ltd.
[9 empty] | Hoshangabad | MSV Intenational
[9 empty] | Indore | RAPP, Jaipur
[9 empty] | Jabalpur | Sowil Limited
[9 empty] | Jhabua | Technogem Consultant Thane
[9 empty] | Katni | Theme Engineering Services Jaipur
[9 empty] | Khargone | Vax Consultant
Mandla
Mandsaur
Morena
Narsinghpur
Panna
Raisen
Ratlam
Rewa
Sagar
Satna
Seoni
Shahdol
Shajapur
Shivpuri
Sidhi
Tikamgarh
Ujjain
Vidisha

## Sheet2 (hidden)
bb | cc | ss | pp
Biaora | Artefact Projects, Nagpur | Artefact Projects, Nagpur | PMGSY
Biaora | Lea Associates, Bhopal. | Lea Associates, Bhopal | ADB
Hoshangabad | Gilcon Project Services Ltd. | Gilcon Project Services Ltd. | PMGSY
Hoshangabad | Lea Associates, Bhopal. | Lea Associates, Bhopal | ADB
Betul | M/s Gherzi Eastern Ltd., Mumbai | Gherzi Eastern Ltd., Mumbai | PMGSY
Betul | Lea Associates, Delhi | Lea Associates, Bhopal | ADB
Gwalior | EMA Unihorn India (Pvt.Ltd.) New Delhi | EMA Unihorn India (Pvt.Ltd.) New Delhi | PMGSY
Gwalior | LEA South Asia Pvt.Ltd., Bhopal | Lea Associates, Bhopal | ADB
Guna | C.E.G. Jaipur | Consulting Engineers Group Ltd. Jaipur | PMGSY
Guna | Lea, New Delhi | Lea Associates, Bhopal | ADB
Shivpuri | Sowil Limited | Sowil Limited | PMGSY
Shivpuri | Lee Pvt LTD | Lea Associates, Bhopal | ADB
Bhind | M/s Lion Engg Consultant | Lion Engg Consultant | PMGSY
Morena | Lea International (For ADB) | Lea Associates, Bhopal | ADB
Morena | Construma Consultancy (For PMGSY) | Construma Consultancy | PMGSY
15
Bhopal | Theme Engineering Serveces Jaipur | Theme Engineering Services Jaipur
Raisen | M/s Theme Engineering Services Pvt. Ltd | Theme Engineering Services Jaipur
Vidisha | M/s Artefact Projects, Nagpur | Artefact Projects, Nagpur | PMGSY
Sagar | RAPP AG Engineers JV MC Sharma Associates, A-4, Jaipur, Through Sneh Nagar, Sagar (M.P.) | RAPP, Jaipur | PMGSY
Chhatarpur | M.S.V. Intarnation Inc. Gurgaon Hariyana | MSV Intenational | PMGSY
Damoh | Theme Engineering Services, Jaipur, H.Q. Vaishali Nagar, Damoh | Theme Engineering Services Jaipur | PMGSY
Panna | Theme Engineering service pvt.Ltd. Jaipur | Theme Engineering Services Jaipur | PMGSY
Tikamgarh | Archtech Consultant, Pvt. Ltd. Kolkata, with JV, Krishna Consultant Pvt., Ltd. Bhopal | Archtech consultant, Bhopal | PMGSY
Bhopal | M/sLea Associates , Sout Asia Pvt. Ltd. New Delhi | Lea Associates, Bhopal | ADB
Raisen | M/sLea Associates , Sout Asia Pvt. Ltd. New Delhi | Lea Associates, Bhopal | ADB
Vidisha | M/sLea Associates , Sout Asia Pvt. Ltd. New Delhi | Lea Associates, Bhopal | ADB
Sagar | M/sLea Associates , Sout Asia Pvt. Ltd. New Delhi | Lea Associates, Bhopal | ADB
Chhatarpur | Meinhardt Singapur Pvt. Ltd. | Meinhardt Singapur Pvt. Ltd. | ADB
Damoh | Meinhardt Singapur Pvt. Ltd. | Meinhardt Singapur Pvt. Ltd. | ADB
Panna | Meinhardt Singapur Pvt. Ltd. | Meinhardt Singapur Pvt. Ltd. | ADB
Tikamgarh | Meinhardt Singapur Pvt. Ltd. | Meinhardt Singapur Pvt. Ltd. | ADB
Indore | Gherzi eastern limited Bombay | Gherzi Eastern Ltd., Mumbai | PMGSY
Dhar | Gherzji eastern limited Bombay | Gherzi Eastern Ltd., Mumbai | PMGSY
Dhar | High point Rendel | High Point Rendel | ADB
Jhabua | M/s Inovate Cadd Consultant | Innovate Cadd Consultant | PMGSY
Jhabua | M/S High Point Rendal (ADB) | High Point Rendel | ADB
Khargone | M/s Technogem Consultant Pvt. Ltd., Thane | Technogem Consultant Pvt. Ltd., Thane | PMGSY
Khargone | M/s Krishna Consultant, Bhopl | Krishna Consultant, Bhopal | PMGSY
Khargone | M/s High Point Rendel, New Delhi | High Point Rendel | ADB
Barwani | Technogem Consultants Pvt. Ltd. | Technogem Consultant Pvt. Ltd., Thane | PMGSY
Barwani | Highpoint Rendal Pvt. Ltd. Indore | High Point Rendel | ADB
Ujjain | Consuting Engineers Group Ltd. Jaipur | Consulting Engineers Group Ltd. Jaipur
Ujjain | High Point Rendal (I) Pvt Ltd Indore | High Point Rendel | ADB
Ratlam | Consuting Engineers Group Ltd. Jaipur | Consulting Engineers Group Ltd. Jaipur | PMGSY
Ratlam | High Point Rendal (I) Pvt Ltd Indore | High Point Rendel | ADB
Dewas (PMGSY) | Theme Engg. Serv. Jaipur | Theme Engineering Services Jaipur | PMGSY
Dewas (ADB) | High Point Rendal (I) Pvt. Ltd. New Delhi | High Point Rendel | ADB
Shajapur (PMGSY) | Theme Engg. Serv. Jaipur | Theme Engineering Services Jaipur | PMGSY
Shajapur (ADB) | High Point Rendal (I) Pvt. Ltd. New Delhi | High Point Rendel | ADB
Mandsaur | M/s Cunsulting Engineering Groups Ltd. Jaipur | Consulting Engineers Group Ltd. Jaipur | PMGSY
Mandsaur | M/s High point rendal Indore | High Point Rendel | ADB
Balaghat | M/s. Artefact Projects Nagpur | Artefact Projects, Nagpur | PMGSY
Balaghat | M/s Meinhardts (ADB) (Singapore) Pvt. Ltd | Meinhardt Singapur Pvt. Ltd. | ADB
Chhindwara | E.M.A. Unihorn (I) Pvt. Ltd. New Delhi | EMA Unihorn India (Pvt.Ltd.) New Delhi | PMGSY
Chhindwara | M/s Meinhardts (ADB) (Singapore) Pvt. Ltd | Meinhardt Singapur Pvt. Ltd. | ADB
Jabalpur | E.M.A. Unihorn Pvt. Ltd. New Delhi | EMA Unihorn India (Pvt.Ltd.) New Delhi | PMGSY
Jabalpur | M/s Meinhardts (ADB) (Singapore) Pvt. Ltd | Meinhardt Singapur Pvt. Ltd. | ADB
Mandla | M/s Artefact Projects Nagpur | Artefact Projects, Nagpur | PMGSY
Mandla | M/s Meinhardts (ADB) (Singapore) Pvt. Ltd | Meinhardt Singapur Pvt. Ltd. | ADB
Narsinghpur | M/s Lino Enginering Consultant | Lion Engg Consultant | PMGSY
Narsinghpur | M/s Meinhardts (ADB) (Singapore) Pvt. Ltd | Meinhardt Singapur Pvt. Ltd. | ADB
Seoni | M/s Lion Engineering Consultant, Ajmer | Lion Engg Consultant | PMGSY
Seoni | M/s Meinhardts (ADB) (Singapore) Pvt. Ltd | Meinhardt Singapur Pvt. Ltd. | ADB
Katni | E.M.A. Unihorn Pvt. Ltd. New Delhi | EMA Unihorn India (Pvt.Ltd.) New Delhi | PMGSY
Katni | M/s Meinhardts (ADB) (Singapore) Pvt. Ltd | Meinhardt Singapur Pvt. Ltd. | ADB
Dindori | M/s Artefact Projects Nagpur | Artefact Projects, Nagpur | PMGSY
Dindori | M/s Meinhardts (ADB) (Singapore) Pvt. Ltd | Meinhardt Singapur Pvt. Ltd. | ADB
Rewa | Data Technosys (Engineers) Pvt. Ltd. | Data Technosys Lucknow | PMGSY
Rewa | Mein Hardt (Singapor) Pvt. Ltd. | Meinhardt Singapur Pvt. Ltd. | ADB
Satna | M.S.V. International Inc. New Delhi | MSV Intenational | PMGSY
Satna | Mainherdt (Singapur) P. Ltd. | Meinhardt Singapur Pvt. Ltd. | ADB
Sidhi | Data Technosys (Eng.) Pvt.Ltd. Lacknow (U.P.) | Data Technosys Lucknow | PMGSY
Sidhi | Meinhardt (Singapore) Pvt.Ltd. India Brach A-8, Sector-16, Noida : 201301 (U.P.) | Meinhardt Singapur Pvt. Ltd. | ADB
Shahdol | Vax Consultant | Vax Consultant | PMGSY
Shahdol | Meinhardts Consultant | Meinhardt Singapur Pvt. Ltd. | ADB
Archtech consultant, Bhopal
Artefact Projects, Nagpur
Construma Consultancy
Consulting Engineers Group Ltd. Jaipur
Data Technosys Lucknow
EMA Unihorn India (Pvt.Ltd.) New Delhi
Gherzi Eastern Ltd., Mumbai
Gilcon Project Services Ltd.
High Point Rendel
Innovate Cadd Consultant
Krishna Consultant, Bhopal
Lea Associates, Bhopal
Lion Engg Consultant
Meinhardt Singapur Pvt. Ltd.
MSV Intenational
RAPP, Jaipur
Sowil Limited
Technogem Consultant Pvt. Ltd., Thane
Theme Engineering Services Jaipur
Vax Consultant