## cgm wise
Status on 17.Jan.2007
Difference of Progress in OMMS (upto 31 Dec' 2006)
No. | Division | CGM | Districts | No. of Photographs on OMMS | Physical Progress | [5 empty] | Financial (Payment Made) in Lakhs
[5 empty] | Showing completed roads in OMMS | Actual | Diff. | Showing completed length in OMMS | Actual | Diff. | Showing Expenditure in OMMS | Actual | Diff. | Entry Completed on OMMAS (Yes/NO) | Completed Month on OMMS
3 | Bhopal | I | Betul | 74 | 85 | 86 | 1 | 470.75 | 475.153 | 4.403 | 9252.95 | 9393.11 | 140.16 | Yes | 2006-10-01
4 | Gwalior | I | Bhind | 35 | 79 | 80 | 1 | 224.15 | 232.715 | 8.565 | 3764.35 | 5092.73 | 1328.38 | No | 2006-03-01
9 | Gwalior | I | Datia | 28 | 28 | 30 | 2 | 114.88 | 115.515 | 0.635 | 2009.87 | 2553.47 | 543.6 | Yes | 2006-11-01
13 | Gwalior | I | Guna (+Ashoknagar) | 24 | 70 | 79 | 9 | 333.37 | 353.709 | 20.339 | 6396.73 | 7092.69 | 695.96 | No | 2006-05-01
14 | Gwalior | I | Gwalior | 97 | 48 | 49 | 1 | 133.79 | 134.203 | 0.413 | 2420.84 | 2671.29 | 250.45 | Yes | 2006-11-01
15 | Bhopal | I | Harda | 14 | 19 | 20 | 1 | 111.05 | 95.497 | -15.553 | 2548.58 | 2876.26 | 327.68 | Yes | 2006-11-01
16 | Bhopal | I | Hoshangabad | 87 | 75 | 74 | -1 | 231.62 | 259.492 | 27.872 | 6371.62 | 6471.91 | 100.29 | Yes | 2006-11-01
25 | Gwalior | I | Morena | 132 | 103 | 109 | 6 | 400.49 | 411.385 | 10.895 | 7473.71 | 9027.18 | 1553.47 | No | 2006-09-01
30 | Bhopal | I | Rajgarh | 47 | 59 | 60 | 1 | 258.9 | 262.644 | 3.744 | 4372.17 | 4847.6654 | 475.4954 | Yes | 2006-11-01
37 | Gwalior | I | Seopur | Zero | 16 | 16 | 0 | 84.31 | 85.709 | 1.399 | 2030.41 | 2580.79 | 550.38 | Yes | 2006-11-01
40 | Gwalior | I | Shivpuri * | Zero | 80 | 84 | 4 | 447.43 | 477.966 | 30.536 | 7635.33 | 9010.293 | 1374.963 | No | 2006-10-01
[5 empty] | 662 | 687 | 25 | 2810.74 | 2903.988 | 93.248 | 54276.56 | 61617.3884 | 7340.8284
5 | Bhopal | II | Bhopal | 16 | 17 | 26 | 9 | 51.49 | 89.46 | 37.97 | 1631.34 | 1940.35 | 309.01 | No | 2006-03-01
6 | Sagar | II | Chhatarpur | 288 | 62 | 66 | 4 | 261.13 | 260.776 | -0.354 | 5759.79 | 5920.754 | 160.964 | No | 2006-11-01
8 | Sagar | II | Damoh | 127 | 64 | 66 | 2 | 233.14 | 255.278 | 22.138 | 5033 | 5176.998 | 143.998 | Yes | 2006-10-01
28 | Sagar | II | Panna | 241 | 30 | 36 | 6 | 135.51 | 159.935 | 24.425 | 4874.81 | 5141.46 | 266.65 | No | 2006-11-01
29 | Bhopal | II | Raisen | 11 | 34 | 35 | 1 | 232.13 | 232.315 | 0.185 | 5075.97 | 5277.66 | 201.69 | Yes | 2006-11-01
33 | Sagar | II | Sagar | 67 | 72 | 75 | 3 | 340.7 | 348.856 | 8.156 | 7809.2 | 8318.7 | 509.5 | No | 2006-03-01
35 | Bhopal | II | Sehore | 23 | 14 | 29 | 15 | 88.96 | 154.588 | 65.628 | 5162.95 | 5731.969 | 569.019 | No | 2006-03-01
42 | Sagar | II | Tikamgarh | 77 | 39 | 57 | 18 | 153.37 | 204.009 | 50.639 | 3695.73 | 4996 | 1300.27 | No | 2006-03-01
45 | Bhopal | II | Vidisha | 143 | 44 | 44 | 0 | 280.77 | 270.855 | -9.915 | 5349.93 | 6093.94 | 744.01 | Yes | 2006-11-01
[5 empty] | 376 | 434 | 58 | 1777.2 | 1976.072 | 198.872 | 44392.72 | 48597.831 | 4205.111
2 | Indore | III | Barwani | Zero | 48 | 49 | 1 | 294.21 | 274.25 | -19.96 | 5260.6 | 5697.127 | 436.527 | Yes | 2006-03-01
10 | Ujjain | III | Dewas | 31 | 58 | 60 | 2 | 271.12 | 276.932 | 5.812 | 5112.26 | 5120.235 | 7.975 | Yes | 2006-11-01
11 | Indore | III | Dhar | 68 | 86 | 90 | 4 | 474.44 | 484.825 | 10.385 | 9761.52 | 10826.07 | 1064.55 | No | 2006-07-01
17 | Indore | III | Indore | 86 | 30 | 32 | 2 | 98.32 | 112.495 | 14.175 | 2291.58 | 2324.07 | 32.49 | No | 2006-11-01
19 | Indore | III | Jhabua | 52 | 58 | 85 | 27 | 248.29 | 365.014 | 116.724 | 6828.68 | 7661.66 | 832.98 | No | 2006-03-01
21 | Indore | III | Khandwa (+Burhanpur) | 39 | 61 | 64 | 3 | 263.07 | 273.48 | 10.41 | 4557.65 | 5202.53 | 644.88 | No | 2006-11-01
22 | Indore | III | Khargone | 24 | 44 | 53 | 9 | 228.22 | 286.959 | 58.739 | 5637.39 | 6284.7842 | 647.3942 | No | 2006-03-01
24 | Ujjain | III | Mandsaur | 22 | 38 | 47 | 9 | 143.89 | 196.865 | 52.975 | 4131.2 | 4841.34 | 710.14 | No | 2006-03-01
27 | Ujjain | III | Neemuch | Zero | 17 | 26 | 9 | 86.77 | 130.372 | 43.602 | 2232.96 | 2553.13 | 320.17 | No | 2006-03-01
31 | Ujjain | III | Ratlam | 4 | 20 | 36 | 16 | 135.01 | 204.085 | 69.075 | 3790.35 | 3899.75 | 109.4 | No | 2006-03-01
39 | Ujjain | III | Shajapur | 10 | 57 | 60 | 3 | 258.89 | 273.439 | 14.549 | 5529.18 | 5875.79 | 346.61 | No | 2006-07-01
43 | Ujjain | III | Ujjain | 59 | 44 | 50 | 6 | 199.31 | 232.46 | 33.15 | 5123.36 | 5584.93 | 461.57 | No | 2006-05-01
[5 empty] | 561 | 652 | 91 | 2701.54 | 3111.176 | 409.636 | 60256.73 | 65871.4162 | 5614.6862
1 | Jabalpur | IV | Balaghat | 31 | 90 | 101 | 11 | 440.02 | 499.485 | 59.465 | 8320.86 | 8655.87 | 335.01 | No | 2006-09-01
7 | Jabalpur | IV | Chhindwara | 211 | 80 | 81 | 1 | 454.78 | 450.93 | -3.85 | 9140.15 | 9722.71 | 582.56 | Yes | 2006-11-01
12 | Jabalpur | IV | Dindori | 60 | 70 | 71 | 1 | 273.61 | 283.302 | 9.692 | 6040.59 | 6102.58 | 61.99 | Yes | 0ct06
18 | Jabalpur | IV | Jabalpur | 49 | 60 | 63 | 3 | 226.63 | 267.519 | 40.889 | 4842.37 | 5128.67 | 286.3 | No | 2006-11-01
20 | Jabalpur | IV | Katni | 34 | 36 | 33 | -3 | 172.7 | 157.66 | -15.04 | 4376.77 | 4857.27 | 480.5 | NO | 2006-11-01
23 | Jabalpur | IV | Mandla | 66 | 77 | 78 | 1 | 429.72 | 447.55 | 17.83 | 6619.33 | 7143.56 | 524.23 | Yes | 2006-07-01
26 | Jabalpur | IV | Narsinghpur | 34 | 46 | 45 | -1 | 172.98 | 162.705 | -10.275 | 4443.66 | 4457.04 | 13.38 | Yes | 2006-11-01
32 | Rewa | IV | Rewa | 57 | 52 | 52 | 0 | 238.98 | 253.635 | 14.655 | 4898.77 | 5078.89 | 180.12 | Yes | 2006-11-01
34 | Rewa | IV | Satna | 21 | 66 | 67 | 1 | 248.26 | 239.254 | -9.006 | 5803.62 | 6090.9217 | 287.3017 | No | 2006-09-01
36 | Jabalpur | IV | Seoni | 43 | 68 | 91 | 23 | 344.7 | 480.385 | 135.685 | 8754.38 | 10107.58 | 1353.2 | No | 2006-03-01
38 | Rewa | IV | Shahdol (+Anuppur) | 50 | 54 | 62 | 8 | 253.09 | 303.772 | 50.682 | 5960.09 | 6450.076 | 489.986 | No | 2006-05-01
41 | Rewa | IV | Sidhi | 59 | 63 | 66 | 3 | 396.89 | 393.508 | -3.382 | 7989.13 | 9025.19 | 1036.06 | Yes | 2006-11-01
44 | Rewa | IV | Umria | 6 | 19 | 19 | 0 | 131.78 | 130.913 | -0.867 | 2525.71 | 2691.1944 | 165.4844 | Yes | 2006-11-01
[5 empty] | 781 | 829 | 48 | 3784.14 | 4070.618 | 286.478 | 79715.43 | 85511.5521 | 5796.1221
[5 empty] | 2380 | 2602 | 222 | 11073.62 | 12061.854 | 988.234 | 238641.44 | 261598.1877 | 22956.7477