## Sheet1
Complete Packages- final Payment Details
S. No. | Phase | CGM | Name of District | Package No. | Status | Date of Completion | Date of Issue completion Certificate by the consultant | Date of final bill payment | Month of final bill payment
1 | 2 | IV | Balaghat | MP 01 03 | Complete | 15.3.04 | 14-06-2004 | 2004-07-08 | 2004-08-04
2 | 2 | IV | Balaghat | MP 01 04 | Complete | 10.1.04 | 14-06-2004 | 30-10-2004 | 2004-10-04
3 | 2 | IV | Balaghat | MP 01 05 | Complete | 5.12.03 | 25-08-2004 | 28/02/06 | 2006-02-06
4 | 2 | IV | Balaghat | MP 01 06 | Complete | 25.12.03 | 14-06-2004 | 2004-07-08 | 2004-08-04
5 | 2 | IV | Balaghat | MP 01 07 | Complete | 28.2.04 | 14-06-2004 | 2004-07-08 | 2004-08-04
6 | 2 | IV | Balaghat | MP 01 08 | Complete | 8.3.04 | 14-06-2004 | 2005-10-08 | 2005-08-04
7 | 2 | IV | Balaghat | MP 01 08a | Complete | 8.3.04 | 14-06-2004 | 30-07-2004 | 2004-07-04
| 3 | IV | Balaghat | MP 0109 | Complete | 28.2.06 | 28-02-2006 | 22.8.06 | 2006-08-06
| 3 | IV | Balaghat | MP 0110 | Complete | 30.11.05 | 09.02.2006 | 28-02-2006 | 2006-02-06
| 3 | IV | Balaghat | MP 0111 | Complete | 25.11.04 | 2004-10-07 | 30.5.06 | 2006-05-26
4 | 3 | IV | Balaghat | MP 0112 | Complete | 30.11.05 | 17-02-2006 | 31-01-2006 | 2006-01-06
1 | 4 | IV | Balaghat | MP 0113 | Complete | 31.01.2007 | 15.04.2007 | 29.06.2007 | 2007-06-07
| 4 | IV | Balaghat | MP 0114 | Complete | 20.6.06 | 14.11.2006 | 23.11.2006 | 2006-11-23
| 4 | IV | Balaghat | MP 0115 | Complete | 28-03.2006 | 28-03-2006 | 31/8/06 | 2006-08-31
2 | 5 | IV | Balaghat | MP 0118 | Complete | 29.12.2006 | 28.02.2007 | 29.06.07 | 2007-06-07
| 5 | IV | Balaghat | MP 0119 | Complete | 30.04.2007 | 2007-03-06 | 30-07-2007 | 2007-07-07
| 5 | IV | Balaghat | MP 0121 | Complete | 28.02.2007 | 2007-03-06 | 30-07-2007 | 2007-07-07
| 5 | IV | Balaghat | MP 0122 | Complete | 28.02.2007 | 2007-03-06 | 30-07-2007 | 2007-07-07
| 5 | IV | Balaghat | MP 0124 | Complete | 29.2.08 | 26.3.08 | 31.3.08 | 2008-03-08
1 | B-III | IV | Balaghat | MP 0151 | Complete | 30.04.2007 | 2007-01-05 | 17-08-2007 | 2007-08-07
| B-IV | IV | Balaghat | MP 0153 | Complete | 30.01.2008
| B-IV | IV | Balaghat | MP 0155 | Complete | 25.2.08 | 24.3.08 | 31.3.08 | 2008-03-08
1 | 1 | I | Betul-1 | MP0402 | Completed | 12.10.02 | 29.10.02 | 19.07.04 | 2004-07-04
8 | 2 | I | Betul-1 | MP 03 03 | Complete | 15.03.05 | 04.04.05 | 25.08.05 | 2005-08-04
9 | 2 | I | Betul-1 | MP 03 04 | Complete | 28.02.06 | 03.07.06 | 30.11.06 | 2006-11-06
10 | 2 | I | Betul-1 | MP 03 05 | Complete | 15.03.05 | 15.03.05 | 31.10.06 | 2006-10-06
11 | 2 | I | Betul-1 | MP 03 06 | Complete | 31.12.05 | 03.07.06 | 24.04.07 | 2007-04-07
1 | 3 | I | Betul-1 | MP 0307 | Complete | 15.08.05 | 14.08.05 | 30.06.06 | 2006-06-30
1 | 3 | I | Betul-1 | MP 0308 | Complete | 15.08.05 | 15.10.05 | 21.04.06 | 2006-04-21
1 | 3 | I | Betul-1 | MP 0309 | Complete | 15.12.05 | 15.12.05 | 26.05.06 | 2006-05-26
1 | 3 | I | Betul-1 | MP 0310 | Complete | 31.12.05 | 31.12.05 | 25.04.06 | 2006-04-25
1 | 3 | I | Betul-1 | MP 0311 | Complete | 15.12.04 | 05.01.05 | 25.08.05 | 2006-08-25
1 | 4 | I | Betul-1 | MP 0312 | Complete | 31.12.05 | 31.12.05 | 22.05.06 | 2006-05-22
| 4 | I | Betul | MP 0313 | Complete | 31.10.05 | 31.10.05 | 23.05.06 | 2006-05-22
1 | 4 | I | Betul-1 | MP 0314 | Complete | 31.07.06 | 15.09.06 | 28.03.07 | 2007-03-07
2 | 4 | I | Betul-1 | MP 0315 | Complete | 31.10.06 | 15.11.06 | 27.08.07 | 2007-08-07
| 2 | I | Betul | MP 0306 | Complete | 31.12.05 | 03.07.06 | 24.04.07 | 2007-04-07
| 5 | I | Betul-1 | MP 0317 | Complete | 23.09.06 | 23.09.06 | 28.12.06 | 2006-12-06
| 5 | I | Betul-1 | MP 0318 | Complete | 30.09.07 | 31.10.07 | 31.01.08 | 2008-01-08
1 | 5 | I | Betul-1 | MP0319 | Complete | 15.03.07 | 23.03.07 | 29.09.07 | 2007-09-07
| 5 | I | Betul-1 | MP0320 | Complete | 29.09.06 | 29.09.06 | 11.1.07 | 2007-01-07
| 6 | I | Betul-1 | MP0327 | Complete | 25.12.07 | 25.12.07 | 31.03.08 | 2008-03-08
8 | B-III | I | Betul-1 | MP 0359 | Complete | 14.03.07
3 | B-I | I | Betul-1 | MP 0352 | Complete | 28.02.07 | 30.06.07 | 27.08.07 | 2007-08-07
| B-III | I | Betul-1 | MP 0353 | Complete | 30.06.07 | 31.10.07 | 31.01.08 | 2008-01-08
|  |  | Betul-1 | MP 0355 | Complete
| B-III | I | Betul | MP 0356 | Complete | 30-06-07 | 30-08-07 | 31-03-08 | 2008-03-08
| B-III | I | Betul | MP 0357 | Complete | 30-11-07 | 30-11-07
3 | 1 | I | Bhopal | MP0601 | Completed | 28.02.2003 | 01.09.2003 | 07.04.2004 | 2004-04-04
| 2 | I | Bhopal | MP 05/3502 | Completed | 31.03.2006 | 30.05.2006 | 30.08.2006 | 2006-08-31
1 | 2 | I | Sehore | MP 35 03 | Complete | 30.04.2006 | 19.07.2006 | 31.07.2006 | 2006-07-31
2 | 2 | I | Sehore | MP 35 04 | Complete | 25.06.2004 | 24.07.2006 | 30.08.2006 | 2006-08-30
| 3 | I | Bhopal | MP 0504 | Complete | 14.05.2004 | 03.07.2004 | 01.07.2005 | 2005-07-05
4 | 3 | I | Bhopal | MP 0505 | Complete | 31.01.2007 | 28.02.2007 | 31.08.2007 | 2007-08-07
| 4 | I | Bhopal | MP 0506 | Complete | 31.03.2006 | 30.05.2006 | 31.07.2006 | 2006-07-31
11 | 5 | I | Bhopal | MP 0507 | Complete | 31.01.2007 | 28.02.2007 | 30.04.2007 | 2007-04-07
5 | B-I | I | Bhopal | MP 0551 | Complete | 31.03.2007 | 23.7.07 | 31.08.2007 | 2007-08-07
3 | 1 | I | Sehore | MP5101 | Completed | 15.04.2003 | 30.08.2003 | 01.07.2004 | 2004-07-04
4 | B-I | I | Sehore | MP3551 | Completed | 31.03.2007 | 23.07.2007 | 30.07.2007 | 2007-07-07
5 | B-II | I | Sehore | MP3552 | Completed | completed | 28.05.07 | 06.09.07 | 2007-09-07
6 | 3 | I | Sehore | MP 3505 | Complete | 30.08.2006 | 30.08.2006 | 14.02.2007 | 2007-02-07
7 | 3 | I | Sehore | MP 3506 | Complete | 14.05.2004 | 29.06.2004 | 07.06.2005 | 2005-06-07
8 | 4 | I | Sehore | MP 3509 | Complete | Feb. 2007 | 25.07.07 | 31.07.07 | 2007-07-07
| 5 | I | Bhopal | MP 3514 | Complete | 31-11-07 | 21.9.07 | 30-11-07 | 2007-11-07
9 | 5 | I | Sehore | MP 3512 | Complete |  | 30.11.2007 | 27.03.08 | 2008-03-01
10 | 5 | I | Sehore | MP 3514 | Complete | 31.08.2007 | 21.09.2007 | 30.11.2007 | 2007-11-07
11 | 6 | I | Sehore | MP 3516 | Complete | 31.01.08 | 31.01.08 | 28-06-2008 | 2008-06-08
12 |  | I | Sehore | MP 3552 | Complete |  | 28.05.07 | 06.09.07 | 2007-09-01
13 | 1 | I | Raisen | MP4301 | complete | 31.5.2006 | 26.7.2006 | 31.8.2006 | 2006-08-31
14 | 2 | I | Raisen | MP 29 02 | complete | 31.5.2006 | 31.5.2006 | 31.3.2007 | 2007-03-07
15 | 2 | I | Raisen | MP 29 03 | Complete | 20.1.04 | 20.1.04 | 20.7.04 | 2004-07-20
16 | 2 | I | Raisen | MP 29 04 | Complete | 10.6.03 | 10.6.03 | 4.6.04 | 2004-06-04
17 | 2 | I | Raisen | MP 29 05 | Complete | 31.8.2005 | 28.2.2006 | 31.10.2006 | 2006-10-06
18 | 3 | I | Raisen | MP 2906 | Complete | 31.5.2006 | 29.7.2006 | 30.9.06 | 2006-09-06
19 | 3 | I | Raisen | MP 2907 | Complete | 31.5.2006 | 21.7.2006 | 31.8.2006 | 2006-08-31
20 | 3 | I | Raisen | MP 2908 | Complete | 31.10.05 | 27.1.2006 | 30.11.2006 | 2006-11-06
21 | 3 | I | Raisen | MP 2909 | Complete | 14.6.04 | 19.7.04 | 27.6.05 | 2005-06-27
22 | 4 | I | Raisen | MP 2910 | Complete | 28.2.2006 | 28.2.2006 | 31.5.2006 | 2006-05-31
23 | 4 | I | Raisen | MP 2911 | Complete | 15.10.05 | 15.10.2005 | 28.2.2006 | 2006-02-28
24 | 4 | I | Raisen | MP 2912 | Complete | 10.10.2005 | 15.10.2005 | 28.2.2006 | 2006-02-28
25 | 5 | I | Raisen | MP 2916 | Complete | 31.10.2007 | 21.11.2007 | 31.5.2008 | 2008-05-08
26 | B-III | I | Raisen | MP 2951 | Complete | 30.6.07 | 22.8.2007 | 31.8.2007 | 2007-08-07
5 | 1 | II | Chhatarpur | MP0801 | Completed | 2.2.05 | 19-04-2005 | 30-04-2005 | 2005-04-30
16 | 2 | II | Chhatarpur | MP 06 02 | Complete | 31/03/2006 | 27-04-2006 | 18-07-2006 | 2006-07-06
17 | 2 | II | Chhatarpur | MP 06 03 | Complete | 30.1.04 | 11/052004 | 31/05/2004 | 2004-05-31
18 | 2 | II | Chhatarpur | MP 06 04 | Complete | 20/4/2007 | 20/4/2007 | 22/05/2007 | 2007-05-07
| 2 | II | Chhatarpur | MP 06 05 | Complete | 31/03/2005 | 18-07-2005 | 14/10/2005 | 2005-10-14
| 3 | II | Chhatarpur | MP 06 06 | Complete | 30/07/2006 | 31-11-2006 | 28-02-2007 | 2007-02-07
| 3 | II | Chhatarpur | MP 06 07 | Complete | 31/03/2006 | 25-04-2006 | 18-07-2006 | 2006-07-06
19 | 3 | II | Chhatarpur | MP 06 09 | Complete | 15/2/2007 | 15/2/2007 | 31/3/2007 | 2007-03-07
| 4 | II | Chhatarpur | MP 06 10 | Complete | 20/5/2007 | 20/5/2007 | 31/05/2007 | 2007-05-07
3 | 4 | II | Chhatarpur | MP 06 11 | Complete | 1/8/2007 | 10/8/07 | 29-9-2007 | 2007-09-01
3 | 4 | II | Chhatarpur | MP 06 12 | Complete | 30-11-06 | 30-11-06 | 30-03-07 | 2007-03-07
| 4 | II | Chhatarpur | MP 0615 | Complete | 31/03/2006 |  | 18/07/06 | 2006-07-18
| B-I | II | Chhatarpur | MP 0651 | Complete | 30-06-07 | 30-06-07 | 06-11-2007 | 2007-11-07
| B-III | II | Chhatarpur | MP 0653 | Complete | 25-05-2007 | 27-06-2007 | 29-09-2007 | 2007-09-07
19 | 2 | II | Tikamgarh | MP 42 02 | Complete | 31.12.03 | 2004-01-09 | 20.1.04 | 2004-01-20
20 | 2 | II | Tikamgarh | MP 42 03 | Complete | 5.12.03 | 2003-12-12 | 31.12.03 | 2003-12-05
21 | 2 | II | Tikamgarh2 | MP 42 04 | Complete | 2004-06-11 | 2004-06-11 | 2004-08-11 | 2004-11-08
22 | 2 | II | Tikamgarh2 | MP 42 05 | Complete | 2003-07-08 | 2003-07-08 | 29-8-03 | 2003-08-04
| 3 | II | Tikamgarh | MP 4206 | Complete | 2005-09-30 | 2005-09-30 | 2005-10-27 | 2005-10-05
| 3 | II | Tikamgarh | MP 4207 | Complete | 2004-12-31 | 2004-12-31 | 2005-10-29 | 2005-10-05
21 | 3 | II | Tikamgarh2 | MP 4208 | Complete | 30-09-05 | 30-09-05 | 29-10-05 | 2005-11-05
7 | 3 | II | Tikamgarh | MP 4209 | Complete | 2006-03-31 | 2006-12-10 | 31.08.2007 | 2007-08-07
23 | 4 | II | Tikamgarh | MP 4210 | Complete | 30-12-2005 | 30-12-2005 | 30-11-2007 | 2007-11-07
4 | 4 | II | Tikamgarh | MP 4211 | Complete | 2006-10-31 | 2006-10-31 | 21-03-2007 | 2007-03-07
24 | 4 | II | Tikamgarh | MP 4212 | Complete | 2007-01-05 | 2007-01-05 | 31-05-2007 | 2007-05-07
| 5 | II | Tikamgarh | MP 4214 | Complete | 31-7-07
| 6 | II | Tikamgarh | MP 4218 | Complete | 07-07-2008 | 07-07-2008
| 6 | II | Tikamgarh | MP 4222 |  | 07-07-2008 | 07-07-2008
24 | B-III | II | Tikamgarh | MP 4252 | Complete | 24-09-2007 | 24-09-2007 | 30-11-2007 | 2007-11-07
7 | 1 | IV | Chhindwara1 | MP0901 | Completed | 17.6.05 | 29-2-2006 | 30-09-05 | 2006-02-06
| 1 | IV | Chhindwara1 | MP0902 | Completed | 31.12.02 | 31-12-02 | 14-06-04 | 2004-06-14
23 | 2 | IV | Chhindwara | MP 07 03 | Complete | 16.12.03 | 16-12-03 | 25-02-04 | 2004-02-25
24 | 2 | IV | Chhindwara | MP 07 04 | Complete | 21.12.03 | 21-12-03 | 04-09-04 | 2004-09-04
25 | 2 | IV | Chhindwara3 | MP 07 05 | Complete | 31.5.05 | 31-05-05 | 31-10-05 | 2005-10-31
26 | 2 | IV | Chhindwara1 | MP 07 06 | Complete | 16.12.03 | 16-12-03 | 25-02-04 | 2004-02-25
27 | 2 | IV | Chhindwara1 | MP 07 07 | Complete | 31.12.03 | 31-12-03 | 19-07-04 | 2004-07-19
28 | 2 | IV | Chhindwara1 | MP 07 08 | Complete | 20.2.04 | 20-02-04 | 04-09-04 | 2004-09-04
| 3 | IV | Chhindwara1 | MP 0710 | Complete | 17.7.04 | 17-07-04 | 14-02-05 | 2005-02-14
| 3 | IV | Chhindwara1 | MP 0711 | Complete | 17.7.04 | 17-07-04 | 15-02-05 | 2005-02-14
| 3 | IV | Chhindwara3 | MP 0712 | Complete | 16.7.04 | 16-07-04 | 30-03-05 | 2005-03-30
| 3 | IV | Chhindwara3 | MP 0713 | Complete | 28.2.06 | 30.6.06 | 30.11.06 | 2006-11-06
| 3 | IV | Chhindwara1 | MP 0714 | Complete | 31.1.06 | 31-01-06 | 31-03-06 | 2006-03-31
| 3 | IV | Chhindwara1 | MP 0715 | Complete | 15.6.04 | 15-06-04 | 31-03-06 | 2006-03-31
| 4 | IV | Chhindwara1 | MP 0716 | Complete | 31.1.06 | 31-01-06 | 31-03-06 | 2006-03-31
| 4 | IV | Chhindwara3 | MP 0717 | Complete | 31.1.06 | 31.01.2006 | 31-03-06 | 2006-03-31
| 4 | IV | Chhindwara1 | MP 0718 | Complete | 6.6.05 | 10.05.2005 | 31-07-05 | 2005-07-31
| 4 | IV | Chhindwara1 | MP 0719 | Complete | 31.3.06 | 5.03.2006 | 30-6-06 | 2006-06-30
| 4 | IV | Chhindwara1 | MP 0720 | Complete | 31.8.05 | 30.08.2005 | 31-10-05 | 2005-10-31
| 5 | IV | Chhindwara1 | MP 0721 | Complete | 31.12.06 | 10.10.2006 | 28-02-07 | 2007-02-07
| 5 | IV | Chhindwara | MP 0722 | Complete | 07-07-2006 | 07.07.06 | 30-11-06 | 2006-11-06
| B-III | IV | Chhindwara1 | MP 0752 | Complete | 31.1.08 | 31.1.08
| B-III | IV | Chhindwara3 | MP 0753 | Complete | 24.8.07 | 24-08-07 | 29-12-07 | 2007-12-01
| 6 | IV | Chhindwara3 | MP 0729 | Complete | 31.5.07 | 16-06-07 | 04-12-07 | 2007-12-07
| 6 | IV | Chhindwara2 | MP 0730 |  | 28.2.083
| 6 | IV | Chhindwara2 | MP 0724 |  | 28.2.08
| 6 | IV | Chhindwara1 | MP 0725 |  | 31.3.08
| 2 | II | Damoh | MP 08 02 | Complete | 31.05.06 | 22.07.06 | 25.7.07 | 2007-07-07
8 | 2 | II | Damoh | MP 08 03 | Complete | 30.12.03 | 31.12.03 | 28.07.04 | 2007-07-07
| 2 | II | Damoh | MP 08 04 | Complete | 30.03.05 | 12.08.05 | 31.01.06 | 2006-01-31
| 2 | II | Damoh | MP 08 05 | Complete | 31.07.05 | 31.07.05 | 30.12.05 | 2005-12-05
| 2 | II | Damoh | MP 08 06 | Complete | 30.06.05 | 17.07.06 | 30.03.07 | 2007-03-07
| 2 | II | Damoh | MP 08 07 | Complete | 31.12.04 | 02.07.05 | 29.10.05 | 2005-10-29
| 2 | II | Damoh | MP 08 08 | Complete | 29.08.04 | 25.07.05 | 31.08.05 | 2005-08-04
| 3 | II | Damoh | MP 0809 | Complete | 13.05.05 | 14.05.05 | 18.01.06 | 2006-01-18
| 3 | II | Damoh | MP 0810 |  | 31.3.08
| 3 | II | Damoh | MP 0811 | Complete | 31.12.05 | 31.12.05 | 22.06.06 | 2006-06-06
| 4 | II | Damoh | MP 0813(2rd Forest) | Complete | 30.11.06 | 05.02.07 | 26.02.07 | 2007-02-07
| 4 | II | Damoh | MP 0814 | Complete | 20.11.07 | 19.02.08
8 | 5 | II | Damoh | MP 0816 | Complete | 10.04.07 | 10.04.07 | 25.08.07 | 2007-08-07
| B-IV | II | Damoh | MP 0854 | Complete | 31-1-08
| 1 | II | Panna | MP 4001 | Complete | 31.1.07 | 30.3.07 | 30.3.07 | 2007-03-07
| 2 | II | Panna | MP 28 03 | Complete
| 2 | II | Panna | MP 28 04 | Complete | 30.4.06 | 29.4.05 | 3.7.06 | 2006-07-03
| 3 | II | Panna | MP 2805 | Complete | 30.04.07 | 15.10.07 | 30.04.08 | 2008-04-08
1 | 3 | II | Panna | MP 28 07 | Complete | 28.02.07 | 30.09.07 | 31.10.07 | 2007-10-07
| 4 | II | Panna | MP 28 08 | Complete | 31.01.07 | 31.01.07 | 31.07.07 | 2007-07-07
| 4 | II | Panna | MP 28 10 | Complete | 31.01.07 | 15.09.07 | 27.03.08 | 2008-03-08
3 | 4 | II | Panna | MP 28 11 | Complete | 30.06.07 | 18.08.07 | 29.09.07 | 2007-09-07
| 5 | II | Panna | MP 28 12 | Complete | 30.04.07 | 30.08.07 | 29.11.07 | 2007-11-07
| B-II | II | Panna | MP 2852 | Complete | 30.06.07 | 25.08.07 | 31.03.08 | 2008-03-08
9 | 1 | III | Dewas1 | MP1301 | Completed | 30.6.05 | 30.6.05 | 28.11.2005 | 2005-11-28
| 2 | III | Dewas1 | MP 10 02 | Complete | 30.6.05 | 15.6.05 | 13.04.2006 | 2006-06-01
| 2 | III | Dewas1 | MP 10 03 | Complete | 31.5.05 | 30.5.05 | 27.02.2006 | 2006-02-27
| 2 | III | Dewas2 | MP 10 04 | Complete | 31.5.05 | 31.5.05 | 27.02.2006 | 2006-02-27
29 | 3 | III | Dewas1 | MP 1005 | Complete | 30.11.04 | 30.11.04 | 28.11.2005 | 2005-11-28
30 | 3 | III | Dewas1 | MP 1006 | Complete | 30.03.2006 |  | 30.12.2006 | 2006-12-06
31 | 3 | III | Dewas2 | MP 1007 | Complete | 31.3.05 | 31.3.05 | 31.1.07 | 2007-01-01
7 | 4 | III | Dewas1 | MP 1008 | Complete | 30.6.06 |  | 31.8.06 | 2006-08-31
| 4 | III | Dewas2 | MP 1009 | Completed | 30.01.2006 | 30.01.2006 | 28.02.2007 | 2007-02-07
| 5 | III | Dewas1 | MP 1011 | Completed | 15-02-2008 | 03.03.2008 | 23.06.2008 | 2008-06-08
| 1 | III | Shajapur | MP5502 | Completed | 30.11.2003 | 27.12.03 | 03.09.05 | 2005-09-03
| 2 | III | Shajapur | MP 39 03 | Complete | 30.12.2003 | 03.01.04 | 31.12.04 | 2004-12-05
| 2 | III | Shajapur | MP 39 04 | Complete | 30.12.2003 | 03.01.04 | 07.01.05 | 2005-01-07
| 2 | III | Agar | MP 39 05 | Complete | 30.12.2003 | 03.01.04 | 29.12.04 | 2005-12-05
32 | 3 | III | Agar | MP 3906 | Complete | 30.06.2004 | 12.02.05 | 21.02.05 | 2005-02-21
33 | 3 | III | Shajapur | MP 3907 | Complete | 31.01.2005 | 30.06.04 | 29.11.05 | 2005-11-29
34 | 3 | III | Shajapur | MP 3908 | Complete | 31.03.2005 | 31.03.05 | 30.03.07 | 2007-03-07
| 4 | III | Agar | MP 3909 | Complete | 31.10.05 | 31.10.05 | 31.07.07 | 2007-07-07
| 4 | III | Agar | MP 3910 | Complete | 31.12.2005 | 16.04.2007
| 5 | III | Shajapur | MP 3912 | Complete | 31.12.2005 | 16.04.2007 | 13/23-12-07 | 2007-12-07
10 | 1 | III | Kukshi | MP1501 | Completed | 31.12.02 | 24.06.04 | 31.05.04 | 2004-05-31
| 1 | III | Dhar | MP1502 | Completed | 31.03.03 | 24.06.04 | 31.08.05 | 2005-08-04
| 2 | III | Dhar-3 | MP 11 03 | Complete | 30.01.04 | 24.06.04 | 22.07.04 | 2004-07-22
| 2 | III | Kukshi | MP 11 04 | Complete | 26.12.03 | 24.06.04 | 22.07.04 | 2004-07-22
| 2 | III | Dhar | MP 11 05 | Complete | 15.01.04 | 24.06.04 | 22.07.04 | 2004-07-22
| 2 | III | Dhar | MP 11 06 | Complete | 26.03.02 | 24.06.04 | 31.12.05 | 2005-12-05
35 | 3 | III | Dhar | MP 1107 | Complete | 20.04.04 | 24.06.04 | 31.12.05 | 2005-12-05
36 | 3 | III | Kukshi | MP 1108 | Complete | 30.06.04 | 03.07.04 | 30.1.06 | 2006-01-30
37 | 3 | III | Dhar | MP 1109 | Complete | 24.12.05 | 6.09.06 | 17.12.07 | 2007-12-07
38 | 3 | III | Dhar-3 | MP 1110 | Complete | 15.5.05 | 31.3.06 | 11.7.06 | 2006-07-11
39 | 3 | III | Kukshi | MP 1111 | Complete | 15.11.05 | 30.03.06 | 11.07.06 | 2007-07-07
40 | 3 | III | Dhar | MP 1112 | Complete | 31.12.05 | 31.12.05 | 30.8..06 | 2006-08-06
41 | 3 | III | Kukshi | MP 1113 | Complete | 30.06.04 | 03.07.04 | 01.06.05 | 2005-06-01
8 | 4 | III | Dhar | MP 1114 | Complete | 28.02.06 | 15.04.06 | 31.1.07 | 2007-01-07
| 4 | III | Dhar | MP 1115 | Complete | 30.8.05 | 17.10.05 | 30.3.06 | 2006-03-30
| 4 | III | Dhar-3 | MP 1116 | Complete | 15.05.06 | 29.05.06 | 30.08.06 | 2006-08-30
| 4 | III | Kukshi | MP 1117 | Complete | 31.12.06 | 31.12.06 | 30.04.07 | 2007-04-07
| 4 | III | Kukshi | MP 1118 | Complete | 24.03.07 | 24.03.07 | 27.06.07 | 2007-06-07
4 | 4 | III | Kukshi | MP 1119 | Complete | 31.05.07 | 31.05.07 | 29.09.07 | 2007-09-07
| 7 | III | Kukshi | MP 1129 |  | 31.7.08
| 8 | III | Kukshi | MP 1132 |  | 31.7.08
| 9 | III | Kukshi | MP 1136 |  | 31.7.08
2 | B-I | III | Dhar | MP 1152 | Complete | 30.4.07 | 13.07.07 | 31.10.07 | 2007-10-07
| B-III | III | Dhar | MP 1157 |  | 30.5.07
| B-III | III | Dhar -3 | MP 1159 | Complete | 20.05.07 | 13.07.07 | 30.11.07 | 2007-11-07
11 | 1 | II | Ashoknagar | MP1801 | Completed | 30-06-03 | 25-10-03 | 19-04-04 | 2004-04-19
| 1 | II | Guna | MP1802 | Completed | 15-07-03 | 25-10-03 | 19-04-04 | 2004-04-19
| 2 | II | Ashoknagar | MP 13 03 | Complete | 25-04-04 | 27-04-05 | 31-08-05 | 2005-08-04
| 2 | II | Ashoknagar | MP 13 04 | Complete | 07-04-03 | 14-08-03 | 31-12-03 | 2003-12-05
| 2 | II | Guna | MP 13 05 | Complete | 07-04-03 | 14-08-03 | 30-09-03 | 2003-09-30
| 2 | II | Guna | MP 13 06 | Complete | 30-06-03 | 26-08-03 | 30-09-03 | 2003-09-30
42 | 3 | II | Ashoknagar | MP 1307 | Complete | 30-04-05 | 05-05-05 | 30-03.07 | 2007-03-07
43 | 3 | II | Ashoknagar | MP 1308 | Complete | 28-02-05 | 10-03-05 | 21-11-05 | 2005-11-21
44 | 3 | II | Guna | MP 1309 | Complete | 31-05-04 | 10-03-05 | 30-07-05 | 2005-07-30
45 | 3 | II | Guna | MP 1310 | Complete | 20-02-05 | 10-03-05 | 16-08-05 | 2005-08-04
46 | 3 | II | Guna | MP 1311 | Complete | 22-02-05 | 10-03-05 | 31-10-05 | 2005-10-31
9 | 4 | II | Guna | MP1312 | Complete | 31-10-05 | 31.10.05 | 30.11.06 | 2006-11-06
| 4 | II | Guna | MP-1313 | Complete | 31.10.05 | 31.10.05 | 31.08.06 | 2006-08-31
| 4 | II | Ashoknagar | MP-1314 | Complete | 30.11.07 | 30.11.07 | 17.01.08 | 2008-01-08
| 5 | II | Guna | MP-1315 | Complete
| 5 | II | Ashoknagar | MP-1316 | Complete | 2007-03-13 | 2007-03-13 | 2007-04-30 | 2007-04-07
| 6 | II | Ashoknagar | MP-1321 |  | 31.03.08 | 29.05.08 | 30.06.08 | 2008-06-08
| B-IV | II | Ashoknagar | MP-1356 |  | 31.3.08
12 | 1 | II | Gwalior | MP1901 | Completed | 28.02.03 | 24.03.03 | 28.01.04 | 2004-01-28
| 2 | II | Gwalior | MP 14 02 | Complete | 30.06.04 | 08.07.04 | 24.10.05 | 2005-10-24
| 2 | II | Gwalior | MP 14 03 | Complete | 30.11.03 | 01.07.04 | 31.05.05 | 2005-05-31
| 3 | II | Gwalior | MP 1404 | Complete | 25.04.05 | 30.07.05 | 28.02.06 | 2006-02-28
58 | 3 | II | Gwalior | MP 1405 | Complete | 15.12.05 | 22.12.05 | 30.4.06 | 2006-04-30
| 3 | II | Gwalior | MP 1406 | Complete | 31.08.05 | 21.10.05 | 30.11.05 | 2005-11-30
| 4 | II | Gwalior | MP 1407 | Complete | 10.06.07 | 30.11.07
| 4 | II | Gwalior | MP 1408 | Complete | 30.11.07 | 20.12.07 | 13.02.08 | 2008-02-08
| B-II | II | Gwalior | MP 1451 |  | 31.3.08
|  |  |  | 9 | 8 | 9 | 8
| 1 | II | Datia | MP0401 | Completed | 31.10.04 | 22.07.05 | 28.09.05 | 2005-09-28
| 2 | II | Datia | MP 09 02 | Complete | 30.10.04 | 06.02.06 | 31.03.06 | 2006-03-31
| 3 | II | Datia | MP 0903 | Complete | 10.11.04 | 02.03.05 | 31.08.05 | 2005-08-04
5 | 3 | II | Datia | MP 0904 | Complete | 31.01.07 | 21.03.07 | 29.09.07 | 2007-09-07
| 4 | II | Datia | MP 0905 | Complete | 25.03.06 | 14.04.06 | 31.03.06 | 2006-03-31
| B-II | II | Datia | MP 0951 | Complete | 31.03.07 | 31.05.07 | 30.04.08 | 2008-04-08
| B-III | II | Datia | MP 0952 | Complete | 31.03.07 | 31.05.07 | 31.05.08 | 2008-05-08
13 | 2 | I | Hoshangabad | MP 16 02 | Complete | 05.08.2004 | 22.11.2004 | 30.06.2005 | 2005-06-30
| 2 | I | Hoshangabad | MP 16 03 | Complete | 30.06.2004 | 25.09.2004 | 30.11.2005 | 2005-11-30
| 2 | I | Hoshangabad | MP 16 04 | Complete | 15.06.2004 | 26.08.2004 | 21.06.2005 | 2005-06-21
| 2 | I | Hoshangabad | MP 16 05 | Complete | 15.06.2004 | 28.08.2004 | 21.06.2005 | 2005-06-21
6 | 3 | I | Hoshangabad | MP 1606 | Complete | 26.02.2007 | 26.02.2007 | 30.03.2007 | 2007-03-07
| 3 | I | Hoshangabad | MP 1607 | Complete | 30.04.2005 | 18.07.2005 | 19.07.2005 | 2005-07-19
| 3 | I | Hoshangabad | MP 1608 | Complete | 31.10.2005 | 31.12.2005 | 31.01.2006 | 2006-01-31
| 3 | I | Hoshangabad | MP 1609 | Complete | 30.04.2005 | 18.07.2005 | 19.07.2005 | 2005-07-19
| 4 | I | Hoshangabad | MP 1610 | Complete | 30.06.2006 | 30.09.2006 | 30.11.2006 | 2006-11-06
| 4 | I | Hoshangabad | MP 1611 | Complete | 03.08.2007 | 03.08.2007 | 30.10.2007 | 2007-10-01
| 4 | I | Hoshangabad | MP 1612 | Complete | 31.07.2006 | 30.07.2006 | 31.10.2006 | 2006-10-05
| 4 | I | Hoshangabad | MP 1614 | Complete | 31.07.2006 | 30.07.2006 | 31.10.2006 | 2006-10-06
| 4 | I | Hoshangabad | MP 1616 | Complete | 30-8-07 | 30-8-07 | 31-1-08 | 2008-01-08
| 5 | I | Hoshangabad | MP 1617 | Complete | 30.03.2007 | 30.09.2007 | 31.12.2007 | 2007-12-07
| 1 | I | Harda | MP 2001 | Completed | 15.04.2003 | 15.04.2003 | 08.09.2003 | 2003-09-08
| 2 | I | Harda | MP 15 02 | Complete | 31.12.2004 | 20.01.2005 | 30.06.2005 | 2005-06-30
| 3 | I | Harda | MP 1503 | Complete | 31.03.2005 | 15.07.2005 | 19.07.2005 | 2005-07-19
| 4 | I | Harda | MP 1505 | Complete | 31-05-2007
| 5 | I | Harda | MP 1506 | Complete | 28.02.2007 | 17-02-07 | 31-12.07 | 2007-12-07
14 | 1 | III | Indore | MP2201 | Completed | 31.12.03 | 31.7.03 | 22-07-05 | 2005-07-22
| 2 | III | Indore | MP 17 02 | Complete | 18.5.03 | 8.12.03 | 22-07-05 | 2005-07-22
| 2 | III | Indore | MP 17 03 | Complete | 30.5.04 | 20.12.04 | 05-07-05. | 2005-07-05
| 3 | III | Indore | MP 17 04 | Complete | 20.6.05 | 31.7.05 | 22-07-05 | 2005-07-22
| 3 | III | Indore | MP 17 06 | Complete | 30.4.05 | 15.7.05 | 22-07-05 | 2005-07-22
| 4 | III | Indore | MP 17 07 | Complete | 15.03.07 | 21.03.07 | 30.03.07 | 2007-03-07
| 4 | III | Indore | MP 17 08 | Complete | 09.04.06 | 24.10.06 | 24.10.06 | 2006-10-06
| 1 | III | Khandwa | MP3001 | Completed | 15.11.02 | 14.8.03 | 26-05-04 | 2004-05-26
| 2 | III | Khandwa | MP 21 02 | Complete | 15.11.03 | 11.12.03 | 14-07-05 | 2005-07-14
| 2 | III | Khandwa | MP 21 03 | Complete | 25.1.04 | 11.12.03/26.1.04 | 14-07-05 | 2005-07-14
| 3 | III | Khandwa | MP 21 04 | Complete | 15.2.06 | 2006-05-06 | 28.2.07 | 2007-02-07
| 3 | III | Khandwa | MP 21 05 | Complete | 15/12/05 | C.C.issued from indore PIU | 31-03-06 | 2006-03-31
| 3 | III | Khandwa | MP 21 06 | Complete | 15/07/04 | C.C.issued from indore PIU | 22-07-05 | 2005-07-22
3 | 4 | III | Khandwa | MP 21 07 | Complete | 28/02/07 | 28-10-07 | 31/10/07 | 2007-10-07
| 4 | III | Khandwa | MP 21 08 | Complete | 31/01/07 | 24-04-07 | 30/04/07 | 2007-04-07
| 6 | III | Khandwa | MP 21 13 |  | 25/11/07 | 25/11/07 | 27/05/08 | 2008-05-08
| 6 | III | Khandwa | MP 21 17 |  | 31.3.08
15 | 1 | IV | Jabalpur | MP2301 | Completed | 29.2.04 | 29.2.04 | 16.7.04 | 2004-07-16
| 1 | IV | Jabalpur | MP2302 | Completed | 30.11.03 | 30.11.03 | 16.7.04 | 2004-07-16
| 2 | IV | Jabalpur | MP 18 03 | Complete | 16.6.05 | 16.6.05 | 23.07.05 | 2005-07-23
| 2 | IV | Jabalpur | MP 18 04 |  | 31.3.08
| 2 | IV | Jabalpur | MP 18 05 | Complete | 31.1.04 | 31.1.04 | 16.7.04 | 2004-07-16
| 2 | IV | Jabalpur | MP 18 06 | Complete | 15.6.03 | 15.6.03 | 16.7.04 | 2004-07-16
6 | 3 | IV | Jabalpur | MP 18 07 | Complete | 10.5.07 | 10.5.07 | 29.9.07 | 2007-09-07
| 3 | IV | Jabalpur | MP 18 08 | Complete | 28.6.04 | 28.6.04 | 31.12.05 | 2006-05-01
| 3 | IV | Jabalpur | MP 18 09 | Complete | 30.1.05 | 30.1.05 | 31.12.05 | 2006-01-01
| 3 | IV | Jabalpur | MP 18 10 | Complete | 30.6.06 | 30.6.06 | 29.12.06 | 2006-12-06
| 3 | IV | Jabalpur | MP 18 11 | Complete | 30.9.06 | 30.9.06 | 31.1.07 | 2007-01-01
| 3 | IV | Jabalpur | MP 18 12 | Complete | 15.10.05 | 15.10.05 | 30.06.06 | 2006-06-30
| 4 | IV | Jabalpur | MP 18 13 | Complete | 29.9.06 | 7.2.07 | 24.5.07 | 2007-05-01
| 4 | IV | Jabalpur | MP 18 14 | Complete | 25.12.05 | 25.12.05 | 30.6.06 | 2006-06-06
| 4 | IV | Jabalpur | MP 18 15 | Complete | 30.9.06 | 30.9.06 | 31.8.07 | 2007-08-07
| 4 | IV | Jabalpur | MP 18 16 | Complete | 31.3.06 | 31.3.06 | 28.2.07 | 2007-02-07
| 5 | IV | Jabalpur | MP 18 17 |  | 31.3.08
| 5 | IV | Jabalpur | MP 18 18 | Complete | 12/2006 | 20.12.06 | 27.7.07 | 2007-07-07
| 5 | IV | Jabalpur | MP Spl | Complete | 7.3.05 | 7.3.2005 | 29.7.05 | 2005-07-29
| 2 | IV | Katni | MP 20 02 | Complete | Dec 06 | 31-12-05 | 30-9-06 | 2006-09-30
| 2 | IV | Katni | MP 20 02a | Complete | 2007-06-01 | 2007-07-04 | 2008-01-31 | 2008-01-08
| 2 | IV | Katni | MP 20 02b | Complete | Dec 05 | 26-12-05 | 30-11-06 | 2006-11-30
| 2 | IV | Katni | MP 2003B | Complete | 2006-08-02 | 2006-09-30 | 2006-09-30 | 2006-09-30
| 2 | IV | Katni | MP 2003 C | Complete | 2006-08-02 | 2006-09-30 | 2006-09-30 | 2006-09-06
16 | 3 | IV | Katni | MP 2004 | Complete | 2005-03-31 | 2005-03-31 | 2005-07-23 | 2005-07-23
| 3 | IV | Katni | MP 2005 | Complete | 2006-04-30 | 2006-08-02 | 2006-08-31 | 2006-08-31
9 | 3 | IV | Katni | MP 2006 | Complete | 2007-03-31 | 2007-04-12 | 2007-08-31 | 2007-08-07
| 3 | IV | Katni | MP 2007 | Complete | 2004-05-08 | 2005-03-31 | 2006-01-13 | 2006-01-06
| 4 | IV | Katni | MP 2008 | Complete | 2006-07-31 | 2006-07-31 | 2006-09-23 | 2006-09-23
| 4 | IV | Katni | MP 2009 | Complete | 2006-03-31 | 2006-07-19 | 2006-08-31 | 2006-08-31
| 4 | IV | Katni | MP 2010 | Complete | 2007-03-31 | 12-04-207 | 2007-05-31 | 2007-05-07
| 5 | IV | Katni | MP 2011 | Complete | 2007-05-31 | 2007-07-04 | 2007-12-30 | 2007-12-07
7 | 5 | IV | Katni | MP 2012 | Complete | 2007-06-01 | 2007-06-25 | 2007-09-30 | 2007-09-07
| 5 | IV | Katni | MP 2013 | Complete | 31-3-2008
| B-IV | IV | Katni | MP 2052 | Complete | 2008-02-02 | 2008-02-03 | 2008-04-30 | 2008-04-08
| B-IV | IV | Katni | MP 2053 | Complete | 2008-01-21 | 2008-01-22
17 | 1 | III | Jhabua | MP2601 | Completed | 31.3.03 | 15.7.03 | 30/11/04 | 2004-11-30
| 1 | III | Jhabua | MP2602 | Completed | 15.4.03 | 15.7.03 | 01/12/04 | 2004-12-05
| 2 | III | Jhabua | MP 19 03 | Complete | 31.1.04 | 12.2.04 | 30/11/04 | 2004-11-30
| 2 | III | Jhabua | MP 19 04 | Complete | 30.4.04 | 30.4.04 | 30/05/05 | 2005-05-30
| 2 | III | Jhabua | MP 19 05 | Complete | 31.3.04 | 31.3.04 | 30/05/05 | 2005-05-30
| 3 | III | Jhabua | MP 19 06 | Complete | 30/11/05 | 15/06/06 | 31/1/07 | 2007-01-07
8 | 3 | III | Jhabua | MP 19 07 | Complete | 15/06/06 | 2006-07-09 | 31-9-06 | 2007-09-06
82 | 3 | III | Jhabua | MP 19 08 | Complete | 15/06/06 |  | 31/07/2006 | 2006-07-06
| 3 | III | Jhabua | MP 19 09 | Complete | 1.6.05 | 28.2.05 | Vr. No 26 /31/12/05 | 2005-12-05
| 4 | III | Jhabua | MP 19 13 | Complete | 31/12/06
18 | 1 | III | Khargone | MP3101 | Completed | 31/12/2002 | 2003-09-11 | 31/07/2003 | 2003-07-31
| 1 | III | Khargone | MP3102 | Completed | 28/02/2003 | 2003-09-11 | 31/07/2003 | 2003-07-31
| 2 | III | MAheshwar | MP 22 03 | Complete | 26/04/2003 | 2003-09-11
| 2 | III | Khargone | MP 22 04 | Complete | 30/07/2003 | 2003-09-11 | 2004-02-01 | 2004-01-21
| 2 | III | Khargone | MP 22 05 | Complete | 24/09/2003 |  | 31/05/2004 | 2004-05-31
| 2 | III | Khargone | MP 2206 | Complete
| 3 | III | Khargone | MP 2207 | Complete | 2004-05-05 | 2004-05-05
| 3 | III | Khargone | MP 2208 | Complete | 24/11/2005 | 24/11/2005 | 28/04/08 | 2008-04-08
| 4 | III | Khargone | MP 2209 | Complete | 30-07-06 | 30-07-06 | 2006-10-10 | 2006-10-10
| 4 | III | Khargone | MP-22-10 | Complete | 2006-07-01 | 2006-07-01 | 28/02/2006 | 2006-02-28
| 4 | III | Khargone | MP-22-11 | Complete | 30/06/2005 | 2005-04-08 | 29/10/2005 | 2005-10-02
| 4 | III | Khargone | MP-22-12 | Complete
| 5 | III | Maheshwar | MP-22-16 | Complete | 16/01/07 | 16/01/07 | 30/04/07 | 2007-04-07
| 5 | III | MAheshwar | MP 2218 | Complete | 29.4.07 | 29.4.07
7 | 5 | III | Maheshwar | MP 2219 | Complete | 23/01/07 | 23/01/07 | 24/03/07 | 2007-03-07
| B-III | III | Khargone | MP 2252 | Complete | 30.11.07 | 30.11.07
19 | 1 | III | Sendhwa | MP0101 | Completed | 2003-05-31 | 28-02-03 | 31-03-06 | 2006-03-31
| 2 | III | Barwani | MP 02 02 | Complete | 2003-06-29 | 2003-06-29 | 31.12.2005 | 2005-12-05
| 2 | III | Barwani | MP 02 03 | Complete | 2003-10-27 | 2003-10-27 | 31.10.03 | 2003-10-31
| 2 | III | Sendhwa | MP 02 04 | Complete | 2004-06-20 | 2004-06-20 | 20.6.04 | 2004-06-20
| 3 | III | Sendhwa | MP 0205 | Complete | 28/02/06 | 28/02/07 | 30/06/07 | 2007-06-07
| 3 | III | Barwani | MP 0206 | Complete | 2007-02-28 | 2007-02-28
8 | 3 | III | Barwani | MP 0207 | Complete | 2006-04-30 | 2006-04-30 | 2007-03-31 | 2007-03-07
| 4 | III | Sendhwa | MP-0208 | Complete | 20.2.06 |  | 29.5.06 | 2006-05-29
| 4 | III | Barwani | MP 0210 | Complete | 2007-01-31 | 2007-01-31 | 2007-07-31 | 2007-07-07
10 | 5 | III | Barwani | MP 0211 | Complete | 30.4.07 | 30.4.07 | 29.8.07 | 2007-08-07
| B-II | III | Sendhwa | MP 0251 | Complete | 31-01-07 | 31.12.07
| B-II | III | Sendhwa | MP 0252 | Complete | 2007-08-03 | 31.1.08
| B-III | III | Barwani | MP 0253 | Complete | 31-12-07 | 31-12-07
| B-III | III | Sendhwa | MP 0255 | Complete | 2007-10-06
20 | 1 | IV | Mandla | MP3501 | Completed | 2003-05-03 | 30/08/2003 | 30/08/2003 Vr.No. 15 | 2003-08-04
| 1 | IV | Mandla | MP3502 | Completed | 2003-05-03 | 30/08/2003 | 30/08/2003 Vr.No. 15 | 2003-08-04
| 1 | IV | Mandla | MP3504 | Completed | 30/5/2003 | 30/08/2003 | 30/08/2003 Vr.No. 16 | 2003-08-04
| 2 | IV | Mandla | MP 23 03 | Complete | 31/12/2004 | 2005-05-05 | 30-11-2005 | 2005-11-30
| 2 | IV | Mandla | MP 23 05 | Complete | 30/6/2005 | 23/07/2005 | 30-11-2005 | 2005-11-30
| 2 | IV | Mandla | MP 23 06 | Complete | 31/05/2003 | 18/09/2003 | 24/3/2005 Vr.No. 21 | 2005-03-24
| 3 | IV | Mandla | MP 23 07 | Complete | 31-12-2004 | 17/02/2005 | 15/4/2005 Vr. No. 1 | 2005-04-15
| 3 | IV | Mandla | MP 23 08 | Complete | 20/02/2005 | 23/03/2005 | 12/8/2005 Vr.No. 2 | 2005-08-04
| 3 | IV | Mandla | MP 23 09 | Complete | 30/06/2004 | 27/07/2004 | 31/7/2004 Vr.No. 7 | 2004-07-31
| 3 | IV | Mandla | MP 23 10 | Complete | 30/06/2005 | 2005-07-07 | 22/12/2005 Vr.No. 3 | 2005-12-22
| 4 | IV | Mandla | MP 23 11 | Complete | 28.2.06 | 26.5.06 | 30.6.06 | 2006-06-30
| 4 | IV | Mandla | MP 23 12 | Complete | 31/7/2006 | 31/7/2006 | 31/1/2007 VR No 8 | 2007-01-07
| 4 | IV | Mandla | MP 23 13 | Complete | 31/7/2006 | 31/7/2006 | 29-12-06 Vr.No.15 | 2006-12-06
| 5 | IV | Mandla | MP 23 14 | Complete | 31/1/2007 | 2007-02-22 | 31/7/2007 VR No 13 | 2007-07-07
| 5 | IV | Mandla | MP 3715 | Complete | 30.6.06 | 20.7.2006 | 28.7.2006 Vr.No. 06 | 2006-07-28
| 5 | IV | Mandla | MP 3716 | Complete | 22/02/2007 | 30.08.2007 Vr.No. 10 | 15/07/07 | 2007-08-07
| 5 | IV | Mandla | MP 23 17 | Complete | 28/2/2006 | 22/3/2006 | 25/3/2006 Vr.No. 16 | 2006-03-25
| 6 | IV | Mandla | MP 23 19 | Complete | 30/10/2007 | 2007-02-11 | 31-03-08 Vr. No. 25 | 2008-03-08
| 6 | IV | Mandla | MP 23 21 |  | 31.3.08
| 6 | IV | Mandla | MP 23 24 | Complete | 31.01.2008 | 2008-04-02 | 11-3-08 Vr.No. 7 | 2008-03-08
| 6 | IV | Mandla | MP 23 25 | Complete | 30/11/2007 | 17.12.07 | 31.01.08 Vr.No.19 | 2008-01-08
| 6 | IV | Mandla | MP 23 26 | Complete | 29.02.2008 | 2008-08-03
| 7 | IV | Mandla | MP 2330 | Complete | 29.02.2008 | 2008-05-03 | 31-5-08 Vr.No. 08 | 2008-05-08
4 | B-III | IV | Mandla | MP 2351 | Complete | 30/11/2006 | 2007-08-10 | 11-10-07 Vr.No.2 | 2007-10-07
| B-III | IV | Mandla | MP 2352 |  | 31.3.08
| B-III | IV | Mandla | MP 2354 | Complete | 2007-06-09 | 2007-08-10 | 31/1/2008 VR No 12 | 2008-01-08
9 | B-III | IV | Mandla | MP 2355 | Complete | 28-2-2007 | 2007-06-09 | 29/9/07 Vr. No. 13 | 2007-09-07
21 | 1 | IV | Dindori | MP1601 | Completed | 30-11-2003 | 30-07-2004 | 29-03-2005 Vr.No. 26 | 2005-03-29
| 2 | IV | Dindori | MP 1203 | Complete | 30-06-2004 | 31-07-2004 | 10/5/2005 Vr.No. 3 | 2005-05-10
11 | 3 | IV | Dindori | MP 12 04 | Complete | 31-01-2007 | 39418 | 30-08-2007 Vr.No. 7 | 2007-08-07
| 3 | IV | Dindori | MP 12 05 | Complete | 30-06-2006 | 1.7.2006 | 15/12/06 Vr.No. 2 | 2006-12-06
| 3 | IV | Dindori | MP 12 06 | Complete | 30-05-2005 | 22-06-2005 | 11/7/2005 Vr.No. 7 | 2005-07-11
| 4 | IV | Dindori | MP 1207 | Complete | 31-10-2006 | 8.1.2007 | 20/2/07 Vr. No. 3 | 2007-02-07
| 4 | IV | Dindori | MP 1208 | Complete | 30-06-2006 | 1.7.2006 | 13/10/06 Vr. No. 14 | 2006-10-06
| 4 | IV | Dindori | MP 1209 | Complete | 30-06-2006 | 1.7.2006 | 15/12/06 Vr. No. 3 | 2006-12-06
10 | 5 | IV | Dindori | MP 1210 | Complete | 31-03-2007 | 12-04-2007 | 27-09-07 Vr.No.2 | 2007-09-07
12 | 5 | IV | Dindori | MP 1211 | Complete | 31-12-2006 | 15-01-2007 | 27-08-07 Vr.No. 6 | 2007-08-07
| 5 | IV | Dindori | MP 1212 | Complete | 28-02-2007 | 15-3-2007 | 03-11-07 Vr.No.1 | 2007-11-07
11 | 5 | IV | Dindori | MP 1213 | Complete | 30-04-2007 | 18-05-07 | 27-09-07 Vr.No.3 | 2007-09-07
| B-III | IV | Dindori | MP 1251 | Complete | 30-11-07 | 17.12.07 | 31.01.08 Vr.No.17 | 2008-01-08
| B-III | IV | Dindori | MP 1252 | Complete | 31.08.07 | 3.11.07 | 31.12.07 Vr.No.9 | 2007-12-01
| B-III | IV | Dindori | MP 1254 | Complete | 31-07-07 | 3.11.07 | 31-01-08 Vr.No.16 | 2008-01-08
| 6 | IV | Dindori | MP 1218 | Complete | 2007-05-11 | 4.01.08 | 23-02-08 Vr.No.6 | 2008-02-08
22 | 1 | III | Mandsaur | MP3601 | Completed | 15.3.03 | 15.03.03 | 10.7.03 | 2003-07-10
| 2 | III | Mandsaur | MP 24 02 | Complete | 30.3.03 | 30.03.03 | 24-03-04 | 2004-03-24
97 | 3 | III | Mandsaur | MP 24 03 | Complete | 31.12.06 | 31.12.06 | 31.03.07 | 2007-03-07
| 3 | III | Mandsaur | MP 24 04 | Complete | 30.8.04 | 30.08.04 | 30.08.04 | 2004-08-04
| 4 | III | Mandsaur | MP 24 07 | Complete | 31.03.07 | 30.09.07 | 16-05-2008 | 2008-05-08
| 5 | III | Mandsaur | MP 24 08 |  | 31.3.08
| B-II | III | Mandsaur | MP 24 51 | Complete | 31.03.07 | 31.3.07
| B-II | III | Mandsaur | MP 24 52 |  | 29.02.08
| 1 | III | Neemuch | MP3901 | Completed | 28.2.03 | 28.02.03 | 2003-10-07 | 2003-07-10
| 2 | III | Neemuch | MP 27 02 | Complete | 30.11.03 | 30-11.03. | 30-11.03. | 2003-11-30
99 | 3 | III | Neemuch | MP 27 03 | Complete | 31.12.06 | 02.01.2007 | 31.05.07 | 2007-05-07
| 3 | III | Neemuch | MP 27 04 | Complete | 15.2.05 | 15.2.05 | 15.2.05 | 2005-02-15
| 5 | III | Neemuch | MP 27 06 | Complete | 15.03.07 | 31.08.2007 | 31.08.07 | 2007-08-07
| 5 | III | Neemuch | MP 27 07 | Complete | 28.02.2007 | 25.10.2007 | 30.11.07 | 2007-11-07
23 | 1 | II | Morena | MP3701 | Completed | 15.01.2003 | 08.04.2003 | 01.04.2004 | 2004-04-01
| 2 | II | Morena | MP 25 02 | Complete | 31.03.2004 | 02.11.2004 | 02.11.2004 | 2004-11-02
| 2 | II | Morena | MP 25 03 | Complete | 30.06.2004 | 02.11.2004 | 11.07.2005 | 2005-07-11
| 3 | II | Morena | MP 2504 | Complete | 31.10.05 | 2.12.05 | 31.10.05 | 2005-10-31
| 3 | II | Morena | MP 2505 | Complete | 28.02.06 | 28.02.06 | 28.02.06 | 2006-02-28
103 | 3 | II | Morena | MP 2506 | Complete | 30.12.05 | 06.01.06 | 05.01.06 | 2006-01-05
104 | 3 | II | Morena | MP 2507 | Complete | 31.03.06 | 10.05.06 | 31.03.06 | 2006-03-31
| 4 | II | Morena | MP 2508 | Complete | 15.12.05 | 31.12.05 | 03.01.06 | 2006-01-03
| 4 | II | Morena | MP 2509 | Complete | 31.03.06 | 10.05.06 | 30.04.06 | 2006-04-06
| 4 | II | Morena | MP 2510 | Complete | 06-06-05 | 06.06.05 | 11.12.06 | 2006-12-06
| 4 | II | Morena | MP 2511 | Complete | 31.03.06 | 17.06.06 | 30.04.06 | 2006-04-06
| 5 | II | Morena | MP 2512 | Complete | 28.02.07 | 28.02.07 | 30.03.07 | 2007-03-07
| 5 | II | Morena | MP 2513 | Complete | 15.03.07 | 15.03.07 | 07.06.07 | 2007-06-07
| 5 | II | Morena | MP 2514 | Complete | 15.03.07 | 15.03.07 | 31.05.07 | 2007-05-07
| 6 | II | Morena | MP 2515 | Complete | 15.02.08 | 15.02.08 | 07.03.08 | 2008-03-08
| 6 | II | Morena | MP 2516 | Complete | 31.12.07 | 31.12.07 | 25.02.08 | 2008-02-08
| 6 | II | Morena | MP 2517 | Complete | 31.12.07 | 31.12.07 | 29.03.08 | 2008-03-08
| 6 | II | Morena | MP 2518 |  | 31.03.08 | 31.03.08 | 16.05.08 | 2008-05-08
12 | 6 | II | Morena | MP 2520 | Complete | 31.08.07 | 25.09.07 | 25.09.07 | 2007-09-07
| B-I | II | Morena | MP 2551 | Complete | 31.10.06 | 31.10.06 | 24.11.06 | 2006-11-06
| B-I | II | Morena | MP 2552 | Complete | 31.10.06 | 31.10.06 | 22.11.06 | 2006-11-06
9 | B-III | II | Morena | MP 2553 | Complete | 28.02.07 | 28.02.07 | 30.03.07 | 2007-03-07
| B-III | II | Morena | MP 2554 | Complete | 30.06.07 | 30.06.07 | 30.06.07 | 2007-06-07
10 | B-III | II | Morena | MP 2555 | Complete | 31.01.07 | 31.01.07 | 30.03.07 | 2007-03-07
11 | B-III | II | Morena | MP 2556 | Complete | 28.02.07 | 28.02.07 | 30.03.07 | 2007-03-07
| B-IV | II | Morena | MP 2557 |  | 31.03.08 | 31.03.08 | 31.05.08 | 2008-05-08
24 | 1 | II | Bhind | MP0501 | Completed | 30.06.03 |  | 30.07.03 | 2003-07-03
| 2 | II | Bhind | MP 04 02 | Complete | 20.12.04. |  | 24.08.05 | 2005-08-05
| 2 | II | Bhind | MP 04 03 | Complete | 31.01.04 | 09,12,04 by GM | 28.07.05 | 2005-07-05
| 2 | II | Bhind | MP 04 04 | Complete | 31.01.04 |  | 31.07.05 | 2005-07-05
| 3 | II | Bhind | MP 0405 | Complete | 14.06.04 | 14,06,04 | 27.10.04 | 2004-10-04
13 | 3 | II | Bhind | MP 0406 | Complete | 31.03.04 | 31,07,05 by GM | 14.09.05 | 2007-09-05
107 | 3 | II | Bhind | MP 0408 | Complete | 31.12.05 |  | 13.03.06 | 2005-03-06
| 4 | II | Bhind | MP 0409 | Complete | 30.07.05 |  | 14.09.05 | 2005-09-05
| 4 | II | Bhind | MP 0410 | Complete | 09.05.05 |  | 28.09.06 | 2006-09-06
| 4 | II | Bhind | MP 0411 | Complete | 30.12.05 | 17.10.06 | 03.05.06 | 2006-05-06
| 4 | II | Bhind | MP 0412 | Complete | 03.06.05 | 11,08,05 | 12.08.05 | 2005-08-04
| 5 | II | Bhind | MP 0413 |  | 31.03.08 |  | 19.06.08 | 2008-06-08
| B-IV | II | Bhind | MP 0453 |  | 31.3.08
27 | 1 | I | Rajgarh | MP4401 | Completed | 5.2.05 | 2005-02-05 | 2005-07-14 | 2005-07-14
28 | 2 | I | Rajgarh | MP 30 02 | Complete | 25.2.04 | 2004-02-25 | 2004-09-22 | 2004-09-22
29 | 2 | I | Rajgarh | MP 30 03 | Complete | 25.2.04 | 2004-02-25 | 2004-09-28 | 2004-09-28
30 | 2 | I | Rajgarh | MP 30 04 | Complete | 25.2.04 | 2004-02-25 | 2005-07-16 | 2005-07-16
31 | 3 | I | Rajgarh | MP 3005 | Complete | 12.1.05 | 2005-01-12 | 2005-07-15 | 2005-07-15
32 | 3 | I | Rajgarh | MP 3006 | Complete | 12.1.05 | 2005-01-12 | 2005-07-16 | 2005-07-16
33 | 3 | I | Rajgarh | MP 3007 | Complete | 12.1.05 | 2005-01-12 | 2005-07-16 | 2005-07-16
34 | 4 | I | Rajgarh | MP 3008 | Complete | 2006-05-31 | 2006-06-25 | 2007-01-31 | 2007-01-01
35 | 4 | I | Rajgarh | MP 3009 | Complete | 17.9.05 | 2005-09-17 | 2005-12-30 | 2005-12-05
36 | 5 | I | Rajgarh | MP 3010 | Complete | 2007-02-10 | 2007-04-10 | 2007-07-31 | 2007-07-07
37 | 5 | I | Rajgarh | MP 3011 | Complete | 2006-12-31 | 2007-05-31 | 2007-06-21 | 2007-06-07
38 | 5 | I | Rajgarh | MP 3012 | Complete | 30.06.2006 | 03.09.2007 | Dec.2007 | 2007-12-07
39 | 5 | I | Rajgarh | MP 3013 | Complete | 31.01.2007 | 05.02.2007 | 10.09.2007 | 2007-09-07
40 | 6 | I | Rajgarh | MP 3014 | Complete | 31.03.2008 | 10.04.2008
41 | 6 | I | Rajgarh | MP 3015 | Complete | 31.12.2007 | 28.01.2008 | 30.04.2008 | 2008-04-08
42 | B-III | I | Rajgarh | MP 3051 | Complete | 07.07.2007 | 31.01.2008 | 31.01.2008 | 2008-01-08
43 | B-III | I | Rajgarh | MP 3052 | Complete | 2006-11-29 | 2006-12-22 | 2007-07-12 | 2007-07-07
44 | B-IV | I | Rajgarh | MP 3053 | Complete | 31.03.2008 | 10.04.2008
45 | B-IV | I | Rajgarh | MP 3055 | Complete | 2007-08-10 | 30.09.2007 | Dec.2007 | 2007-12-07
46 | B-IV | I | Rajgarh | MP 3056 | Complete | 31.03.2008 | 10.04.2008
47 | B-IV | I | Rajgarh | MP 3054 | Complete | 31.01.2008 | 31.03.2008 | 30.06.2008 | 2008-06-08
48 | 1 | I | Vidisha | MP 6101 | Complete | 31-10-2005 | 31-03-06 | 30-04-06 | 2006-04-30
49 | 2 | I | Vidisha | MP 45 02 | Complete | 15/10/2004 | 15/10/2004 | 30/8/05 | 2005-08-04
50 | 2 | I | Vidisha | MP 45 03 | Complete | 30/04/2004 | 30/04/2004 | 20/08/2004 | 2004-08-04
51 | 2 | I | Vidisha | MP 45 04 | Complete | 24/10/2003 | 24/10/2003 | 20/08/2004 | 2004-08-04
52 | 3 | I | Vidisha | MP 4505 | Complete | 31/12/2004 | 31/01/2005 | 31-10-05 | 2005-10-31
53 | 3 | I | Vidisha | MP 4506 | Complete | 20-05-2006 | 20-05-2006 | 30-05-06 | 2006-05-30
54 | 3 | I | Vidisha | MP 4507 | Complete | 13/03/2005 | 30/04/2005 | 25-05-06 | 2006-05-25
55 | 3 | I | Vidisha | MP 4508 | Complete | 19/082004 | 19/082004 | 30-11-2005 | 2005-11-30
56 | 3 | I | Vidisha | MP 4509 | Complete | 15/02/2005 | 15/02/2005 | 31.12.05 | 2005-12-05
57 | 4 | I | Vidisha | MP 4510 | Complete | 30-04-06 | 30-04-06 | 30-05-2006 | 2006-05-30
58 | 4 | I | Vidisha | MP 4511 | Complete | 30.4.06 | 30.4.06 | 30.6.06 | 2006-06-30
59 | 4 | I | Vidisha | MP 4512 | Complete | 31.5.06 | 31.5.06 | 2006-07-07 | 2006-07-06
27 | 1 | IV | Rewa | MP4701 | Completed | 31.07.03 | 14.08.03 | 12.10.04 | 2004-10-12
| 1 | IV | Rewa | MP4702 | Completed | 15.07.04 | 29.09.04 | 28.05.05 | 2005-05-28
| 2 | IV | Rewa | MP 32 03 | Complete | 14.06.04 | 14.06.04 | 27.02.06 | 2006-02-27
13 | 2 | IV | Rewa | MP 3204 | Complete | 28.02.07 | 28.02.07 | 31.08.07 | 2007-08-07
| 2 | IV | Rewa | MP 3204b | Complete | 31.07.05 | 31.07.05 | 30.05.06 | 2006-05-06
| 2 | IV | Rewa | MP 3205 | Complete
| 2 | IV | Rewa | MP 32 06 | Complete | 25.4.06 | 25.4.06 | 31.10.06 | 2006-10-06
| 3 | IV | Rewa | MP 32 07 | Complete | 31.12.06 | 20.12.06 | 31.3.07 | 2007-03-07
| 3 | IV | Rewa | MP 32 08 | Complete | 31.08.07 | 04.09.07 | 31.12.07 | 2007-12-07
5 | 3 | IV | Rewa | MP 32 10 | Complete | 31.07.07 | 31.07.07 | 31.10.07 | 2007-10-07
120 | 3 | IV | Rewa | MP 32 11 | Complete | 5.2.06
14 | 4 | IV | Rewa | MP 32 12 | Complete | 28.02.07 | 30.04.07 | 31.08.07 | 2007-08-07
| 4 | IV | Rewa | MP 32 15 | Complete | 28.02.07 | 25-05-07 | 30-11-07 | 2007-11-07
6 | 4 | IV | Rewa | MP 32 16 | Complete | 31.03.07 | 30-04-07 | 31-10-07 | 2007-10-07
| 5 | IV | Rewa | MP 3218 | Complete | 30.06.07 | 04.09.07
| 5 | IV | Rewa | MP 3218A | Complete | 18.12.06 | 30.12.06 | 31.05.07 | 2007-05-07
| B-III | IV | Rewa | MP 3251 |  | 30.03.08 | 31.03.08 | 16.05.08 | 2008-05-08
7 | B-III | IV | Rewa | MP 3252 | Complete | 30.06.07 | 09.10.07 | 31.10.07 | 2007-10-07
| B-IV | IV | Rewa | MP 3256 |  | 30.05.08 | 31.05.08 | 28.06.08 | 2008-06-08
28 | 1 | II | Sagar | MP4801 | Completed | 29.7.03 | 28.2.04 | 31.3.04 | 2004-03-31
| 1 | II | Sagar | MP4802 | Completed | 25.5.03 | 25.9.03 | 30.9.03 | 2003-09-30
| 2 | II | Sagar | MP 33 03 | Complete | 31.1.04 |  | 31.3.06 | 2006-03-31
| 2 | II | Sagar | MP 33 04 | Complete | 31.1.04 | 20.7.04 | 24.7.04 | 2004-07-24
| 2 | II | Sagar | MP 33 06 | Complete | 24.7.04 | 20.7.04 | 24.7.04 | 2004-07-24
| 2 | II | Sagar | MP 33 07 | Complete | 5.3.04 | 20.7.04 | 26.7.04 | 2004-07-26
| 2 | II | Sagar | MP 33 08 | Complete | 5.3.04 | 20.7.04 | 24.7.04 | 2004-07-24
| 3 | II | Sagar | MP 33 09 | Complete | 30.06.06 | 31.7.06 | 31.01.07 | 2007-01-07
| 3 | II | Sagar | MP 33 11 | Complete | 31.12.06 | 31.1.07 | 30.6.07 | 2007-06-07
| 3 | II | Sagar | MP 33 12 | Complete | 31.3.07
| 3 | II | Sagar | MP 33 13 | Complete | 25.5.04 | 25.5.04 | 31.3.06 | 2006-03-06
| 3 | II | Sagar | MP 33 14 | Complete | 31.3.07 | 30.4.07 | 31.12.07 | 2007-12-07
| 4 | II | Sagar | MP 33 15 | Complete | 31.3.07 | 30.4.07
| 4 | II | Sagar | MP 33 16 | Complete | 30.6.07
| 4 | II | Sagar | MP 33 17 | Complete | 31.8.06 | 31.8.06 | 31.01.07 | 2007-01-07
| 5 | II | Sagar | MP 33 18 | Complete | 30.09.07 | 29.11.07
| B-III | II | Sagar | MP 33 51 | Complete | 29.9.07 | 29.9.07 | 11.01.08 | 2008-01-01
9 | 1 | IV | Satna | MP5001 | complete | 15/6/2006 | 15/6/2006 | 2007-06-09 | 2007-09-01
| 1 | IV | Satna | MP5002 | complete
29 | 2 | IV | Satna | MP 34 03 | Complete | 23/3/03 | 23/3/05 | 30/09/05 | 2005-09-30
| 2 | IV | Satna | MP 34 04 | Complete | 28/4/04 | 28/4/04 | 2005-10-10 | 2005-10-10
| 2 | IV | Satna | MP 34 04a | Complete | 29/4/04 | 29/4/04 | 30/09/05 | 2005-09-30
| 2 | IV | Satna | MP 34 04b | Complete | 30/4/04 | 30/4/04 | 2005-10-10 | 2005-10-10
| 2 | IV | Satna | MP 34 05 | Complete | 2004-08-01 | 2004-08-01 | 2004-01-06 | 2004-06-01
| 2 | IV | Satna | MP 34 06 | Complete | 18/6/2003 | 31/1/2004 | 30.5.06 | 2004-03-01
| 2 | IV | Satna | MP 34 06a | Complete | 2004-10-06 | 2004-10-06 | 30.5.06 | 2006-05-31
| 3 | IV | Satna | MP 34 08 | Complete | 30/4/07 | 30/4/07 | 31/8/07 | 2007-08-07
15 | 3 | IV | Satna | MP 34 09 | Complete | 30/4/07 | 30/4/07 | 31/8/07 | 2007-08-07
| 3 | IV | Satna | MP 34 10 | Complete | 28/1/07 | 28/1/07 | 30/4/07 | 2007-04-07
12 | 3 | IV | Satna | MP 3412 | Complete | 2006-06-12 | 2006-06-12 | 29/4/07 | 2007-04-07
15 | 3 | IV | Satna | MP 3413 | Complete | 20/7/2007 | 20/7/2007 | 29/9/2007 | 2007-09-07
22 | 4 | IV | Satna | MP3414 | Complete | 31.12.05 | 31-12-2005 | 19/12/2006 | 2006-12-06
| 4 | IV | Satna | MP3415 | Complete | 20.7.07 | 20.7.07 | 31-12-07 | 2007-12-07
| 4 | IV | Satna | MP 3417 | Complete | 23/11/2006 | 23/11/2006 | 31/5/2007 | 2007-05-07
8 | 5 | IV | Satna | MP 3419 | Complete | 21-07-2007 | 21-07-2007 | 31-10-2007 | 2007-10-07
| B-III | IV | Satna | MP 3455 | Complete | 2008-10-02 | 2008-10-02 | 31.3.08 | 2008-03-08
30 | 2 | IV | Seoni | MP 36 02 | Complete | 15-05-05 | 07-07-05 | 31-10-05 | 2005-10-31
| 2 | IV | Seoni | MP 36 03 | Complete | 31-12-03 | 17-05-04 | 21-05-05 | 2005-05-21
| 2 | IV | Seoni | MP 36 04 | Complete | 31-12-04 | 02-03-05 | 22-10-05 | 2005-10-31
| 2 | IV | Seoni | MP 36 05 | Complete | 30-06-04 | 25-09-04 | 22-10-05 | 2005-10-31
| 2 | IV | Seoni | MP 36 06 | Complete | 06-02-04 | 19-06-04 | 26-10-04 | 2004-10-26
| 2 | IV | Seoni | MP 36 07 | Complete | 03-11-04 | 05-01-05 | 9-11-06 | 2006-11-06
| 3 | IV | Seoni | MP 3608 | Complete | 28-02-06 | 22-8-06 | 22-8-06 | 2006-08-01
| 3 | IV | Seoni | MP 3609 | Complete | 15-06-04 | 19-06-04 | 28-02-07 | 2007-02-01
| 3 | IV | Seoni | MP 3610 | Complete | 30-11-05 | 23-10-06 | 30-03-07 | 2007-03-07
| 3 | IV | Seoni | MP 3611 | Complete | 30-04-05 | 21-7-05 | 10-11-06 | 2006-11-06
| 4 | IV | Seoni | MP 3612 | Complete | 30-06-07 | 15-07-07 | 31-10-07 | 2007-10-01
| 4 | IV | Seoni | MP 3613 | Complete | 20-07-06 | 07-03-07 | 30-11-07 | 2007-11-01
| 4 | IV | Seoni | MP 3614 | Complete | 20-07-05 | 13-4-06 | 31-01-07 | 2007-01-07
| 4 | IV | Seoni | MP 3615 | Complete | 31-03-06 | 24-04-06 | 29-12-07 | 2007-12-01
16 | 5 | IV | Seoni | MP 3616 | Complete | 21.03-07 | 13-4-07 | 31-8-07 | 2007-08-07
17 | 5 | IV | Seoni | MP 3617 | Complete | 28-03-07 | 5-4-07 | 31-8-07 | 2007-08-07
18 | 5 | IV | Seoni | MP 3618 | Complete | 09-08-06 | 24-6-07 | 31-8-07 | 2007-08-07
| 6 | IV | Seoni | MP 3619 | Complete | 15-06-07 | 28-06-07 | 31-01-08 | 2008-01-08
| B-I | IV | Seoni | MP 3651 | Complete | 20-04-06 | 22-9-06 | 30-04-07 | 2007-04-07
| B-I | IV | Seoni | MP 3652 | Complete | 24-11-06 | 28-11-06 | 5.5.07 | 2007-05-07
| B-III | IV | Seoni | MP 3653 | Complete | 18-09-07 | 29-10-07 | 30-11-07 | 2007-11-01
16 | B-III | IV | Seoni | MP 3654 | Complete | 08-05-07 | 29-09-07 | 18-09-07 | 2007-09-07
| B-III | IV | Seoni | MP 3655 | Complete | 18-02-08 | 20-02-08
| B-III | IV | Seoni | MP 3656 | Complete | 10-01-08 | 18-01-08 | 31-03-08 | 2008-03-08
31 | 2 | IV | Narsinghpur | MP 26 02 | Complete | 31.12.03 | 31/12/03 | 22/07/06 | 2006-07-06
| 2 | IV | Narsinghpur | MP 26 03 | Complete | 4.1.04 | 2004-04-01 | Feb. 07 | 2007-02-07
| 2 | IV | Narsinghpur | MP 26 04 | Complete | 31.12.06 | 30/11/07 | 29.02.08 | 2008-02-01
| 2 | IV | Narsinghpur | MP 26 05 | Complete | 10.09.07 | 10.09.07 | 31.12.07 | 2007-12-07
| 2 | IV | Narsinghpur | MP 26 06 | Complete | 31/03/05 | 31/03/05 | 30/09/06 | 2006-09-06
| 2 | IV | Narsinghpur | MP 26 07 | Complete | 31-5-07
| 3 | IV | Narsinghpur | MP 2608 | Complete | 31/3/05 | 31/3/05 | 22/07/06 | 2006-07-06
| 3 | IV | Narsinghpur | MP 2609 | Complete | 30/6/05 | 30/6/05 | 30/01/06 | 2006-01-02
| 3 | IV | Narsinghpur | MP 2610 | Complete | 31/03/06 | 31/03/06 | 22/07/06 | 2006-07-06
| 4 | IV | Narsinghpur | MP 2611 | Complete | 31.12.07 | 31.12.07 | 31.12.07 | 2007-12-07
| 5 | IV | Narsinghpur | MP 2613 | Complete | 30.11.07 | 30/11/07 | 31.12.07 | 2007-12-07
| 5 | IV | Narsinghpur | MP 2614 | Complete | 31-01-06 | 31-03-07 | 30-03-07 | 2007-03-07
| 5 | IV | Narsinghpur | MP 2615 |  | 31.3.08
17 | 5 | IV | Narsinghpur | MP 2618 | Complete | 15/6/07 | 15/6/07 | 30/09/07 | 2007-09-07
| B-III | IV | Narsinghpur | MP 2651 | Complete | 26-02-08 | 26-02-08 | 31-03-08 | 2008-03-08
| B-III | IV | Narsinghpur | MP 2652 | Complete | 15-01-08 | 15-01-08 | 31-03-08 | 2008-03-08
32 | 1 | IV | Shahdol | MP5401 | Completed | 31.3.04 | 24.6.04 | 12.10.2004 | 2004-10-12
| 2 | IV | Shahdol | MP 38 02 | Complete | 31.1.04 | 22.1.04 | 21.02.2005 | 2005-02-21
| 2 | IV | Shahdol | MP 38 03 | Complete | 15.1.04 | 22.1.04 | 12.10.2004 | 2004-10-12
| 2 | IV | Shahdol | MP 38 04 | Complete | 31.12.03 | 22.1.04 | 11.10.2004 | 2004-10-11
| 2 | IV | Shahdol | MP 38 05 | Complete | 31.12.03 | 22.1.04 | 12.10.2004 | 2004-10-12
| 3 | IV | Shahdol | MP 3806 | Complete | 15.6.04 | 23.8.04 | 15.10.2004 | 2004-10-15
| 3 | IV | Shahdol | MP 3807 | Complete | 30.4.07 | - | 31.7.07 | 2007-07-07
| 3 | IV | Shahdol | MP 3808 | Complete | 30.3.07 | 28.04.07 | 30.6.07 | 2007-06-07
| 4 | IV | Shahdol | MP 3809 | Complete | 31.5.06 | 12.7.06 | 31.8.06 | 2006-08-31
9 | 4 | IV | Shahdol | MP 3810 | Complete | 31.8.07 | 31.8.07 | 31.10.07 | 2007-10-07
| 4 | IV | Shahdol | MP 3811 | Complete | 15.6.06 | 15.6.06 | 30.6.07 | 2007-06-07
| 5 | IV | Shahdol | MP 3812 | Complete | 28.2.07 | 28.04-07 | 30.6.07 | 2007-06-07
| 5 | IV | Shahdol | MP 3813 | Complete | 5.6.07 | 6.6.07 | 18.7.07 | 2007-08-07
19 | 5 | IV | Shahdol | MP 3814 | Complete | 15.02.07 | 15.02.07 | 31-08-07 | 2007-08-07
18 | 5 | IV | Anuppur | MP 3815 | Complete | 30.06.07 | 30.06.07 | 30.09.07 | 2007-11-01
| B-III | IV | Shahdol | MP 3852 | Complete | 30.09.07 | 18.12.07 | 31.03.08 | 2008-03-08
10 | B-III | IV | Shahdol | MP 3853 | Complete | 15.6.07 | 11.8.07 | 31.10.07 | 2007-10-07
| B-III | IV | Shahdol | MP 3855 | Complete | 28.2.07 | 28.2.07
| 6 | IV | Anuppur | MP 4604 |  | 31.3.08
| B-IV | IV | Anuppur | MP 4651 |  | 28.2.08
| 1 | IV | Umaria | MP6001 | Completed | 28.2.03 | 24.6.04 | 18.10.2004 | 2004-10-18
| 2 | IV | Umaria | MP 44 02 | Complete | 31.12.03 | 22.1.04 | 18.10.2004 | 2004-10-18
| 4 | IV | Umaria | MP 44 04 | Complete | 31.05.06 | 31.05.06 | 31.10.06 | 2006-10-06
20 | 5 | IV | Umaria | MP 44 05 | Complete | 30.04.06 | 30.04.06 | 31.08.07 | 2007-08-07
| B-III | IV | Umaria | MP 44 51 | Complete | 26.09.07 | 26.09.07 | 30.11.07 | 2007-11-07
| 1 | II | Sheopur | MP5301 | Completed | 16.11.02 | 15.1.04 | 30.7.05 | 2004-07-30
| 2 | II | Sheopur | MP 3702 | Complete | 10.9.03 |  | 28.07.06 | 2006-07-06
| 2 | II | Sheopur | MP 3702 A | Complete | 10.10.03 | 31.3.05 | 30.05.05 | 2005-05-30
| 2 | II | Sheopur | MP 3702 B | Complete | 31.5.06 |  | 03.07.06 | 2006-07-06
| 3 | II | Sheopur | MP 3703 | Complete | 30.6.04 | 30.6.04 | 28.6.05 | 2005-06-28
| 3 | II | Sheopur | MP 3703a | Complete | 3.1.07
| 4 | II | Sheopur | MP 3705 | Complete | 25.06.2006 | 29.06.06 | 12.07.06 | 2006-07-06
| 5 | II | Sheopur | MP 3708 |  | 31.03.08 | 31.03.08 | 24.05.08 | 2008-05-08
33 | 1 | II | Shivpuri | MP5601 | Completed | 9.6.02 |  | 28-2-06 | 2006-02-28
| 1 | II | Shivpuri | MP5604 | Completed | 9.6.02 |  | 31-12-05 | 2004-12-05
| 2 | II | Shivpuri | MP 40 02 | Complete | 2.5.03 | 6.9.04 | 15.12.04 | 2004-12-05
| 2 | II | Shivpuri | MP 40 03 | Complete | 2.5.03 | 6.9.04 | 26.2.05 | 2005-02-26
| 2 | II | Shivpuri | MP 40 05 | Complete | 29.4.03 | 30.6.03 | 31.3.05 | 2005-03-31
| 2 | II | Shivpuri | MP 40 06 | Complete | 29.4.03 | 30.6.03 | 12.4.05 | 2005-04-12
| 2 | II | Shivpuri | MP 40 07 | Complete | 2.5.03 | 31.3.05 | 31.3.05 | 2005-03-31
| 2 | II | Shivpuri | MP 40 08 | Complete | 2.5.03 | 31.3.04 | 8.7.04 | 2004-07-08
| 3 | II | Shivpuri | MP 4009 | Complete | 12.5.04 | 1.10.04 | 30.5.05 | 2005-05-30
| 3 | II | Shivpuri | MP 4010 | Complete | 2004-11-04 | 2007-10-05 | 30-7-07 | 2007-07-07
13 | 3 | II | Shivpuri | MP 4011 | complete | 11.4.04 | 31.12.06 | 31.3.07 | 2007-03-07
150 | 3 | II | Shivpuri | MP 4012 | complete | 2004-11-04 | 30-11-05 | 2006-12-07 | 2006-07-06
| 3 | II | Shivpuri | MP 4013 | complete | 2004-01-06 | 15-6-05 | 31-3-06 | 2006-03-06
| 4 | II | Shivpuri | MP 4014 | Complete | 2005-08-03 | 25-6-06 | 31-8-2006 | 2006-08-06
| 4 | II | Shivpuri | MP 4015 | Complete | 2005-08-03 | 15-3-06 | 31-8-2006 | 2006-08-06
| 5 | II | Shivpuri | MP 4016 | Complete | 14.6.06 | 30.1.07 | 31.5.07 | 2007-05-07
14 | 5 | II | Shivpuri | MP 4017 | Complete | 15.9.06 | 5.1.07 | 30.3.07 | 2007-03-07
| 6 | II | Shivpuri | MP 4019 | Complete | 15.1.08
15 | B-II | II | Shivpuri | MP 4051 | Complete | 9.10.06 | 31.12.06 | 30.3.07 | 2007-03-07
16 | B-II | II | Shivpuri | MP 4052 | Complete | 9.10.06 | 31.1.07 | 31.3.07 | 2007-03-07
17 | B-III | II | Shivpuri | MP 4053 | Complete | 28.12.06 | 23.12.06 | 31.3.07 | 2007-03-07
| B-III | II | Shivpuri | MP 4055 | Complete | 28-12-06 | 30-6-2007 | 30-7-07 | 2007-07-07
| B-IV | II | Shivpuri | MP 4056 | Complete | 31.12.07
| B-IV | II | Shivpuri | MP 4059 |  | 31.3.08
34 | 1 | IV | Sidhi | MP5701 | Completed | 25.06.04 | 02.08.05 | 08.02.05 | 2005-02-01
| 1 | IV | Sidhi | MP5702 | Completed | 31.3.06 | 31.3.06 | 9.11.06 | 2006-11-06
| 2 | IV | Waidhan | MP 41 03 | Complete | 30.08.03 | 30.08.03 | 13.07.04 | 2004-07-13
| 2 | IV | Waidhan | MP 41 04 | Complete | 30.07.03 | 30.07.03 | 13.07.04 | 2004-07-13
| 2 | IV | Waidhan | MP 41 05 | Complete | 30.04.06 | 30.04.06 | 31.08.06 | 2006-08-01
| 2 | IV | Sidhi | MP 41 06 | Complete | 30.3.06 | 30.3.06 | 30.6.07 | 2007-06-07
| 2 | IV | Sidhi | MP 41 07 | Complete | 15.01.05 | 28.04.05 | 31.03.06 | 2006-03-31
| 2 | IV | Sidhi | MP 41 08 | Complete | 31.08.05 | 31.08.05 | 28.02.06 | 2006-02-28
| 2 | IV | Sidhi | MP 41 09 | Complete | 31.01.05 | 28.04.05 | 14.11.06 | 2006-11-06
| 3 | IV | Waidhan | MP 4110 | Complete | 31.05.04 | 15.07.04 | 11.7.05 | 2005-07-11
| 3 | IV | Sidhi | MP 4111 | Complete | 31.3.06 | 31.3.06 | 14.11.06 | 2006-11-06
| 3 | IV | Sidhi | MP 4112 | Complete | 30.4.06 | 30.4.06 | 30.9.06 | 2006-09-06
155 | 3 | IV | Sidhi | MP 4113 | complete | 21.01.06 | 21.1.06 | 31.03.06 | 2006-03-31
| 4 | IV | Sidhi | MP 4114 | complete | 30.04.06 | 30.4.06 | 31.08.06 | 2006-08-31
| 4 | IV | Sidhi | MP 4115 | complete | 31.05.06 | 31.05.06 | 30.06.07 | 2007-06-07
| 4 | IV | Sidhi | MP 4116 | complete | 2008-02-01
| 4 | IV | Waidhan | MP 4117 | complete | 15.06.05 | 15.06.05 | Vr. No. 04 Dt. 31.08.05 by sidhi piu | 2005-08-01
| 5 | IV | Waidhan | MP 4118 | complete | 28.10.06 | 28-10-06 | 31-5-2007 | 2007-05-07
| 5 | IV | Waidhan | MP 4119 | complete | 10.10.06 | 2006-10-10 | 23-3-07 | 2007-03-07
| 5 | IV | Sidhi | MP 4121 | complete | 31.08.07 | 31.08.07 | 31.3.08 | 2008-03-08
| 5 | IV | Sidhi | MP 4122 | complete | 30.10.06 | 29.12.06 | 30.06.07 | 2007-06-07
| 6 | IV | Sidhi | MP 4124 |  | 31.3.08
| 6 | IV | Sidhi | MP 4125 | complete
| 6 | IV | Waidhan | MP 4127 | complete | 31.5.07 | 31.5.07 | 31.7.07 | 2007-07-07
| 6 | IV | Waidhan | MP 4128 | complete | 5.1.08 | 5.1.08
| B-I | IV | Sidhi | MP 4152 | complete | 31.1.08
| B-III | IV | Waidhan | MP 4153 | complete | 31-3-07 | 31.03.07 | 29.6.07 | 2007-06-07
| B-III | IV | Waidhan | MP 4154 | complete | 31-3-07 | 16.04.07 | 07.08.07 | 2007-08-07
| B-IV | IV | Sidhi | MP 4156
| B-IV | IV | Sidhi | MP 4157 | complete | 31.07.07 | 31.07.07 | 31.12.07 | 2007-12-01
| B-IV | IV | Sidhi | MP 4158 | complete | 20.08.07 | 20.08.07 | 31.12.07 | 2007-12-01
| B-IV | IV | Sidhi | MP 4161 |  | 30.3.08
| B-IV | IV | Sidhi | MP 4163 | complete | 30.11.07 | 30.11.07 | 31.3.08 | 2008-03-08
| 1 | III | Ratlam | MP4301 | Completed | 31.01.03 |  | 07.08.04 | 2004-08-04
| 2 | III | Ratlam | MP 31 02 | Complete | 15.01.04 |  | 25.09.04 | 2004-09-25
| 3 | III | Ratlam | MP 3103 | Complete | 15.06.05 |  | 24.12.05 | 2005-12-05
| 4 | III | Ratlam | MP 3105 | Complete | 31-03-06 | 31.3.06 | 31.10.06 | 2006-10-06
| 4 | III | Ratlam | MP 3106 | Complete | 06.04.05 |  | 12.08.05 | 2005-08-04
| 5 | III | Ratlam | MP 3108 |  | 31.3.08
| B-III | III | Ratlam | MP 3152 | Complete | 29.02.08
35 | 1 | III | Ujjain | MP5901 | Completed | 31.1.04 | 2.7.04 | 28-2-05 | 2005-02-28
| 2 | III | Ujjain | MP 43 02 | Complete | 20.7.04 | 22.2.05 | 30.11.05 | 2005-11-30
| 2 | III | Ujjain | MP 43 03 | Complete | 30.8.03 | 30.8.03 | 30.9.05 | 2005-09-30
| 2 | III | Ujjain | MP 43 04 | Complete | 15.9.04 | 10.12.04 | 31.3.06 | 2006-03-31
| 4 | III | Ujjain | MP 4308 | Complete | 30.6.05 |  | 31.12.05 | 2005-12-05
| 4 | III | Ujjain | MP 4309 | Complete | 4.03.05 | 5.06.06 | 31.01.07 | 2007-01-07
19
108
532