## proforma-I
Proforma-I
Name of PIU-----------------------------------------------Name of Contractor---------------------------------------
|  |  | Contract Pkg. No MP----------------------------- | Value of work done upto
P.A.C. Amount Rs-------------------- |  |  | stipulated date of Completion :-Rs-----------------------
Contract Amount Rs --------------- |  |  |  | I Extension up to---------------------work done Rs-----------------
II Extension up to----------------------work done Rs-----------------
Date of Work Order |  |  | Stipulated Date | III Extension up to----------------------work done Rs-----------------
Of Cmpletion-------------------------------------------
Actual Date of
Completion
S.No | Period of delay Give Dates |  | Reasons given by Contractor | Comments of Consultants for each reasons & recommendation | Comments of G.M. of P.I.U. on the each reason | Value of Work done to date | date up to which extension recommded
| From | To
1 | 2 |  | 3 | 4 | 5 | 6 | 7
| signature of Contractor |  | signature of Consultant |  |  |  | signature of G.M.

## proforma-II
Proforma-II
Proforma to be used while submitting time extension case
1. | Name of work with estimated cost and contract amount separately
PAC Rs.
Contract Amount Rs.
2. | Name of Contractor
3. | Percentage above/below tendered by the contractor
4. | Authority sanctioning the work with reference No. Date.
5. | No. & Date of work order issued by the General Manager
6. | Date of layout given by the PIU/Department
7. | Time allowed originally for completion as per agreement (excluding or including rainy season)
8. | Date of actual starting the work by the contractor
9. | Whether any extension granted earlier, if any
10. | (a) for what period
(b) On what ground
11. | Notices given by the General Manager
12. | Further extension applied for
(a) Dates of application
(for such extension)
| (b) | (c) | (d)
| Ground given by contractor | comments of Consultant | Comments of GM
Please attach separate sheet if necessary
13. | Value of work done by the contractor during the stipulated period of contract
14. | Value of work done by the contractor I/c during extended period
(a) Value of work done up to date
(b) Value of work to be done
15. | Recommendations

## proforma-III
Proforma-III
Madhya Pradesh Rural Road Development Authority Project Implementation Unit ……………..
Road wise Programme
Name of Contractor :- | [5 empty] | Probable amount of contract:-
Name of Consultant :- | [5 empty] | Date of work order:
Rate :- %below/above | [5 empty] | Stipulated date of completion :-
Extended date of completion :-
Name of Road : |  |  |  | Package No. :- |  |  | Length: |  | Total Cost (Lakhs) Rs.
S.No | Activity | Length Km. | Completed upto | Balance | Sept. | Oct. | Nov. | Dec. | Jan | Feb. | March
1 | Setting out & Jungle Clearance
2 | Earth work for Embankment
3 | Earth work of Subgrade
4 | Granular Sub Base
5 | WBM Grade-II
6 | WBM Grade-III
7 | Hard Shoulder
8 | B.T. Work
9 | CC Pavement
10 | C.D. Work/Bridge
11 | Road side Furnitures & missellanous
| Sign of Contractor |  |  | Comments of Consultant | Total Cost (Lakhs) Rs. Jan: GM's Remarks