## Sheet2 (2)
| T A R G E T 09-10 |  |  | A C H I E V E M E N T 09-10 |  |  |  | BALANCE --- TARGET upto Sept'9 |  | TARGET ------ 2009-10
PIU | Length in KM | No. of Road | Total amount | Length in KM | Expenditure in Lakh | % of Phy. | % of Fin. | Length in KM | Total Expenditure | Oct'09 |  | Nov'09 |  | Dec'09 |  | Jan'10 |  | Feb'10 |  | Mar'10
[10 empty] | Length in km | Amount rs. in lakh | Length in km | Amount rs. in lakh | Length in km | Amount rs. in lakh | Length in km | Amount rs. in lakh | Length in km | Amount rs. in lakh | Length in km | Amount rs. in lakh
Alirajpur-1 | 107.64 | 27 | 2250 | 13.8 | 1461 | 12.8205 | 64.9333 | 93.84 | 789 | 15.64 | 131.5 | 15.64 | 131.5 | 15.64 | 131.5 | 15.64 | 131.5 | 15.64 | 131.5 | 15.64 | 131.5
Alirajpur-2 | 192.68 | 46 | 4360 | 3.5 | 1141 | 1.8165 | 26.1697 | 189.18 | 3219 | 31.53 | 536.5 | 31.53 | 536.5 | 31.53 | 536.5 | 31.53 | 536.5 | 31.53 | 536.5 | 31.53 | 536.5
Anuppur-1 | 153.78 | 29 | 3869.89 | 5.1 | 1773 | 3.3164 | 45.8153 | 148.68 | 2096.89 | 24.78 | 349.4817 | 24.78 | 349.4817 | 24.78 | 349.4817 | 24.78 | 349.4817 | 24.78 | 349.4817 | 24.78 | 349.4817
Anuppur-2 | 86.81 | 18 | 1347.58 | 0 | 1304 | 0 | 96.7661 | 86.81 | 43.58 | 14.4683 | 7.2633 | 14.4683 | 7.2633 | 14.4683 | 7.2633 | 14.4683 | 7.2633 | 14.4683 | 7.2633 | 14.4683 | 7.2633
Ashoknagar | 27.64 | 6 | 725 | 7.701 | 557 | 27.8618 | 76.8276 | 19.939 | 168 | 3.3232 | 28 | 3.3232 | 28 | 3.3232 | 28 | 3.3232 | 28 | 3.3232 | 28 | 3.3232 | 28
Balaghat-1 | 291.56 | 55 | 5791.05 | 4.2 | 1135 | 1.4405 | 19.5992 | 287.36 | 4656.05 | 47.8933 | 776.0083 | 47.8933 | 776.0083 | 47.8933 | 776.0083 | 47.8933 | 776.0083 | 47.8933 | 776.0083 | 47.8933 | 776.0083
Balaghat-2 | 192.7 | 45 | 3614 | 29.09 | 1388 | 15.096 | 38.4062 | 163.61 | 2226 | 27.2683 | 371 | 27.2683 | 371 | 27.2683 | 371 | 27.2683 | 371 | 27.2683 | 371 | 27.2683 | 371
Balaghat-3 | 185.55 | 41 | 4227.88 | 0 | 357 | 0 | 8.4439 | 185.55 | 3870.88 | 30.925 | 645.1467 | 30.925 | 645.1467 | 30.925 | 645.1467 | 30.925 | 645.1467 | 30.925 | 645.1467 | 30.925 | 645.1467
Barwani-1 | 153.88 | 38 | 2416 | 58 | 968 | 37.6917 | 40.0662 | 95.88 | 1448 | 15.98 | 241.3333 | 15.98 | 241.3333 | 15.98 | 241.3333 | 15.98 | 241.3333 | 15.98 | 241.3333 | 15.98 | 241.3333
Barwani-2 | 336 | 28 | 5113.46 | 82.75 | 2051 | 24.628 | 40.1098 | 253.25 | 3062.46 | 42.2083 | 510.41 | 42.2083 | 510.41 | 42.2083 | 510.41 | 42.2083 | 510.41 | 42.2083 | 510.41 | 42.2083 | 510.41
Sendhwa | 309.5 | 71 | 3600 | 34.026 | 1616 | 10.9939 | 44.8889 | 275.474 | 1984 | 45.9123 | 330.6667 | 45.9123 | 330.6667 | 45.9123 | 330.6667 | 45.9123 | 330.6667 | 45.9123 | 330.6667 | 45.9123 | 330.6667
Betul-1 | 197.16 | 61 | 4625.06 | 29.679 | 1564 | 15.0533 | 33.8158 | 167.481 | 3061.06 | 27.9135 | 510.1767 | 27.9135 | 510.1767 | 27.9135 | 510.1767 | 27.9135 | 510.1767 | 27.9135 | 510.1767 | 27.9135 | 510.1767
Betul-2 | 236.62 | 68 | 2891.78 | 6.262 | 1412 | 2.6464 | 48.8281 | 230.358 | 1479.78 | 38.393 | 246.63 | 38.393 | 246.63 | 38.393 | 246.63 | 38.393 | 246.63 | 38.393 | 246.63 | 38.393 | 246.63
Betul-3 | 153.03 | 31 | 2342.36 | 3.937 | 810 | 2.5727 | 34.5805 | 149.093 | 1532.36 | 24.8488 | 255.3933 | 24.8488 | 255.3933 | 24.8488 | 255.3933 | 24.8488 | 255.3933 | 24.8488 | 255.3933 | 24.8488 | 255.3933
Betul-4 | 231.79 | 45 | 3886 | 15.9 | 1140 | 6.8597 | 29.3361 | 215.89 | 2746 | 35.9817 | 457.6667 | 35.9817 | 457.6667 | 35.9817 | 457.6667 | 35.9817 | 457.6667 | 35.9817 | 457.6667 | 35.9817 | 457.6667
Bhind | 485.62 | 111 | 5326.9 | 28.707 | 1582 | 5.9114 | 29.6983 | 456.913 | 3744.9 | 76.1522 | 624.15 | 76.1522 | 624.15 | 76.1522 | 624.15 | 76.1522 | 624.15 | 76.1522 | 624.15 | 76.1522 | 624.15
Bhopal | 143.2 | 50 | 2000 | 25.536 | 1146 | 17.8324 | 57.3 | 117.664 | 854 | 19.6107 | 142.3333 | 19.6107 | 142.3333 | 19.6107 | 142.3333 | 19.6107 | 142.3333 | 19.6107 | 142.3333 | 19.6107 | 142.3333
Burhanpur | 163.73 | 32 | 3300 | 25.79 | 1213 | 15.7515 | 36.7576 | 137.94 | 2087 | 22.99 | 347.8333 | 22.99 | 347.8333 | 22.99 | 347.8333 | 22.99 | 347.8333 | 22.99 | 347.8333 | 22.99 | 347.8333
Chhatarpur 1 | 93.08 | 15 | 1650 | 0 | 605 | 0 | 36.6667 | 93.08 | 1045 | 15.5133 | 174.1667 | 15.5133 | 174.1667 | 15.5133 | 174.1667 | 15.5133 | 174.1667 | 15.5133 | 174.1667 | 15.5133 | 174.1667
Chhatarpur-2 | 328.15 | 81 | 3600 | 19.801 | 714 | 6.0341 | 19.8333 | 308.349 | 2886 | 51.3915 | 481 | 51.3915 | 481 | 51.3915 | 481 | 51.3915 | 481 | 51.3915 | 481 | 51.3915 | 481
Chhindwara-1 | 79.73 | 26 | 2211 | 41.19 | 714 | 51.6619 | 32.2931 | 38.54 | 1497 | 6.4233 | 249.5 | 6.4233 | 249.5 | 6.4233 | 249.5 | 6.4233 | 249.5 | 6.4233 | 249.5 | 6.4233 | 249.5
chhindwara-2 | 161.32 | 49 | 2982.88 | 9.032 | 654 | 5.5988 | 21.9251 | 152.288 | 2328.88 | 25.3813 | 388.1467 | 25.3813 | 388.1467 | 25.3813 | 388.1467 | 25.3813 | 388.1467 | 25.3813 | 388.1467 | 25.3813 | 388.1467
Chhindwara-3 | 145.33 | 38 | 3045.66 | 40.08 | 657 | 27.5786 | 21.5717 | 105.25 | 2388.66 | 17.5417 | 398.11 | 17.5417 | 398.11 | 17.5417 | 398.11 | 17.5417 | 398.11 | 17.5417 | 398.11 | 17.5417 | 398.11
Chhindwara-4 | 68.85 | 19 | 2046.99 | 34.928 | 641 | 50.7306 | 31.3143 | 33.922 | 1405.99 | 5.6537 | 234.3317 | 5.6537 | 234.3317 | 5.6537 | 234.3317 | 5.6537 | 234.3317 | 5.6537 | 234.3317 | 5.6537 | 234.3317
Chhindwara-5 | 158.67 | 47 | 3157.5 | 68.085 | 1297 | 42.9098 | 41.0768 | 90.585 | 1860.5 | 15.0975 | 310.0833 | 15.0975 | 310.0833 | 15.0975 | 310.0833 | 15.0975 | 310.0833 | 15.0975 | 310.0833 | 15.0975 | 310.0833
Damoh | 101.11 | 32 | 1900 | 32.013 | 834 | 31.6616 | 43.8947 | 69.097 | 1066 | 11.5162 | 177.6667 | 11.5162 | 177.6667 | 11.5162 | 177.6667 | 11.5162 | 177.6667 | 11.5162 | 177.6667 | 11.5162 | 177.6667
Datia | 114.102 | 35 | 1692 | 26.351 | 324 | 23.0942 | 19.1489 | 87.751 | 1368 | 14.6252 | 228 | 14.6252 | 228 | 14.6252 | 228 | 14.6252 | 228 | 14.6252 | 228 | 14.6252 | 228
Dewas-1 | 120 | 36 | 2574.98 | 0 | 935 | 0 | 36.311 | 120 | 1639.98 | 20 | 273.33 | 20 | 273.33 | 20 | 273.33 | 20 | 273.33 | 20 | 273.33 | 20 | 273.33
Dewas-2 | 89.45 | 20 | 2635 | 22.265 | 1062 | 24.891 | 40.3036 | 67.185 | 1573 | 11.1975 | 262.1667 | 11.1975 | 262.1667 | 11.1975 | 262.1667 | 11.1975 | 262.1667 | 11.1975 | 262.1667 | 11.1975 | 262.1667
Dhar-1 | 85.89 | 26 | 3501.7 | 51.18 | 752 | 59.5878 | 21.4753 | 34.71 | 2749.7 | 5.785 | 458.2833 | 5.785 | 458.2833 | 5.785 | 458.2833 | 5.785 | 458.2833 | 5.785 | 458.2833 | 5.785 | 458.2833
Dhar-3 | 114.43 | 32 | 3100 | 33.635 | 1256 | 29.3935 | 40.5161 | 80.795 | 1844 | 13.4658 | 307.3333 | 13.4658 | 307.3333 | 13.4658 | 307.3333 | 13.4658 | 307.3333 | 13.4658 | 307.3333 | 13.4658 | 307.3333
Dhar-4 | 113.3 | 34 | 3737 | 45.785 | 1543 | 40.4104 | 41.2898 | 67.515 | 2194 | 11.2525 | 365.6667 | 11.2525 | 365.6667 | 11.2525 | 365.6667 | 11.2525 | 365.6667 | 11.2525 | 365.6667 | 11.2525 | 365.6667
Kukshi | 161.85 | 44 | 2971.41 | 35.18 | 979 | 21.7362 | 32.9473 | 126.67 | 1992.41 | 21.1117 | 332.0683 | 21.1117 | 332.0683 | 21.1117 | 332.0683 | 21.1117 | 332.0683 | 21.1117 | 332.0683 | 21.1117 | 332.0683
Dindori-1 | 164.14 | 46 | 4643.19 | 39.98 | 1014 | 24.3573 | 21.8384 | 124.16 | 3629.19 | 20.6933 | 604.865 | 20.6933 | 604.865 | 20.6933 | 604.865 | 20.6933 | 604.865 | 20.6933 | 604.865 | 20.6933 | 604.865
Dindori-2 | 238.175 | 52 | 4884.5 | 28.18 | 682 | 11.8316 | 13.9625 | 209.995 | 4202.5 | 34.9992 | 700.4167 | 34.9992 | 700.4167 | 34.9992 | 700.4167 | 34.9992 | 700.4167 | 34.9992 | 700.4167 | 34.9992 | 700.4167
Guna | 140.858 | 20 | 2200 | 45.562 | 581 | 32.3461 | 26.4091 | 95.296 | 1619 | 15.8827 | 269.8333 | 15.8827 | 269.8333 | 15.8827 | 269.8333 | 15.8827 | 269.8333 | 15.8827 | 269.8333 | 15.8827 | 269.8333
Gwalior | 186.976 | 53 | 3248.46 | 0 | 947 | 0 | 29.1523 | 186.976 | 2301.46 | 31.1627 | 383.5767 | 31.1627 | 383.5767 | 31.1627 | 383.5767 | 31.1627 | 383.5767 | 31.1627 | 383.5767 | 31.1627 | 383.5767
Harda | 168.9 | 27 | 2000 | 29.598 | 797 | 17.524 | 39.85 | 139.302 | 1203 | 23.217 | 200.5 | 23.217 | 200.5 | 23.217 | 200.5 | 23.217 | 200.5 | 23.217 | 200.5 | 23.217 | 200.5
Hoshangabad | 71.715 | 22 | 1717 | 30.851 | 456 | 43.0189 | 26.5579 | 40.864 | 1261 | 6.8107 | 210.1667 | 6.8107 | 210.1667 | 6.8107 | 210.1667 | 6.8107 | 210.1667 | 6.8107 | 210.1667 | 6.8107 | 210.1667
Indore | 97 | 23 | 1295 | 31.115 | 673 | 32.0773 | 51.9691 | 65.885 | 622 | 10.9808 | 103.6667 | 10.9808 | 103.6667 | 10.9808 | 103.6667 | 10.9808 | 103.6667 | 10.9808 | 103.6667 | 10.9808 | 103.6667
Jabalpur | 99.42 | 20 | 1550 | 0 | 524 | 0 | 33.8065 | 99.42 | 1026 | 16.57 | 171 | 16.57 | 171 | 16.57 | 171 | 16.57 | 171 | 16.57 | 171 | 16.57 | 171
Jhabua-1 | 183.209 | 49 | 4672 | 0 | 1750 | 0 | 37.4572 | 183.209 | 2922 | 30.5348 | 487 | 30.5348 | 487 | 30.5348 | 487 | 30.5348 | 487 | 30.5348 | 487 | 30.5348 | 487
Jhabua-2 | 948.57 | 413 | 6927.443 | 18.705 | 1324 | 1.9719 | 19.1124 | 929.865 | 5603.443 | 154.9775 | 933.9072 | 154.9775 | 933.9072 | 154.9775 | 933.9072 | 154.9775 | 933.9072 | 154.9775 | 933.9072 | 154.9775 | 933.9072
Jhabua-3 | 230.16 | 45 | 3999.4 | 15.398 | 1037 | 6.6901 | 25.9289 | 214.762 | 2962.4 | 35.7937 | 493.7333 | 35.7937 | 493.7333 | 35.7937 | 493.7333 | 35.7937 | 493.7333 | 35.7937 | 493.7333 | 35.7937 | 493.7333
Katni | 161.59 | 40 | 3018 | 30.774 | 1680 | 19.0445 | 55.666 | 130.816 | 1338 | 21.8027 | 223 | 21.8027 | 223 | 21.8027 | 223 | 21.8027 | 223 | 21.8027 | 223 | 21.8027 | 223
Khandwa-1 | 250.05 | 58 | 5652.42 | 21.16 | 1363 | 8.4623 | 24.1136 | 228.89 | 4289.42 | 38.1483 | 714.9033 | 38.1483 | 714.9033 | 38.1483 | 714.9033 | 38.1483 | 714.9033 | 38.1483 | 714.9033 | 38.1483 | 714.9033
Khandwa-2 | 144.65 | 43 | 4140.95 | 21.091 | 1453 | 14.5807 | 35.0886 | 123.559 | 2687.95 | 20.5932 | 447.9917 | 20.5932 | 447.9917 | 20.5932 | 447.9917 | 20.5932 | 447.9917 | 20.5932 | 447.9917 | 20.5932 | 447.9917
Khandwa-3 | 159.39 | 40 | 4118.8841 | 0 | 1073 | 0 | 26.0507 | 159.39 | 3045.8841 | 26.565 | 507.6473 | 26.565 | 507.6473 | 26.565 | 507.6473 | 26.565 | 507.6473 | 26.565 | 507.6473 | 26.565 | 507.6473
Khargone-1 | 207.13 | 51 | 5006.64 | 0 | 541 | 0 | 10.8057 | 207.13 | 4465.64 | 34.5217 | 744.2733 | 34.5217 | 744.2733 | 34.5217 | 744.2733 | 34.5217 | 744.2733 | 34.5217 | 744.2733 | 34.5217 | 744.2733
Khargone-2 | 233.875 | 62 | 5506 | 50.719 | 1418 | 21.6864 | 25.7537 | 183.156 | 4088 | 30.526 | 681.3333 | 30.526 | 681.3333 | 30.526 | 681.3333 | 30.526 | 681.3333 | 30.526 | 681.3333 | 30.526 | 681.3333
Khargone-3 | 61.65 | 23 | 2119 | 52.53 | 484 | 85.2068 | 22.841 | 9.12 | 1635 | 1.52 | 272.5 | 1.52 | 272.5 | 1.52 | 272.5 | 1.52 | 272.5 | 1.52 | 272.5 | 1.52 | 272.5
Maheshwar | 292.55 | 62 | 3691.7 | 2.536 | 2020 | 0.86686 | 54.7173 | 290.014 | 1671.7 | 48.3357 | 278.6167 | 48.3357 | 278.6167 | 48.3357 | 278.6167 | 48.3357 | 278.6167 | 48.3357 | 278.6167 | 48.3357 | 278.6167
Mandla-I | 63.86 | 25 | 1515.03 | 0 | 706 | 0 | 46.5997 | 63.86 | 809.03 | 10.6433 | 134.8383 | 10.6433 | 134.8383 | 10.6433 | 134.8383 | 10.6433 | 134.8383 | 10.6433 | 134.8383 | 10.6433 | 134.8383
Mandla-II | 239.79 | 64 | 3683.09 | 68.24 | 1176 | 28.4582 | 31.9297 | 171.55 | 2507.09 | 28.5917 | 417.8483 | 28.5917 | 417.8483 | 28.5917 | 417.8483 | 28.5917 | 417.8483 | 28.5917 | 417.8483 | 28.5917 | 417.8483
Mandsaur-1 | 32.3 | 11 | 1247 | 20.725 | 587 | 64.1641 | 47.073 | 11.575 | 660 | 1.9292 | 110 | 1.9292 | 110 | 1.9292 | 110 | 1.9292 | 110 | 1.9292 | 110 | 1.9292 | 110
Mandsaur-2 | 157.62 | 24 | 4015.32 | 0 | 1363 | 0 | 33.945 | 157.62 | 2652.32 | 26.27 | 442.0533 | 26.27 | 442.0533 | 26.27 | 442.0533 | 26.27 | 442.0533 | 26.27 | 442.0533 | 26.27 | 442.0533
Mandsaur-3 | 105.725 | 26 | 1600 | 0 | 1038 | 0 | 64.875 | 105.725 | 562 | 17.6208 | 93.6667 | 17.6208 | 93.6667 | 17.6208 | 93.6667 | 17.6208 | 93.6667 | 17.6208 | 93.6667 | 17.6208 | 93.6667
Morena-1 | 365.38 | 70 | 4184 | 0 | 1746 | 0 | 41.7304 | 365.38 | 2438 | 60.8967 | 406.3333 | 60.8967 | 406.3333 | 60.8967 | 406.3333 | 60.8967 | 406.3333 | 60.8967 | 406.3333 | 60.8967 | 406.3333
Morena-2 | 195.15 | 57 | 3717.88 | 14.55 | 1289 | 7.4558 | 34.6703 | 180.6 | 2428.88 | 30.1 | 404.8133 | 30.1 | 404.8133 | 30.1 | 404.8133 | 30.1 | 404.8133 | 30.1 | 404.8133 | 30.1 | 404.8133
Narsinghpur-1 | 102.11 | 31 | 2300 | 18.9 | 829 | 18.5095 | 36.0435 | 83.21 | 1471 | 13.8683 | 245.1667 | 13.8683 | 245.1667 | 13.8683 | 245.1667 | 13.8683 | 245.1667 | 13.8683 | 245.1667 | 13.8683 | 245.1667
Narsinghpur-2 | 40.7 | 7 | 1300 | 0 | 234 | 0 | 18 | 40.7 | 1066 | 6.7833 | 177.6667 | 6.7833 | 177.6667 | 6.7833 | 177.6667 | 6.7833 | 177.6667 | 6.7833 | 177.6667 | 6.7833 | 177.6667
Neemuch | 71.1 | 14 | 2219 | 65.22 | 1320 | 91.73 | 59.4863 | 5.88 | 899 | 0.98 | 149.8333 | 0.98 | 149.8333 | 0.98 | 149.8333 | 0.98 | 149.8333 | 0.98 | 149.8333 | 0.98 | 149.8333
Panna | 192.2 | 28 | 2100 | 0 | 634 | 0 | 30.1905 | 192.2 | 1466 | 32.0333 | 244.3333 | 32.0333 | 244.3333 | 32.0333 | 244.3333 | 32.0333 | 244.3333 | 32.0333 | 244.3333 | 32.0333 | 244.3333
Pawai | 81.56 | 14 | 2640 | 21.29 | 782 | 26.1035 | 29.6212 | 60.27 | 1858 | 10.045 | 309.6667 | 10.045 | 309.6667 | 10.045 | 309.6667 | 10.045 | 309.6667 | 10.045 | 309.6667 | 10.045 | 309.6667
Raisen | 223.695 | 62 | 3856 | 76.994 | 1414 | 34.4192 | 36.6701 | 146.701 | 2442 | 24.4502 | 407 | 24.4502 | 407 | 24.4502 | 407 | 24.4502 | 407 | 24.4502 | 407 | 24.4502 | 407
Biaora | 166.46 | 19 | 1200 | 68.8453 | 1411 | 41.3585 | 117.5833 | 97.6147 | -211 | 16.2691 | -35.1667 | 16.2691 | -35.1667 | 16.2691 | -35.1667 | 16.2691 | -35.1667 | 16.2691 | -35.1667 | 16.2691 | -35.1667
Ratlam-1 | 167.95 | 53 | 4698.13 | 28.222 | 1210 | 16.8038 | 25.7549 | 139.728 | 3488.13 | 23.288 | 581.355 | 23.288 | 581.355 | 23.288 | 581.355 | 23.288 | 581.355 | 23.288 | 581.355 | 23.288 | 581.355
Ratlam-2 | 253 | 45 | 4517 | 51.869 | 2108 | 20.5016 | 46.6681 | 201.131 | 2409 | 33.5218 | 401.5 | 33.5218 | 401.5 | 33.5218 | 401.5 | 33.5218 | 401.5 | 33.5218 | 401.5 | 33.5218 | 401.5
Mauganj | 126.93 | 28 | 2580 | 13.58 | 714 | 10.6988 | 27.6744 | 113.35 | 1866 | 18.8917 | 311 | 18.8917 | 311 | 18.8917 | 311 | 18.8917 | 311 | 18.8917 | 311 | 18.8917 | 311
Rewa-1 | 186.1 | 47 | 2900 | 45.607 | 1587 | 24.5067 | 54.7241 | 140.493 | 1313 | 23.4155 | 218.8333 | 23.4155 | 218.8333 | 23.4155 | 218.8333 | 23.4155 | 218.8333 | 23.4155 | 218.8333 | 23.4155 | 218.8333
Rewa-2 | 135.88 | 28 | 2881.27 | 12.85 | 944 | 9.4569 | 32.7633 | 123.03 | 1937.27 | 20.505 | 322.8783 | 20.505 | 322.8783 | 20.505 | 322.8783 | 20.505 | 322.8783 | 20.505 | 322.8783 | 20.505 | 322.8783
Sagar | 228.64 | 69 | 2975 | 32.453 | 1006 | 14.1939 | 33.8151 | 196.187 | 1969 | 32.6978 | 328.1667 | 32.6978 | 328.1667 | 32.6978 | 328.1667 | 32.6978 | 328.1667 | 32.6978 | 328.1667 | 32.6978 | 328.1667
Satna-03 | 173.035 | 43 | 3021.15 | 17.99 | 746 | 10.3967 | 24.6926 | 155.045 | 2275.15 | 25.8408 | 379.1917 | 25.8408 | 379.1917 | 25.8408 | 379.1917 | 25.8408 | 379.1917 | 25.8408 | 379.1917 | 25.8408 | 379.1917
Satna-1 | 75.11 | 20 | 2300 | 4.87 | 1200 | 6.4838 | 52.1739 | 70.24 | 1100 | 11.7067 | 183.3333 | 11.7067 | 183.3333 | 11.7067 | 183.3333 | 11.7067 | 183.3333 | 11.7067 | 183.3333 | 11.7067 | 183.3333
Satna-2 | 167.295 | 44 | 2804 | 20.082 | 265 | 12.0039 | 9.4508 | 147.213 | 2539 | 24.5355 | 423.1667 | 24.5355 | 423.1667 | 24.5355 | 423.1667 | 24.5355 | 423.1667 | 24.5355 | 423.1667 | 24.5355 | 423.1667
Sehore-I | 151.675 | 38 | 3600 | 26.28 | 1593 | 17.3265 | 44.25 | 125.395 | 2007 | 20.8992 | 334.5 | 20.8992 | 334.5 | 20.8992 | 334.5 | 20.8992 | 334.5 | 20.8992 | 334.5 | 20.8992 | 334.5
Sehore-II | 107.1 | 43 | 3700 | 0 | 1324 | 0 | 35.7838 | 107.1 | 2376 | 17.85 | 396 | 17.85 | 396 | 17.85 | 396 | 17.85 | 396 | 17.85 | 396 | 17.85 | 396
Seoni -3 | 19.06 | 5 | 910.89 | 6.114 | 628 | 32.0776 | 68.9436 | 12.946 | 282.89 | 2.1577 | 47.1483 | 2.1577 | 47.1483 | 2.1577 | 47.1483 | 2.1577 | 47.1483 | 2.1577 | 47.1483 | 2.1577 | 47.1483
Seoni-1 | 165.88 | 30 | 3100 | 29.3684 | 1009 | 17.7046 | 32.5484 | 136.5116 | 2091 | 22.7519 | 348.5 | 22.7519 | 348.5 | 22.7519 | 348.5 | 22.7519 | 348.5 | 22.7519 | 348.5 | 22.7519 | 348.5
Seoni-2 | 113.78 | 17 | 2777.07 | 17.805 | 772 | 15.6486 | 27.7991 | 95.975 | 2005.07 | 15.9958 | 334.1783 | 15.9958 | 334.1783 | 15.9958 | 334.1783 | 15.9958 | 334.1783 | 15.9958 | 334.1783 | 15.9958 | 334.1783
Seoni-4 | 241.72 | 60 | 3950 | 35.557 | 748 | 14.71 | 18.9367 | 206.163 | 3202 | 34.3605 | 533.6667 | 34.3605 | 533.6667 | 34.3605 | 533.6667 | 34.3605 | 533.6667 | 34.3605 | 533.6667 | 34.3605 | 533.6667
Seoni-5 | 219.94 | 38 | 4074.4 | 54.55 | 1225 | 24.8022 | 30.0658 | 165.39 | 2849.4 | 27.565 | 474.9 | 27.565 | 474.9 | 27.565 | 474.9 | 27.565 | 474.9 | 27.565 | 474.9 | 27.565 | 474.9
Shahdol-1 | 288.16 | 53 | 5000 | 25.043 | 1086 | 8.6907 | 21.72 | 263.117 | 3914 | 43.8528 | 652.3333 | 43.8528 | 652.3333 | 43.8528 | 652.3333 | 43.8528 | 652.3333 | 43.8528 | 652.3333 | 43.8528 | 652.3333
Shahdol-2 | 261.27 | 53 | 3600 | 22.5 | 1036 | 8.6118 | 28.7778 | 238.77 | 2564 | 39.795 | 427.3333 | 39.795 | 427.3333 | 39.795 | 427.3333 | 39.795 | 427.3333 | 39.795 | 427.3333 | 39.795 | 427.3333
Shajapur | 428.02 | 114 | 6780.27 | 28.9 | 2448 | 6.752 | 36.1048 | 399.12 | 4332.27 | 66.52 | 722.045 | 66.52 | 722.045 | 66.52 | 722.045 | 66.52 | 722.045 | 66.52 | 722.045 | 66.52 | 722.045
Sheopur | 138.91 | 31 | 2400 | 0 | 809 | 0 | 33.7083 | 138.91 | 1591 | 23.1517 | 265.1667 | 23.1517 | 265.1667 | 23.1517 | 265.1667 | 23.1517 | 265.1667 | 23.1517 | 265.1667 | 23.1517 | 265.1667
Shivpuri | 142.79 | 47 | 2650 | 44.857 | 948 | 31.4147 | 35.7736 | 97.933 | 1702 | 16.3222 | 283.6667 | 16.3222 | 283.6667 | 16.3222 | 283.6667 | 16.3222 | 283.6667 | 16.3222 | 283.6667 | 16.3222 | 283.6667
Sidhi-1 | 146.05 | 23 | 3573 | 4.9 | 1158 | 3.355 | 32.4097 | 141.15 | 2415 | 23.525 | 402.5 | 23.525 | 402.5 | 23.525 | 402.5 | 23.525 | 402.5 | 23.525 | 402.5 | 23.525 | 402.5
Sidhi-2 | 146.61 | 19 | 2834 | 29.435 | 1068 | 20.0771 | 37.6853 | 117.175 | 1766 | 19.5292 | 294.3333 | 19.5292 | 294.3333 | 19.5292 | 294.3333 | 19.5292 | 294.3333 | 19.5292 | 294.3333 | 19.5292 | 294.3333
Sidhi-3 | 253.28 | 29 | 5549.28 | 27.7 | 1049 | 10.9365 | 18.9034 | 225.58 | 4500.28 | 37.5967 | 750.0467 | 37.5967 | 750.0467 | 37.5967 | 750.0467 | 37.5967 | 750.0467 | 37.5967 | 750.0467 | 37.5967 | 750.0467
Sidhi-4 | 165.15 | 25 | 4318.16 | 1.71 | 931 | 1.0354 | 21.5601 | 163.44 | 3387.16 | 27.24 | 564.5267 | 27.24 | 564.5267 | 27.24 | 564.5267 | 27.24 | 564.5267 | 27.24 | 564.5267 | 27.24 | 564.5267
Waidhan-1 | 135.46 | 19 | 2514.2 | 23.785 | 1166 | 17.5587 | 46.3766 | 111.675 | 1348.2 | 18.6125 | 224.7 | 18.6125 | 224.7 | 18.6125 | 224.7 | 18.6125 | 224.7 | 18.6125 | 224.7 | 18.6125 | 224.7
Waidhan-2 | 106.18 | 13 | 2574.83 | 9.89 | 963 | 9.3144 | 37.4005 | 96.29 | 1611.83 | 16.0483 | 268.6383 | 16.0483 | 268.6383 | 16.0483 | 268.6383 | 16.0483 | 268.6383 | 16.0483 | 268.6383 | 16.0483 | 268.6383
Waidhan-3 | 147.1 | 22 | 2750.5 | 2.84 | 882 | 1.9307 | 32.0669 | 144.26 | 1868.5 | 24.0433 | 311.4167 | 24.0433 | 311.4167 | 24.0433 | 311.4167 | 24.0433 | 311.4167 | 24.0433 | 311.4167 | 24.0433 | 311.4167
Tikamgarh | 271.28 | 63 | 3578.95 | 87.25 | 1599 | 32.1623 | 44.6779 | 184.03 | 1979.95 | 30.6717 | 329.9917 | 30.6717 | 329.9917 | 30.6717 | 329.9917 | 30.6717 | 329.9917 | 30.6717 | 329.9917 | 30.6717 | 329.9917
Ujjain - 1 | 257.75 | 63 | 3554.58 | 45.764 | 1850 | 17.7552 | 52.0455 | 211.986 | 1704.58 | 35.331 | 284.0967 | 35.331 | 284.0967 | 35.331 | 284.0967 | 35.331 | 284.0967 | 35.331 | 284.0967 | 35.331 | 284.0967
Ujjain - 3 | 99.4 | 20 | 2200 | 6.075 | 802 | 6.1117 | 36.4545 | 93.325 | 1398 | 15.5542 | 233 | 15.5542 | 233 | 15.5542 | 233 | 15.5542 | 233 | 15.5542 | 233 | 15.5542 | 233
Ujjain-2 | 145.84 | 37 | 3327.83 | 3.152 | 836 | 2.1613 | 25.1215 | 142.688 | 2491.83 | 23.7813 | 415.305 | 23.7813 | 415.305 | 23.7813 | 415.305 | 23.7813 | 415.305 | 23.7813 | 415.305 | 23.7813 | 415.305
Umaria | 119.35 | 31 | 4817.71 | 2.25 | 993 | 1.8852 | 20.6115 | 117.1 | 3824.71 | 19.5167 | 637.4517 | 19.5167 | 637.4517 | 19.5167 | 637.4517 | 19.5167 | 637.4517 | 19.5167 | 637.4517 | 19.5167 | 637.4517
Vidisha | 123.41 | 34 | 2678 | 33.0091 | 1094 | 26.7475 | 40.8514 | 90.4009 | 1584 | 15.0668 | 264 | 15.0668 | 264 | 15.0668 | 264 | 15.0668 | 264 | 15.0668 | 264 | 15.0668 | 264
| 17570.915 | 4241 | 323951.2071 | 2402.7238 | 107728 | 13.6744 | 33.2544 | 15168.1912 | 216223.2071 | 2528.0319 | 36037.2012 | 2528.0319 | 36037.2012 | 2528.0319 | 36037.2012 | 2528.0319 | 36037.2012 | 2528.0319 | 36037.2012 | 2528.0319 | 36037.2012