## upto_31Aug09
Status on 14th Sep 2009
Difference of Progress in OMMS (upto 31st Aug 2009)
No. | Division | CGM | Districts | Physical Progress | [6 empty] | Financial Progress (Payment Made) in Lakhs
|  |  |  | completed roads on OMMS | Actual | Diff. | Completed length on OMMS | Actual | Diff. | Phy. Entry Status (Yes/NO) | Expenditure on OMMS | Actual | Diff. | Fin. Entry Status (Yes/NO)
1 | Rewa | IV | Anuppur | 143 | 146 | -3 | 570.53 | 577.33 | -6.8 |  | 13894.54 | 13894.538 | 0.00202
2 | Gwalior | I | Ashoknagar | 81 | 88 | -7 | 331.46 | 365.44 | -33.98 |  | 6784.54 | 5863.22 | 921.32
3 | Jabalpur | IV | Balaghat | 214 | 214 | 0 | 927.45 | 959.375 | -31.925 |  | 24878.92 | 24807.81 | 71.11
4 | Indore | III | Barwani | 148 | 138 | 10 | 624.53 | 577.476 | 47.054 |  | 19049.22 | 19669.69 | -620.47
5 | Bhopal | I | Betul | 224 | 216 | 8 | 1022.65 | 1028.022 | -5.372 |  | 28962.87 | 29090.9797 | -128.1097
6 | Gwalior | I | Bhind | 146 | 167 | -21 | 476.79 | 562.355 | -85.565 |  | 12110.34 | 12609.33 | -498.99
7 | Bhopal | II | Bhopal | 49 | 50 | -1 | 154.6 | 156.88 | -2.28 |  | 4726.19 | 6815.81 | -2089.62
8 | Indore | III | Burhanpur | 23 | 24 | -1 | 107.5 | 100.41 | 7.09 |  | 4078.75 | 4340.49 | -261.74
9 | Sagar | II | Chhatarpur | 212 | 210 | 2 | 831.98 | 834.9245 | -2.9445 |  | 19945.5 | 20001.914 | -56.414
10 | Jabalpur | IV | Chhindwara | 227 | 210 | 17 | 1111.01 | 1054.6123 | 56.3977 |  | 31788.23 | 31747.6104 | 40.6196
11 | Sagar | II | Damoh | 117 | 113 | 4 | 452.17 | 423.706 | 28.464 |  | 9279.12 | 9263.246 | 15.874
12 | Gwalior | I | Datia | 79 | 73 | 6 | 341.79 | 322.478 | 19.312 |  | 5021.78 | 6096.62 | -1074.84
13 | Ujjain | III | Dewas | 118 | 121 | -3 | 504.18 | 513.48 | -9.3 |  | 14614.33 | 14600.5793 | 13.7507
14 | Indore | III | Dhar | 254 | 267 | -13 | 1113.13 | 1250.635 | -137.505 |  | 29143.5 | 29353.19 | -209.69
15 | Jabalpur | IV | Dindori | 117 | 146 | -29 | 479.68 | 620.169 | -140.489 |  | 19180.54 | 19144.209 | 36.331
16 | Gwalior | I | Guna | 110 | 110 | 0 | 454.18 | 470.183 | -16.003 |  | 9192.4 | 9136.6 | 55.8
17 | Gwalior | I | Gwalior | 71 | 71 | 0 | 207.93 | 239.713 | -31.783 |  | 6370.38 | 6502.5106 | -132.1306
18 | Bhopal | I | Harda | 38 | 42 | -4 | 202.81 | 297.887 | -95.077 |  | 7592.14 | 7699.61 | -107.47
19 | Bhopal | I | Hoshangabad | 116 | 107 | 9 | 361.82 | 383.922 | -22.102 |  | 10373 | 10374.21 | -1.21
20 | Indore | III | Indore | 44 | 48 | -4 | 150.3 | 192.75 | -42.45 |  | 4262.69 | 4274.694 | -12.004
21 | Jabalpur | IV | Jabalpur | 107 | 95 | 12 | 393.65 | 388.553 | 5.097 |  | 9222.89 | 9151.152 | 71.738
22 | Indore | III | Jhabua | 196 | 206 | -10 | 785.16 | 848.0074 | -62.8474 |  | 27834.49 | 28472.2219 | -637.7319
23 | Jabalpur | IV | Katni | 112 | 107 | 5 | 448.08 | 431.579 | 16.501 |  | 11128.77 | 11145.35 | -16.58
24 | Indore | III | Khandwa | 92 | 87 | 5 | 376.85 | 346.73 | 30.12 |  | 10715.66 | 11559.3 | -843.64
25 | Indore | III | Khargone | 95 | 99 | -4 | 433.85 | 469.92 | -36.07 |  | 17285.47 | 16805.8057 | 479.6643
26 | Jabalpur | IV | Mandla | 252 | 241 | 11 | 1049.67 | 1065.282 | -15.612 |  | 22222.14 | 22231.61 | -9.47
27 | Ujjain | III | Mandsaur | 191 | 190 | 1 | 876.21 | 865.655 | 10.555 |  | 22546.63 | 22777.1 | -230.47
28 | Gwalior | I | Morena | 307 | 319 | -12 | 996.49 | 1145.57 | -149.08 |  | 22812.14 | 23029.94 | -217.8
29 | Jabalpur | IV | Narsinghpur | 85 | 94 | -9 | 343.13 | 374.49 | -31.36 |  | 9390.29 | 9370.379 | 19.911
30 | Ujjain | III | Neemuch | 64 | 64 | 0 | 319.38 | 313.15 | 6.23 |  | 7223.34 | 7222.22 | 1.12
31 | Sagar | II | Panna | 114 | 116 | -2 | 520.2 | 531.45 | -11.25 |  | 14432.67 | 14879.06 | -446.39
32 | Bhopal | II | Raisen | 74 | 79 | -5 | 425.87 | 474.45 | -48.58 |  | 11466.84 | 11418.173 | 48.667
33 | Bhopal | I | Rajgarh | 174 | 151 | 23 | 717.1 | 606.195 | 110.905 |  | 15074.12 | 15074.1154 | 0.0046
34 | Ujjain | III | Ratlam | 158 | 165 | -7 | 582.03 | 754.222 | -172.192 |  | 15460.11 | 14067.0898 | 1393.0202
35 | Rewa | IV | Rewa | 119 | 133 | -14 | 532.95 | 644.495 | -111.545 |  | 14864.74 | 16762.1371 | -1897.3971
36 | Sagar | II | Sagar | 183 | 192 | -9 | 789.01 | 806.108 | -17.098 |  | 15549.68 | 15633.57 | -83.89
37 | Rewa | IV | Satna | 163 | 166 | -3 | 598.73 | 604.13 | -5.4 |  | 15876.66 | 15804.6959 | 71.9641
38 | Bhopal | II | Sehore | 133 | 143 | -10 | 495.48 | 640.77 | -145.29 |  | 21014.52 | 20265.0931 | 749.4269
39 | Jabalpur | IV | Seoni | 326 | 303 | 23 | 1375.27 | 1285.61 | 89.66 |  | 33364.83 | 33385.701 | -20.871
40 | Gwalior | I | Seopur | 54 | 66 | -12 | 273.44 | 326.385 | -52.945 |  | 7145.92 | 7267.23 | -121.31
41 | Rewa | IV | Shahdol | 164 | 190 | -26 | 742.43 | 851.684 | -109.254 |  | 16912.49 | 16924.1889 | -11.6989
42 | Ujjain | III | Shajapur | 142 | 151 | -9 | 519.6 | 603.001 | -83.401 |  | 15565.78 | 15757.4356 | -191.6556
43 | Gwalior | I | Shivpuri * | 206 | 199 | 7 | 891.7 | 1052.845 | -161.145 |  | 18485.32 | 18342.6 | 142.72
44 | Rewa | IV | Sidhi | 176 | 187 | -11 | 1002.84 | 1104.03 | -101.19 |  | 36187.41 | 36200.7122 | -13.3022
45 | Sagar | II | Tikamgarh | 175 | 173 | 2 | 666.39 | 671.402 | -5.012 |  | 14023.93 | 14022.109 | 1.821
46 | Ujjain | III | Ujjain | 107 | 123 | -16 | 461.6 | 553.823 | -92.223 |  | 17605.78 | 17251.4335 | 354.3465
47 | Rewa | IV | Umria | 69 | 72 | -3 | 363.84 | 373.606 | -9.766 |  | 8872.35 | 8968.1227 | -95.7727
48 | Bhopal | II | Vidisha | 119 | 105 | 14 | 596.05 | 550.305 | 45.745 |  | 12909.85 | 13024.7 | -114.85
|  |  |  | 6688 | 6777 | -89 | 28003.49 | 29615.1952 | -1611.7052 |  | 746443.8 | 752100.1068 | -5656.3068