## Agenda-2
Agenda-2
Detail Review of Roads having major Dispute
Sno | CGM | District | Block | PIU | Package No. | Phase/Batch | Name of Road in dispute | Type of Disput |  |  | Detail brief of dispute road | Approx time in months to resolve the dispute | Remarks
[8 empty] | Land Disput | Forest
[9 empty] | Pending at GM level | Pending at Forest Department Level
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Agenda 3
Agenda No |  | 3
Detailed review of incomplete works of Phase-II to Phase-VIII and ADB batch-I to IV and plan for their completion by December 11
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Date of work order | Name of road | Total |  | Balance |  | Physical Status- Approx. balance work in Kms / nos | [6 empty] | Total expenditure upto the reporting month | Work done in last 4 Months Rs in Lakhs | Reason in brief for not completing | Target date of completion Apr/ May/ Jun / Jul/Aug/Sep/Oct/Nov/Dec/Jan/Feb/Mar | Remarks
[10 empty] | Length | Cost | Length | Cost | E/W | GSB | G-2 | G-3 | BT | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [6 empty] | 16 | 17 | 18 | 19 | 20

## Agenda-4
Agenda No |  | 4
Road wise Program for construction of sanctioned works under IAP District
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Road | Date of work order | Total |  | Month wise program of Road Works | [9 empty] | Total Expenditure till reporting month | Remarks
[9 empty] | Length | Cost | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23

## Agenda 5
Agenda -5
Preparation of DPR's of IAP District
S.N. | Name of District | Name of PIU | Name of Block | DPR already prepared in old pattern |  | Revised DPR in New Final Template |  | Balance DPR to be revised in New Final Template col. (5-7) & col (6-8) |  | Preparation of New DPR having population 250 to 499 in General block of IAP District |  | TOTAL BALANCE DPR in IAP District
|  |  |  | No. of road | Length of Road in km | No. of road | Length of Road in km | No. of road col. 5-7 | Length of Road in km col 6-8 | No. of road | Length of Road in km | No. of road | Length of Road in km
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Agenda 6
Agenda No : 6
Review & Program for completion of roads of Bharat Nirman Habitation upto Dec-11
S.N. | CGM (I,II,III, IV) | District | PIU Name | Name of packages | Name of Road | No of Habitation to be benefited |  |  | Proposed to be completed in month /year
[6 empty] | 1000+ | 500+ | other
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Agenda 7
Agenda No |  | 7
Road wise Program for construction of Incomplete Roads of PMGSY Phase IX,X (upgradation) Batch V & LWE
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Road | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Total |  | Balance |  | Physical Status- Approx. balance work in Kms / nos | [6 empty] | Schedule Date of Completion | Target date of completion | Monthwise programme for completion (Length in Kms) | [11 empty] | Remarks
[11 empty] | Length | Cost | Length | Cost | E/W | GSB | G-2 | G-3 | BT | CC road | CD |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | [6 empty] | 17 | 18 | Monthwise programme for completion (Length in Kms) Apr: 19 | 20

## Agenda-8
Agenda No |  | 8
Progress of Bridges under construction
Length in Meters & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Total |  |  |  | Approx. balance work in Mts / nos/Lakhs |  |  |  | Schedule Date of Completion | Target date of completion | Quarterly programme for completion (Only Rs in Lakhs) |  |  |  | Remarks
[12 empty] | Length of both approaches | No of Spans | No of Piers | Cost | Length of both approaches | No of Spans | No of Piers | Cost |  |  | Apr to Jun | Jul to Sep | Oct to Dec | Jan to Mar
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |  |  | 14 |  |  |  | 15 | 16 | 17 |  |  |  | 18

## Agenda- 9
Agenda-9
Review of Status of Payment of Final Bills for the completed packages
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Sanctioned Amount | Expenditure Made (Up to the month) | Date of WO | Date of Completion | Date of issue Completion Certificate by the Consultant | Date of Final Payment Made by GM | Date of Verification by GM | Delay in months in final payment
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Agenda 10
Agenda 10
Review of un-awarded packages of construction work including balance work
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Sanctioned Amount | Expenditure Made (Up to Mar11) | Amount of balance work | No fo calls (for tender) | NIT issued yes / no | If Yes then date of opening of bid | If No, then reason for non issuing of NIT | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Agenda 11 a
Agenda 11 (a)
Maintenance works : Information of expenditure for packages within 5 years
Length in Kms & Cost in Rs Lakhs
S. No | Name of Dist. | Name of PIU | Phase | Package No. | Completion date (mm-dd-yyyy) | Maintenance start date (mm-dd-yyyy) | Completed Roads under Five Year Maintenance |  | Maintenance Funding and Expenditure during the last financial year (upto 31.03.11) |  | Maintenance Funding and Expenditure during the current financial year ( 2011-2012) Rs. .in LAKH |  |  | Amount to be paid as per contract provision during next financial year 2012-13 | Maintenance ongoing /completed (Yes / No)
[7 empty] | Name of road | Length | Funds Required (in Lakhs) as per contract provision upto 31.03.11 | Expenditure (in Lakhs) upto 31.03.11 | Funds Required for the current year as per contract provision i.e. for 2011-12 | cumulative Expenditure upto last month (for current financial year 2010-11) | cumulative Expenditure upto this month (for current financial year 2010-11)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16

## Agenda 11 b
Agenda 11 (b)
Maintenance works : Information of expenditure for packages beyond 5 years
Length in Kms & Cost in Rs Lakhs
[12 empty] | Part -I |  |  |  | Part-II |  |  | Part-III |  |  |  |  | Part-IV
Name of District | Name of PIU | Road no. | Const pkg No. | Maint Pkg No | Name of road | Length of road | PAC for MTN Pkgs | Tender Percentage (only in figure) | Name of Cont. | Date of work order (dd-mm-yyyy) | Total Cumulative amount paid during last financial year | Total Amt of Part-I (as per contract) | cumulative Amount paid upto last month | cumulative Amount paid upto current month | Date of completion of part-I (dd-mm-yyyy) | Total Amount for part II (as per contract) | cumulative Amount paid upto last month | cumulative Amountpaid upto current month | Total Amount for Part III (as per contract) | Target Length to be renewed | Achieved Length renewed | cumulative Amount paid upto last month | cumulative Amount paid upto current month | Total Amount for Part IV (as per contract) | Fin. (amount paid during the month) | Total amount paid for Part-IV | Upto date total amount paid for Part-I+II+III+IV
[13 empty] | Payment made |  |  | Pay. Which was due to be paid | Payment made |  |  |  |  | Payment made
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
|  | 101 |  | MTN-001 |  |  |  | -5.2 |  | 2010-03-13 |  |  |  |  | 2010-07-10
|  | 102 |  | MTN-001 |  |  |  | 5.2 |  | 2010-03-13 |  |  |  |  | 2010-05-02
|  | 103 |  | MTN-001 | [5 empty] | 2010-03-13 |  |  |  |  | 2010-08-06
|  | 201 |  | MTN-002 | [5 empty] | 2010-05-18 |  |  |  |  | 2010-08-20
|  | 202 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 203 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 204 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 301 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 302 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 303 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 304 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 305 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 306 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 307 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 308 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 309 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 310 |  | MTN-003 | [5 empty] | 2010-06-20
1) Information to be submitted in Excel format only
2) No addition/reduction in col. Should be made
3) Expenditure should be in lacs only.
4) In case of NIL entry zero entry should be made
5) In column no. 1, entered only road no. (like example) it will remain fixed for road name.
6) Column no. 9 & 14 should be in date format only.

## Agenda 11 c
Agenda 11 C
Un-awarded tenders of maintenance works
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MTN | No of Roads in the Package | Expiry Date of 5 years guarantee period | Total Amount of maintenace pkg | date of NIT | No fo calls (for tender) | NIT issued yes / no | If Yes then date of opening of bid | If No, then reason for non issuing of NIT | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Agenda 11 d
Agenda | 11 d
Remaining packages for tendering for maintenance - upto Dec-11
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Packages which are becoming due for maintenance after 5 year guarantee period - upto Dec 10 / Mar 11/ Jun 11 (Specify) | Phase / Batch of contruction package | Const pkg No. MP- | Name of Roads in the Package | Length of road | Date of completion of package | Expiry date of guarantee period | status of Submission of Proposal | Status of TS to maintenance estimate | Remarks | 1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  |  | 12

## Agenda-12
Agenda point -12
Complaince on NQM reports & ATRs
S.No | District | Name of PIU | Name of NQM | Date of Inspection | Name of Road | SRI / U | Main points for ATR - in very brief | Latest position of ATR | Ref. no & date of sending ATR to Head Office Bhopal
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Agenda-13
Agenda 13
Review of Deviation/Change of alignment/Extra items/pending / pending with HO.
Sno | District | PIU | Type of Case Deviation/ Change of alignment/ Extra item/ crust revision /Other | Name of Package | Name of road | Sent to HQ/CGM office vide letter |  |  | Any querry from HQ - Yes/ No | If Yes, then |  | Present status of the case | Period of Compliance (in month only 5,6,7)
[6 empty] | Head office/ CGM office | No | Date |  | querry points in very very brief | Date by which the compliance will be submitted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Agenda-14
Agenda 14
OMMS Entry for Physical & Financial Works

## Agenda -15
Agenda 15
Status of GIS data verification & updation
S. No. | CGM | Name of District | Name of PIU | Name & post of nodal person for GIS data verification/ Updation | GIS data verified - Yes/ No | If no, then date on which verification is scheduled | GIS data updated Yes / No | If yes, GIS data updated up to the month of | If No, date by which data upto Mar 10 will be updated | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11

## Agenda-16
Agenda point -16
Information of verification of Bank Guarantees
S.No. | CGM | Name of District | Name of PIU | Package No. | Name Of Contractor | latest B.G.No | Date | Amount in Rs Lakhs | Validity till date | Name of the Bank & Branch | Place | Purpose of bank guarantee in brief | Remark
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
* | Amount should be Rs. in lakh only

## Agenda-17
Agenda point -17
Pending AG Audit Para compliance
S.No. | CGM | Name of District | Name of PIU | Pending audit para no | Audit for the period | Compliance sent vide no & date | Remark
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8

## Agenda18 E-1
Agenda point -18 | [13 empty] | Format- E 1
Staff position As on 31.03.11
Sno | CGM | Name of District | PIU | Post in MPRRDA | Sanctioned Post | Inplace | Vacant | On deputation/ Contract | If on contract, appointment done by HQ or PIU | Due Date of renewal of contract (Samvida) dd/mm/yy | Name | Category Gen/SC/ ST/OBC | Home District | Parent Department | Post held in Parent Deptt. | Date since when working in MPRRDA dd/mm/yy | Date since when working in the PIU dd/mm/yy | Date of Birth dd/mm/yy | Date of Retirement dd/mm/yy | Present Pay Scale/ Samvida Pay | Present Basic Pay/ Samvida pay | If worked in any other PIU, name of PIU/Distt | If any disciplinary action (SCN/ DE etc) is pending give brief detail | If any application for transfer is pending give brief detail | Mobil No./Phone No. | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
GM
AM
AO
S/E
DM
ADM
Steno
Accountant
AG-I
AG-II
AG-III
DEO
Peon
Lab Asstt.
Lab Helper
* | Note : | Post should be written only as given above : | bar: 16 to 19

## Agenda -19
Agenda point -19
Updated information As on 31.03.11
Position of CRs of GMs, AMs & S/Es for the year ending Mar 2011
Sno | Name of employee | Post in MPRRDA | Parent deptt | Post in parent deptt | Period of CR | Name & post of officer who has written CR | CR sent to whom | Sent vide no & Date | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Agenda 20 CTE(V)
Agenda-20
Review of cases of CTE (V)
Sno | Distt | PIU | CTE Case no (include year) | Name of road inspected | Date of inspection | First reply sent vide Letter No & date | Present status | Pending with PIU/ CGM/ HQ | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Addl Agenda 1
Agenda |  | 20
Review of Administrative Expenditure
Length in Kms & Cost in Rs Lakhs
S.No. | CGM | Name of District | Name of PIU | During 10-11 | [5 empty] | Remark
|  |  |  | Expenditure incurred on Works | Expenditure incurred on pay & allowances | Expenditure incurred on vehicle | Expenditure incurred on Stationery & office contingency | Expenditure incurred on consultancy | Expenditure incurred on misc items
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
* |  |  | Amount should be Rs. in lakh only

## Addl Agenda-2
Agenda | 14
Review of Department Enquiery
(information only by CGM)