## Agenda 1
Agenda no. 1
Target & Achievement of Physical & Financial works
S.N. | CGM (I,II,III, IV) | District | PIU Name | Target for the year 2011-12 |  | Achievement for the year 2011-12 |  | % of Achievement
|  |  |  | Length in km | Amount rs. In lakh | Length in km | Amount rs. In lakh | Physical | Financial

## Agenda 2
Agenda No : 2
Review & Program for completion of roads of Bharat Nirman Habitation upto Mar-12
S.N. | CGM (I,II,III, IV) | District | PIU Name | Name of packages | Name of Road | No of Habitation to be benefited |  |  | Proposed to be completed in month /year
[6 empty] | 1000+ | 500+ | other
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Agenda 3
Agenda No |  | 3
Detailed review of incomplete works of Phase-III to Phase-VIII and ADB batch-I to IV and plan for their completion by
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) & E-in-C | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Date of work order | Name of road | Total |  | Balance |  | Physical Status- Approx. balance work in Kms / nos | [6 empty] | Total expenditure upto the reporting month | Work done in last 4 Months Rs in Lakhs | Reason in brief for not completing | Target date of completion Apr/ May/ Jun / Jul/Aug/Sep/Oct/Nov/Dec/Jan/Feb/Mar | Remarks
[10 empty] | Length | Cost | Length | Cost | E/W | GSB | G-2 | G-3 | BT | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [6 empty] | 16 | 17 | 18 | 19 | 20

## Agenda 4
Agenda No |  | 4
Road wise programme for Phase-IX to X and ADB Batch -5 & LWE works and their planning for completion
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) & E-in-C | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Date of work order | Name of road | Total |  | Balance |  | Physical Status- Approx. balance work in Kms / nos | [6 empty] | Total expenditure upto the reporting month | Planning for Next month wise | [5 empty] | Work done in last 4 Months Rs in Lakhs | Reason in brief for not completing | Target date of completion Apr/ May/ Jun / Jul/Aug/Sep/Oct/Nov/Dec/Jan/Feb/Mar | Remarks
[10 empty] | Length | Cost | Length | Cost | E/W | GSB | G-2 | G-3 | BT | CC road | CD |  | Oct | Nov | Dec | Jan | Feb | Mar
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [6 empty] | 16 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32

## Agenda 5 a
Agenda No. 5a
Physical and Financial Progress of IAP Roads (District committee)
Financial Year - 2011-2012
Format- IAP 1
S. No. | District | Package no. | Work order No. & Date | Name of Raod | Length (in km) | Construction Cost (Rs. In lakh) | Maintanance Cost (Rs. In lakh) | Cost of AA (Rs. In lakh) | Up to June 2011 (Ist QTR) |  | Iind QTR | [5 empty] | Remark
[11 empty] | 2011-07-01 |  | 2011-08-01 |  | 2011-09-01
[9 empty] | Financial Progress (expenditure in Lakh) | Physical Progress (in km) | Financial Progress (expenditure in Lakh) | Physical Progress (in km) | Financial Progress (expenditure in Lakh) | Physical Progress (in km) | Financial Progress (expenditure in Lakh) | Physical Progress (in km)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1

## Agenda 5 b
Agenda No. 5b
Physical and Financial Progress of IAP Bridges (District committee)
Financial Year - 2011-2012
Format- IAP 2
S. No. | District | Package no. | Work order No. & Date | Name of Bridge | No. of Bridges | Construction Cost (Rs. In lakh) | Maintanance Cost (Rs. In lakh) | Cost of AA (Rs. In lakh) | Up to June 2011 (Ist QTR) |  | IInd QTR | [5 empty] | Remark
[11 empty] | 2011-07-01 |  | 2011-08-01 |  | 2011-09-01
[9 empty] | Financial Progress (expenditure in Lakh) | Physical Progress | Financial Progress (expenditure in Lakh) | Physical Progress | Financial Progress (expenditure in Lakh) | Physical Progress | Financial Progress (expenditure in Lakh) | Physical Progress
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Note: | If tender not receive then give note on remark coloum

## Agenda-6
Agenda No |  | 6
Progress of Bridges under construction
Length in Meters & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Total |  |  |  | Approx. balance work in Mts / nos/Lakhs |  |  |  | Total Expenditure done upto date | Schedule Date of Completion | Target date of completion | Quarterly programme for completion (Only Rs in Lakhs) |  |  |  | Remarks
[11 empty] | Length of both approaches | No of Spans | No of Piers | Cost | Length of both approaches | No of Spans | No of Piers | Cost |  |  |  | Apr to Jun | Jul to Sep | Oct to Dec | Jan to Mar
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 |  |  |  | 14 |  |  |  | 15 | 16 | 17 | 18 |  |  |  | 19

## Agenda-7
Ageda no. 7
Detail review of Deleted/Proposed for delete road / part deleted
Sno | CGM | District | Block | PIU | Package No. | Phase/Batch | Name of deleted / proposed for delete road Road | Reason in brief for deletion of the road | (If deleted) no. & date of approval for deletion | Details of road | [5 empty] | Reason for deletion of the road
[10 empty] | Sanctioned length in Kms | Constructed length in Kms | Length of road deleted in Kms | Sanctioned Amount of road in Rs Lakhs | Payment made in Rs Lakhs | Balance Amount in RS Lakhs
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17

## Agenda- 8
Agenda-9
Review of Status of Payment of Final Bills for the completed packages
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Sanctioned Amount | Expenditure Made (Up to the month) | Date of WO | Date of Completion | Date of issue Completion Certificate by the Consultant | Date of Final Payment Made by GM | Date of Verification by GM | Delay in months in final payment (in no. 5/8/12/16)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Agenda 9
Agenda 9
Review of un-awarded packages of construction work including balance work
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Sanctioned Amount | Expenditure Made (Up to Mar11) | Expenditure Made (Up to Sep11) | Amount of balance work | No fo calls (for tender) | NIT issued yes / no | If Yes then date of opening of bid | If No, then reason for non issuing of NIT | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16

## Agenda 10 a
Agenda 10 (a)
Maintenance works : Information of expenditure for packages within 5 years
Length in Kms & Cost in Rs Lakhs
S. No | Name of Dist. | Name of PIU | Phase | Package No. | Completion date (mm-dd-yyyy) | Maintenance start date (mm-dd-yyyy) | Completed Roads under Five Year Maintenance |  | Maintenance Funding and Expenditure during the last financial year (upto 31.03.11) |  | Maintenance Funding and Expenditure during the current financial year ( 2011-2012) Rs. .in LAKH |  |  | Amount to be paid as per contract provision during next financial year 2012-13 | Maintenance ongoing /completed (Yes / No)
[7 empty] | Name of road | Length | Funds Required (in Lakhs) as per contract provision upto 31.03.11 | Expenditure (in Lakhs) upto 31.03.11 | Funds Required for the current year as per contract provision i.e. for 2011-12 | cumulative Expenditure upto last month (for current financial year 2010-11) | cumulative Expenditure upto this month (for current financial year 2010-11)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16

## Agenda 10 b
Agenda 10 (b)
Maintenance works : Information of expenditure for packages beyond 5 years
Length in Kms & Cost in Rs Lakhs
[12 empty] | Part -I |  |  |  | Part-II |  |  | Part-III |  |  |  |  | Part-IV
Name of District | Name of PIU | Road no. | Const pkg No. | Maint Pkg No | Name of road | Length of road | PAC for MTN Pkgs | Tender Percentage (only in figure) | Name of Cont. | Date of work order (dd-mm-yyyy) | Total Cumulative amount paid during last financial year | Total Amt of Part-I (as per contract) | cumulative Amount paid upto last month | cumulative Amount paid upto current month | Date of completion of part-I (dd-mm-yyyy) | Total Amount for part II (as per contract) | cumulative Amount paid upto last month | cumulative Amountpaid upto current month | Total Amount for Part III (as per contract) | Target Length to be renewed | Achieved Length renewed | cumulative Amount paid upto last month | cumulative Amount paid upto current month | Total Amount for Part IV (as per contract) | Fin. (amount paid during the month) | Total amount paid for Part-IV | Upto date total amount paid for Part-I+II+III+IV
[13 empty] | Payment made |  |  | Pay. Which was due to be paid | Payment made |  |  |  |  | Payment made
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
|  | 101 |  | MTN-001 |  |  |  | -5.2 |  | 2010-03-13 |  |  |  |  | 2010-07-10
|  | 102 |  | MTN-001 |  |  |  | 5.2 |  | 2010-03-13 |  |  |  |  | 2010-05-02
|  | 103 |  | MTN-001 | [5 empty] | 2010-03-13 |  |  |  |  | 2010-08-06
|  | 201 |  | MTN-002 | [5 empty] | 2010-05-18 |  |  |  |  | 2010-08-20
|  | 202 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 203 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 204 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 301 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 302 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 303 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 304 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 305 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 306 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 307 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 308 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 309 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 310 |  | MTN-003 | [5 empty] | 2010-06-20
1) Information to be submitted in Excel format only
2) No addition/reduction in col. Should be made
3) Expenditure should be in lacs only.
4) In case of NIL entry zero entry should be made
5) In column no. 1, entered only road no. (like example) it will remain fixed for road name.
6) Column no. 9 & 14 should be in date format only.

## Agenda 10 c
Agenda 10 C
Un-awarded tenders of maintenance works
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MTN | No of Roads in the Package | Expiry Date of 5 years guarantee period | Total Amount of maintenace pkg | date of NIT | No fo calls (for tender) | NIT issued yes / no | If Yes then date of opening of bid | If No, then reason for non issuing of NIT | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Agenda 10d
Agenda | 10d
Remaining packages for tendering for maintenance - upto March-12
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Packages which are becoming due for maintenance after 5 year guarantee period - upto Dec 10 / Mar 11/ Jun 11 (Specify) | Phase / Batch of contruction package | Const pkg No. MP- | Name of Roads in the Package | Length of road | Date of completion of package | Expiry date of guarantee period | status of Submission of Proposal | Status of TS to maintenance estimate | Remarks | 1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Agenda-11
Agenda point -11
Complaince on NQM reports & ATRs
S.No | District | Name of PIU | Name of NQM | Date of Inspection | Name of Road | SRI / U | Main points for ATR - in very brief | Latest position of ATR | Ref. no & date of sending ATR to Head Office Bhopal
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Agenda-12
Agenda point -12
ATR of inspection of CEO/E-in-C/CGM
S.No | District | Name of PIU | Name of Officers CEO/ENC/CGM-1,CGM-2,CGM-3,CGM-4,CGM-5,CGM-6 | Date of Inspection | Name of Road | SRI / U | Main points for ATR - in very brief | Latest position of ATR | Ref. no & date of sending ATR to Head Office Bhopal
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Agenda-13
Agenda 13
Review of Deviation/Change of alignment/Extra items/pending / pending with HO.
Sno | District | PIU | Type of Case Deviation/ Change of alignment/ Extra item/ crust revision /Other | Name of Package | Name of road | Sent to HQ/CGM office vide letter |  |  | Any querry from HQ - Yes/ No | If Yes, then |  | Present status of the case | Period of Compliance (in month only 5,6,7)
[6 empty] | Head office/ CGM office | No | Date |  | querry points in very very brief | Date by which the compliance will be submitted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Agenda-14
Agenda 14
OMMS Entry for Physical & Financial Works

## Agenda -15
Agenda 15
Status of GIS data verification & updation
S. No. | CGM | Name of District | Name of PIU | Name & post of nodal person for GIS data verification/ Updation | GIS data verified - Yes/ No | If no, then date on which verification is scheduled | GIS data updated Yes / No | If yes, GIS data updated up to the month of | If No, date by which data upto Mar 10 will be updated | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11

## Agenda -16
Agenda 16
Mining Forest Electric pole
S. No. | CGM | Name of District | Name of PIU | Pending Forest cases |  |  |  |  | PendingMining | Electric pole shifting |  |  |  | Remarks
|  |  |  | National Parks | Forest conservation act 1980 | Cancelled case of which permission was given earlier | Other cases | Total |  | Total no of cases | No of cases in which agency fixed | No of cases where work executed | No of cases where work is in progress
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Agenda-17
Agenda point -17
Information of verification of Bank Guarantees
S.No. | CGM | Name of District | Name of PIU | Package No. | Name Of Contractor | latest B.G.No | Date | Amount in Rs Lakhs | Validity till date | Name of the Bank & Branch | Place | Purpose of bank guarantee in brief | Remark
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
* | Amount should be Rs. in lakh only

## Agenda-18
Agenda point -18
Recovery of amount in terminated packages
Length in Kms & Cost in Rs Lakhs
S.no. | CGM | District | PIU | Package No. | Name of Contractor | Date of termination of contract | Total Amount to be recovered in Rs. Lakhs | [5 empty] | Amount of SD of the contractor has been forfeited-Yes/No | If col. 14 is No, Reason thereof in very brief | Amount available in SD and other deposit/ final bill | Balance to be recovered from contractor (13-16) | Action taken for recovery | Does the penalty for the package has been decided from HO-Yes/No | Remarks
[7 empty] | Negative bill amount | Liquidated Damage (LD) amount | Amount of SD Deposit | Extra Cost | Other | Total (8+9+10+11)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
* | Amount should be Rs. in lakh only

## Agenda19 E-1
Agenda point -19 | [13 empty] | Format- E 1
Staff position As on 31.03.11
Sno | CGM | Name of District | PIU | Post in MPRRDA | Sanctioned Post | Inplace | Vacant | On deputation/ Contract | If on contract, appointment done by HQ or PIU | Due Date of renewal of contract (Samvida) dd/mm/yy | Name | Category Gen/SC/ ST/OBC | Home District | Parent Department | Post held in Parent Deptt. | Date since when working in MPRRDA dd/mm/yy | Date since when working in the PIU dd/mm/yy | Date of Birth dd/mm/yy | Date of Retirement dd/mm/yy | Present Pay Scale/ Samvida Pay | Present Basic Pay/ Samvida pay | If worked in any other PIU, name of PIU/Distt | If any disciplinary action (SCN/ DE etc) is pending give brief detail | If any application for transfer is pending give brief detail | Mobil No./Phone No. | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
GM
AM
AO
S/E
DM
ADM
Steno
Accountant
AG-I
AG-II
AG-III
DEO
Peon
Lab Asstt.
Lab Helper
* | Note : | Post should be written only as given above : | bar: 16 to 19

## Agenda 19 E-2
Agenda No. 19 E-2
Format-E 2
Updated information As on 30-9-2011
Incumbency Statement of GM/AO/AM/Sub Engineer/DM/ADM/Clerk/DEO
Since start of PIU Present (ih-vkbZ-;w- ds izkjaHk ls vkt rd)
S.No. | CGM | Name of District | PIU | Post in MPRRDA | Name of employee | Posted in PIU : Date |  | Parent Deptt. | Remarks
[6 empty] | From | To
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Agenda 20 CTE(V)
Agenda-20
Review of cases of CTE (V)
Sno | Distt | PIU | CTE Case no (include year) | Name of road inspected | Date of inspection | First reply sent vide Letter No & date | Present status | Pending with PIU/ CGM/ HQ | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10