## Sheet1
Format TL 1
Month: |  | PIU:
Contractor | Package No. | Cost (Lakhs) | No. of roads |  |  | Length (Kms) | Date of work order | Stipulated date of completion | Date of completion | If incomplete likely date of completion
|  |  | C | I | T
Total
C- Completed, I - Incomplete, T-Total

## Sheet2
Format TL 2
Technical staff of contractor
Month:
Technical Staff | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor
| Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no.
| Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed
Project Engineer
Asst. Project Engineer
Material Engineer
Asst. Material Engineer
Lab Technician
Field Engineer
Others (Pls specify)
Deployment of machinery by contractor
Equipment | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor |  | Name of Contractor
| Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no.
| Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed

## Sheet3
Format TL 3
Milestones to be achieved (in financial terms)
Month: April, 04
Package No. | Date of work order | Months passed since work order | % Achievement as on date | 1st Quarter | 2nd Qaurter | 3rd Quarter | 4th Quarter
Example | 12.03.04 | 1 | 1.2% | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%
|  |  |  | 12.5% | 37.5% | 75% | 100%

## Sheet4
Format TL 4
Status of work
Month: PIU:
Items
| Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No.
| Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms) | Total Length (Kms) | Balance Length (Kms)
Earthwork
GSB
WBM GII
WBM GIII
Hard shoulder
BT work
CD works (Nos.)
Financial Progress (In Lakhs)
Items | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No. |  | Package No.
A. Work plan for the month
B. Progress achieved (Cumulative)
C. Progress till previous month (Cumulative)
D. Progress in this month

## Sheet5
Format TL 5
Technical staff of consultant
Month:
Technical Staff | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no. |  | Package no.
| Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed | Required | Deployed
TL
ARE
AME
FE
RE
Others (Pls specify)

## Sheet6
Format TL 6
Name of Road: |  |  |  | District |  |  |  | PAC including tender %
Package No. |  |  |  | Length as per DPR
Block: |  |  |  | Actual length
PAC: |  |  |  | Above/Below percentage
|  |  | As per DPR |  |  | As paid |  |  | Variation
S.No. | SOR No. | Particulars | Quantity | Rate | Amount | Quantity | Rate | Amount | Saving | Excess
Jungle clearance
Earthwork
Ghat cutting
Select soil
Hard shoulder
GSB
G 2
G 3
CC road
Prime coat
Tack coat
Seal coat
OPGC
MPM/BM
MSS
CD work
Others if any (Pls Specify)