## Ag 1
Agenda No |  | 1
Review & Program for completion of roads of Bharat Nirman Habitation upto Mar 11
S.N. | CGM (I,II,III, IV) | District | PIU Name | Name of packages | Name of Road | No of Habitation to be benefited |  |  | Proposed to be completed in month /year
[6 empty] | 1000+ | 500+ | other
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Ag 2
Agenda No |  | 2
Review of PIU wise, Month wise Financial & Physical Progress
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III, IV) | District | PIU Name | Name of GM | Target 2010-11 |  | Target 2010-11 (till Jan-11) |  | Balance work as on 1.4.10 |  |  | New sanction received after 1.4.10 till now |  |  | Progress during Year 10-11
[5 empty] | Amount | Length | Amount | Length | No of roads | Length of road | Amount | No of roads | Length of road | Amount | 2010-04-01 |  |  | 2010-05-01 |  |  | 2010-06-01 |  |  | 2010-07-01 |  |  | 2010-08-01 |  |  | 2010-09-01 |  |  | 2010-10-01 |  |  | 2010-11-01 |  |  | 2010-12-01 |  |  | 2011-01-01 |  |  | Total of Year 10-11
[15 empty] | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure | No of roads completed | Length of road completed | Expenditure
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48

## Ag 3
Agenda No |  | 3
Roadwise Review of Incomplete Roads of All phases & ADB Batch I, II, III, IV ( Except resigned packages)
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Name of road | Total |  | Balance |  | Physical Status- Approx. balance work in Kms / nos | [6 empty] | Expenditure made in the last month | Total expenditure upto the reporting month Jan-11 | Work done in last 4 Months Rs in Lakhs | Reason in brief for not completing | Target for completion Month/Year | Remarks
[12 empty] | Length | Cost | Length | Cost | E/W | GSB | G-2 | G-3 | BT | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | [6 empty] | 18 | 19 | 20 | 21 | 22 | 23

## Ag 4
Agenda | 4
Status of terminated (resigned) packages – calling NIT, fixing agency, plan to complete these resigned packages
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Name of contractor | Date of termination of package | Sanctioned Amount of package | Expenditure Made (Up to date) Jan-11 | Amount of balance work | NIT issued yes / no | If Yes then date of opening of bid | If No, then reason for non issuing of NIT | Planned to be completed in month of | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17

## Ag 5
Agenda |  | 5
Review of packages completed but CC not issued, CC issued but final bill not paid
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Sanctioned Amount | Expenditure Made (Up to date) Jan-2011 | Date of Work order | Date of Completion | Date of issue Completion Certificate | If CC not issued, give reason | Date of Final Payment Made by GM | If final payment not made, give reason | Date of Verification by GM | Delay in months in final payment
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17

## Ag 6
Agenda |  | 6
PIU wise Balance Workload as on 31.01.2011
Rs in Lakhs
Length in Kms
S. no | CGM | Division | Name of PIU | Name of District | Name of Block | Name of Assembly Constituency | Phase / Batch | Name of Package | Name of Contractor | Name of Consultant | Total Nos of roads | No of incomplete roads | Total Length in Kms | Length of incompleted roads in Kms | Total Cost in Rs Lakhs | Tender % +/ - | Cost in Rs Lakhs including tender % | Expenditure made upto 31.01.11 in Rs Lakhs | Balance Cost in Rs Lakhs (Col 18-col 19) | Approx. Excess/ Saving (Give saving amount as minus) | Approx. Cost of balance work (after including excess or saving if any) Rs Lakhs (Col 20+col 21) | Status of pacakge as on 31.01.2011 ( Complete/ Incomlete/ Complete but payment to be made) | Name of Present incharge AM | Name of Present incharge S/E | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26

## 7a
MPR-1(Maintenance)
Monthly Reporting Format for Maintenance Funding during the year as per Standard Bidding Document
(For within five years roads)
S. No | Name of Dist. | Name of PIU | Phase | Package No. | Completion date (dd-mm-yyyy) | Maintenance start date (dd-mm-yyyy) | Completed Roads under Five Year Maintenance |  | Maintenance Funding and Expenditure during the last financial year (upto 31.03.10) |  | Maintenance Funding and Expenditure during the current financial year ( 2010-2011) Rs. .in LAKH |  |  | Amount to be paid as per contract provision during next financial year 2011-12 | Maintenance ongoing /completed (Yes / No)
[7 empty] | Name of road | Length | Funds Required (in Lakhs) as per contract provision upto 31.03.10 | Expenditure (in Lakhs) upto 31.03.10 | Funds Required for the current year as per contract provision i.e. for 2010-11 | cumulative Expenditure upto last month (for current financial year 2010-11) | cumulative Expenditure upto this month (for current financial year 2010-11)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
| Note :- | 1) Information to be submitted in Excel format only
2) No addition/reduction in col. Should be made
3) Expenditure should be in lacs only.
4) In case of NIL entry zero entry should be made
5) In column no. 1, entered only road no. (like example) it will remain fixed for road name.
6) Column no. 9 & 14 should be in date format only.

## 7b
Progress of Maintenance Work for the Month of
MPR-II(Maintenance)
(Post five years roads)
[12 empty] | Part -I |  |  |  | Part-II |  |  | Part-III |  |  |  | Part-IV
Name of District | Name of PIU | Road no. | Const pkg No. | Maint Pkg No | Name of road | Length of road | PAC for MTN Pkgs | Tender Percentage (only in figure) | Name of Cont. | Date of work order (dd-mm-yyyy) | Total Cumulative amount paid during last financial year | Total Amt of Part-I (as per contract) | cumulative Amount paid upto last month | cumulative Amount paid upto current month | Date of completion of part-I (dd-mm-yyyy) | Total Amount for part II (as per contract) | cumulative Amount paid upto last month | cumulative Amountpaid upto current month | Target Length to be renewed | Achieved Length renewed | cumulative Amount paid upto last month | cumulative Amount paid upto current month | Total Amount for Part IV (as per contract) | Fin. (amount paid during the month) | Total amount paid for Part-IV | Upto date total amount paid for Part-I+II+III+IV
[13 empty] | Payment made |  |  | Pay. Which was due to be paid | Payment made |  |  |  | Payment made
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  | 101 |  | MTN-001 |  |  |  | -5.2 |  | 2010-03-13 |  |  |  |  | 2010-07-10
|  | 102 |  | MTN-001 |  |  |  | 5.2 |  | 2010-03-13 |  |  |  |  | 2010-05-02
|  | 103 |  | MTN-001 | [5 empty] | 2010-03-13 |  |  |  |  | 2010-08-06
|  | 201 |  | MTN-002 | [5 empty] | 2010-05-18 |  |  |  |  | 2010-08-20
|  | 202 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 203 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 204 |  | MTN-002 | [5 empty] | 2010-05-18
|  | 301 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 302 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 303 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 304 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 305 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 306 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 307 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 308 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 309 |  | MTN-003 | [5 empty] | 2010-06-20
|  | 310 |  | MTN-003 | [5 empty] | 2010-06-20
| Note :- | 1: 1) Information to be submitted in Excel format only
2) No addition/reduction in col. Should be made
3) Expenditure should be in lacs only.
4) In case of NIL entry zero entry should be made
5) In column no. 1, entered only road no. (like example) it will remain fixed for road name.
6) Column no. 9 & 14 should be in date format only.

## Ag 7 c
Agenda | 7 c
Remaining packages for tendering for maintenance - upto Jan-2011
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Packages which are becoming due for maintenance after 5 year guarantee period - Due in Jun 10 / Dec 10 / Jun 11/ Dec 11 (Specify) | Phase / Batch of contruction package | Const pkg No. MP- | Name of Roads in the Package | Length of road | Date of completion of package | Expiry date of guarantee period | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12

## Ag 8
Agenda | 8
Complaince on NQM reports & ATRs
S.No | District | Name of PIU | Name of NQM | Date of Inspection | Name of Road | SRI / U | Main issues in the road for SRI/ U grade | ATR - in brief | Latest position of ATR | Ref. no & date of sending ATR to Head Office Bhopal
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11

## Ag 9
Agenda | 9
Quality issues
ONLY FOR DISCUSSION

## Ag 10
Agenda |  | 10
ATR of Inspection of CEO/E-in-C/CGM
Inspections made from June 09 till date
Sno | District | PIU | Inspection made by CEO/ E in C/ CGM | Date of inspection | Name of Road inspected | Package no | Name of Consultant | Name of contractor | Name of Am/Sub engineer incharge | Points in inspection report needed ATR, in very very short | Status of ATR - Compliance done Yes/ No | ATR report sent to HO vide no | Date | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Ag 11
Agenda |  | 11
ATR of Divisional meeting
Sno | District | PIU | Meeting of division | Date of meeting | Points for followup in brief | Status of ATR of points | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8

## Ag 12
Agenda |  | 12
Recovery of amount in terminated packages
Length in Kms & Cost in Rs Lakhs
S.no. | CGM | District | PIU | Phase/ Batch | Package No. | Name of Contractor | Date of termination of contract | Total Amount to be recovered in Rs. Lakhs |  |  |  |  | Amount of SD of the contractor has been forfeited-Yes/No | If col. 14 is No, Reason thereof in very brief | Amount available in SD and other deposit/ final bill | [5 empty] | Balance to be recovered from contractor (13-21) | Action taken for recovery | Total amount available with the department | LD has been decided from HO-Yes/No | Remarks
[8 empty] | Negative bill amount | Liquidated Damage (LD) amount | Extra Cost | Other (specify details) | Total (9+10+11+12) |  |  | Performance / SD | Other deposit | Forfeit amount | Withheld amount | Other | Total (Col 16+17+18+19+20)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26

## Ag 13
Agenda |  | 13
Information of verification of Bank Guarantees
Length in Kms & Cost in Rs Lakhs
S.No. | CGM | Name of District | Name of PIU | Package No. | Name Of Contractor | Purpose of bank guarantee in brief | Latest B.G.No | Date | Amount in Rs Lakhs | Validity date of BG | Name of the Bank & Branch | Place | Verification status | Remark
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Ag 14
Agenda |  | 14
Review of Administrative Expenditure
Length in Kms & Cost in Rs Lakhs
S.No. | CGM | Name of District | Name of PIU | During 09-10 |  |  |  |  | During Apr-2010 to Jan-2011 |  |  |  |  | Remark
|  |  |  | Expenditure incurred on pay & allowances | Expenditure incurred on vehicle | Expenditure incurred on Stationery & office contingency | Expenditure incurred on consultancy | Expenditure incurred on misc items | Expenditure incurred on pay & allowances | Expenditure incurred on vehicle | Expenditure incurred on Stationery & office contingency | Expenditure incurred on consultancy | Expenditure incurred on misc items
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Ag 15
Agenda | 15
Review of submission of QPR, MPR
Information Not Required from PIUs

## Ag 16
Agenda | 16
Review of Departmental Enquiry
Information Required from CGMs only.

## Ag 17 a
Additional Agenda No |  |  |  | a
Roadwise Review of ADB Batch V & LWE Works
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Name of road | Total |  |  | Design/Drawing of road work given to contractor - Yes/ No | Design/Drawing of structures given to contractor - Yes/ No | Setting out work completed - Yes/ No | Physical Status- Approx. work executed in Kms / nos | [6 empty] | Expenditure made in the last month | Total expenditure upto the reporting month Jan-2011 | Work done in last 4 Months Rs in Lakhs | Target for completion Month/Year | Remarks
[12 empty] | Length | No of structures | Total Cost |  |  |  | E/W | GSB | G-2 | G-3 | BT | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | [6 empty] | 20 | 21 | 22 | 23 | 24

## Ag 17 b
Additional Agenda No |  |  |  | b
Position of OGL submission of ADB Batch V & LWE Works
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Name of road | Total |  | OGL recorded |  |  |  | Remarks
[12 empty] | Length | Cost | length of which OGL completed in Kms | Date of sumission of soft copy to HQ | soft copy uploaded in email oglrrda@rediffmail.com Yes/ No | If OGL not recorded, give reasons in brief
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19

## Ag 17 c
Additional Agenda No |  |  |  | c
Forward Planning of ADB batch V & LWE works
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Name of road | Total |  | Forest case |  |  |  | Mining case |  |  | Electric pole shifting cases |  |  | Private land case |  | Any other issue related to obstruction in road construction | Remarks
[12 empty] | Length | Cost | Length affected by forest | Case submitted to Forest authority - Yes/ No | Permission obtained for no of case | Status of case | No of cases submitted to collector | No for which sanctions received | Problem if any state in brief | No of poles identified for shifting | Agency fixed for the work Yes/No | If not, reason in brief | No of cases of private land | Status of cases
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28

## Ag 17 d
Additional Agenda No |  |  |  | d
Status of contractor's lab in ADB Batch V & LWE Works
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Field Lab established by contractor |  |  |  | Remarks
[11 empty] | Yes/No | If yes, name the place where lab situated | All necessary testing equipments available Yes/ No | Lab functioning - Yes/No
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16

## Ag 18
Agenda Point-11
Updated information As on 31-01-2011 | [16 empty] | E-1
Proforma E-1 for PIUs Establishment Information
S no | CGM | Name of District | PIU | Post | Name | Category Gen/SC/ ST/OBC | Home District | Parent Department | Post held in Parent Deptt. | Date since when working in MPRRDA | Date since when working in the PIU | Date of Renewal (Contract Post) | Date of Birth | Date of Retirement | Present Pay Scale/ Samvida Pay | Present Basic Pay/ Samvida pay | If worked in any other PIU, name of PIU/Distt | Mobil No./Phone No. | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
uksV % tkudkjh vxzsth QksaV ¼time new roman½ esa gkMZ dkih ,oa lk¶V dkih esa nsa] rFkka bZ esy& ¼mamprrda@rediffmail.com) ij HkstsaaA
1- Give information for all employees- Deputation /Contract /Other- including transferred but not relieved.
2- Send this information ONLY by e-mail : NO HARD COPY Required
3- Information ONLY in MS excel with Arial 12 fonts.
QkjesV Hkjus ds fy, funsZ'k &
1- lHkh deZpkjh & izfrfu;qDr@ lafonk@vU; dh tkudkjh nsaA ,sls deZpkjh Hkh tks LFkkukUrfjr gks x, fdUrq HkkjeqDr ugha gq, mUgsa Hkh 'kkfey djsa rFkk fjekdZ esa fy[ksa HkhA
2- tkudkjh dsoy vaxzsth rFkk ,Dlsy esa gksuh pkfg,A
NO HARD COPY Required

## Ag 19
E-2
Incumbency Statement of GM/AO/AM/Sub Engineer/DM/ADM/Clerk/DEO
Since start of PIU Till date (ih-vkbZ-;w- ds izkjaHk ls vkt rd)
Updated information As on
S. No. | CGM | Name of District | PIU | Post | Name | Date |  | Parent Deptt. | Remarks
[6 empty] | From | To
1
2
3
4
5
6
7
8
uksV % tkudkjh vxzsth QksaV ¼time new roman½ esa gkMZ dkih ,oa lk¶V dkih esa nsa] rFkk bZ esy&(mamprrda@rediffmail.com) ij HkstsaaA

## Agenda2 (hidden)
Agenda No |  | 2
Roadwise Review of Incomplete Roads of PMGSY Phase -III, IV, V, VI & ADB Batch I, II, III, IV
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Name of road | Total |  | Balance |  | Physical Status- Approx. balance work in Kms / nos | [6 empty] | Expenditure made in the last month | Total expenditure upto the reporting month | Work done in last 4 Months Rs in Lakhs | Reason in brief for not completing | Target date of completion Apr/ May/ Jun / Jul/Aug/Sep/Oct/Nov/Dec/Jan/Feb/Mar | Remarks
[12 empty] | Length | Cost | Length | Cost | E/W | GSB | G-2 | G-3 | BT | CC road | CD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | [6 empty] | 18 | 19 | 20 | 21 | 22 | 23

## Agenda3 (hidden)
Agenda No |  | 3
Packagewise Program for construction of Incomplete Roads of PMGSY Phase -VII, VIII,IX,X, ADB Batch V & LWE works
Length in Kms & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Phase/ Batch | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Total |  | Balance |  | Physical Status- Approx. balance work in Kms / nos | [6 empty] | Schedule Date of Completion | Target date of completion | Monthwise programme for completion (Rs in Lakhs) | [11 empty] | Monthwise programme for completion (Length in Kms) | [11 empty] | Remarks
[13 empty] | Length | Cost | Length | Cost | E/W | GSB | G-2 | G-3 | BT | CC road | CD |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 15 | 16 | 17 | 18 | 19 | [6 empty] | 20 | 21 | Monthwise programme for completion (Rs in Lakhs) Apr: 22; Monthwise programme for completion (Length in Kms) Apr: 23 | 24

## Agenda 4 (hidden)
Agenda No |  | 4
Progress of Bridges under construction
Length in Meters & Cost in Rs Lakhs
S.N. | CGM (I,II,III or IV) | District | PIU Name | Block | Name of packages | Name of Contractor | Incharge AM/Sub Engineer | Date of agreement | Date of work order | Date of establishment of laboratory by contractor | Date of providing layout, DPR, drawings and working design to contractor by GM/Consultant | Total |  |  |  | Approx. balance work in Mts / nos/Lakhs |  |  |  | Schedule Date of Completion | Target date of completion | Quarterly programme for completion (Only Rs in Lakhs) |  |  |  | Remarks
[12 empty] | Length of both approaches | No of Spans | No of Piers | Cost | Length of both approaches | No of Spans | No of Piers | Cost |  |  | Apr to Jun | Jul to Sep | Oct to Dec | Jan to Mar
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |  |  | 14 |  |  |  | 15 | 16 | 17 |  |  |  | 18

## Agenda 5 (hidden)
Agenda 5
Review of Status of Payment of Final Bills for the completed packages
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Sanctioned Amount | Expenditure Made (Up to the month) | Date of WO | Date of Completion | Date of issue Completion Certificate by the Consultant | Date of Final Payment Made by GM | Date of Verification by GM | Delay in months in final payment
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Agenda 6 (hidden)
Agenda 6
Review of un-awarded packages: including balance works of all phases/ batches but excluding maintenance work
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Sanctioned Amount | Expenditure Made (Up to Mar 10) | Amount of balance work | No fo calls (for tender) | NIT issued yes / no | If Yes then date of opening of bid | If No, then reason for non issuing of NIT | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Agenda 7 a (hidden)
Agenda 7 (a)
Maintenance works : Roadwise Expenditure for packages within 5 years ie. Under performance guarantee
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | Name of Road | Length | Date of work order | Date of completion | Payment made for maintenance during last year 2008-09 | Payment made to the contractor for maintenance as per agreement |  |  | Present Condition of Road ( Satisfactory/ Requires maintenance / Unsatisfactory) | Name of incharge AM / Sub Engineer | Remarks
[11 empty] | upto previous month | During the month | Cummulative
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17

## Agenda 7 b (hidden)
Agenda 7 (b)
Maintenance works : Roadwise Expenditure for packages beyond 5 years.
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages | Name of Road | Length | Date of completion | Agency fixed Yes/ No | If Agency fixed then |  |  |  |  | If No Agency fixed then |  | Name of incharge AM / Sub Engineer | Remarks
[10 empty] | Name of contractor | Date of work order | Work done till Mar 10 in brief | Approx. cost of work done for maintenance | Present Condition of Road | NIT issued Yes/ No | Present Condition of Road
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19

## Agenda 7 c (hidden)
Agenda 7 C
Review of un-awarded tenders of maintenance work
Length in Kms & Cost in Rs Lakhs
S. No. | CGM | Name of District | Name of PIU | Phase / Batch | Name of Packages MP- | No of Roads in the Package | Date of completion of package | Sanctioned Amount of maintenace | Expenditure Made (Up to Mar 10) | Amount of balance work | No fo calls (for tender) | NIT issued yes / no | If Yes then date of opening of bid | If No, then reason for non issuing of NIT | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16