## RIS-1
R I S - 1
M.P. Rural Road Development Authority
Project Implemantation Unit ………………..
Road wise Inspection Status NQM/SQM
Month :- August 2010
SN | Name of PIU's | Name of Block | Package No. | Name of Road | Actual Length | Date of Work order (dd/mm/yy) | Total physical work done in % | Date of Competition ( if completed) | Amount paid (Lakh) | Inspection Status
[10 empty] | Date of Inspection (dd/mm/yy) |  |  | Name of |  | Grade given
[10 empty] | Earth work/ Subgra-de | GSB/G-2 /G-3 | BT/ CC | NQM | SQM
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Sidhi-3 | Rampur Naikin | MP-4194 | Maura to Magrohar (Bamhani-Magrohar Road) | 7.55 | 2008-06-23 | 59 | 144.14 | 144.14 | E/W , GSB Culv. |  |  |  | Shri A.K. Sharma | S
[11 empty] | G-2 & CD |  |  | Shri S.K. Shukla | S
[11 empty] | G-2, G-3 and CD |  |  | Shri J.N. Purohit | S
[11 empty] | G-3 in Progress |  |  | Shri P.C. Mathur | S
2 | Sidhi-3 | Rampur Naikin | MP-4194 | NH-75 to Amarwah via Naugawa Dhir Singh | 6.4 | 2008-06-23 | 61 | 136.3 | 136.3 | E/W, GSB, Culv. |  |  |  | Shri A.K. Sharma | S
[11 empty] | G-2 & CD |  |  | Shri K.K. Choubey | S
[11 empty] | G-3 in Progress |  | Shri Gokharan Singh |  | U
3 | Sidhi-3 | Rampur Naikin | MP-41108 | Semariya-Posta Road | 15.3 | 2008-09-24 | 99 | 363.21 | 363.31 | E/W & CD |  |  |  | Shri R.K. Agrawal
[11 empty] | G-2 & CD |  |  | Shri K.K. Choubey | S
[11 empty] | G-3 in Progress |  |  | Shri P.C. Mathur | S
[12 empty] | B.T. Completed |  | Shri S.Lal | S
4 | Sidhi-3 | Rampur Naikin | MP-41109 | Hattha-Shikarganj Chamaradol Road | 19.1 | 2008-10-08 | 97 | 444.36 | 444.36 | E/W |  |  |  | Shri A.K. Sharma | S
[11 empty] | G-2 & CD |  |  | Shri S.K. Shukla | S
[11 empty] | G-2, G-3 and CD |  |  | Shri J.N. Purohit | S
[11 empty] | G-2, G-3 & B.T. |  |  | Shri P.C. Mathur | S
[12 empty] | B.T. Completed |  | Shri S.Lal | S
[12 empty] | B.T. Completed |  | Shri S.P. Singh | S
5 | Sidhi-3 | Rampur Naikin | MP-41110 | Khaira-Chandreh Shikarganj Road | 15.57 | 2008-09-24 | 98 | 374.7 | 374.7 | E/W, Culv. |  |  |  | Shri A.K. Sharma | S
[11 empty] | G-3 |  |  | Shri S.A. Sharma | S
[12 empty] | B.T. Completed |  | Shri S.P. Singh | S
6 | Sidhi-3 | Rampur Naikin | MP-41111 | Semariya Kushmahar Mata Road | 19.6 | 2008-12-16 | 37 | 300.94 | 300.94 | E/W |  |  |  | Shri S.Lal | S
[11 empty] | GSB & G-2 |  |  | Shri L.K.Jain | S
[11 empty] | GSB, G-2, G-3 |  |  | Shri S.P. Singh | S
7 | Sidhi-3 | Rampur Naikin | MP-41112 | Amarpur to Mohaniya | 11.26 | 2008-10-13 | 30 | 77.68 | 77.68 | E/W |  |  | Shri Prahlad Das |  | S
[11 empty] | GSB & CD in Progress |  |  | Shri P.C. Mathur | S
8 | Sidhi-3 | Rampur Naikin | MP-41112 | Kuwa to Badkhara 734 | 6.05 | 2008-10-13 | 28 | 57.11 | 57.11 | E/W |  |  |  | Shri S.Lal | S
[10 empty] | E/W | GSB in Progress |  |  | Shri P.C. Mathur | S
9 | Sidhi-3 | Rampur Naikin | MP-41113 | Rampur to Gaddi Rewa Road | 13 | 2008-09-24 | 58 | 189.43 | 189.43 | E/W |  |  |  | Shri K.K. Chapra | S
[11 empty] | G-2 & CD |  |  | Shri S.K. Shukla | S
[11 empty] | G-2,G-3 & CD |  |  | Shri J.N. Purohit | S
10 | Sidhi-3 | Rampur Naikin | MP-41114 | Rampur-Gaddi Road to Ghatokhar | 6.6 | 2009-02-16 | 65 | 106.24 | 106.24 |  | GSB |  |  | Shri S.Lal | S
[11 empty] | G-2 in Progress |  |  | Shri S.A. Sharma | S
[12 empty] | BT |  | Shri K.S. Vilku | S
11 | Sidhi-3 | Rampur Naikin | MP-41115 | SH-52 to Naikin | 7.8 | 2008-09-24 | 64 | 120.83 | 120.83 | E/W |  |  |  | Shri K.K. Chapra | S
[11 empty] | G-3 in Progress |  | Shri S.k. Sharma & B.K. Baghmare
[11 empty] | G-3 in Progress |  |  | Shri P.C. Mathur | S
12 | Sidhi-3 | Rampur Naikin | MP-41115 | Baghwar to Godhatola | 7.4 | 2008-09-24 | 32 | 34 | 33.83 | E/W |  |  |  | Shri S.Lal | S
[11 empty] | G-2 in Progress |  |  | Shri S.A. Sharma | S
[11 empty] | G-2, G-3 |  |  | Shri K.S. Vilku | S
13 | Sidhi-3 | Rampur Naikin | MP-41116 | NH-75 to Hanumangarh | 10.2 | 2008-10-10 | 57 | 161.85 | 161.85 | E/W |  |  |  | Shri S.R. Sahu | S
[11 empty] | G-2 in Progress |  |  | Shri S.A. Sharma | S
[12 empty] | BT |  | Shri K.S. Vilku | S
14 | Sidhi-3 | Rampur Naikin | MP-41117 | Gedura to Madwa | 5.63 | 2008-09-16 | 92 | 143.81 | 143.81 | E/W, Culv. |  |  |  | Shri R.K. Agrawal | S
[11 empty] | G-2 & CD |  |  | Shri K.K. Choubey | S
15 | Sidhi-3 | Rampur Naikin | MP-41117 | Beldah to Gaurdah-Posta | 6.63 | 2008-09-16 | 96 | 155.74 | 155.74 | E/W, Culv. |  |  |  | Shri R.K. Agrawal
[11 empty] | G-2 |  |  | Shri S. Lal | S
[11 empty] | G-3 in Progress |  |  | Shri L.K.Jain | S
[12 empty] | B.T. Completed |  | Shri S.Lal | S
16 | Sidhi-3 | Rampur Naikin | MP-41118 | NH-75 to Kapuri-Parkhuri | 8.3 | 2008-09-16 | 99 | 151 | 151 | E/W, Culv. |  |  |  | Shri A.K. Sharma | S
[11 empty] | G-3 in Progress |  |  | Shri A.K. Sharma | S
[12 empty] | BT |  | Shri K.S. Vilku | S
17 | Sidhi-3 | Rampur Naikin | MP-41119 | Chakdour to Ahirantola | 4.3 | 2008-09-24 | 97 | 106.56 | 106.56 | E/W, Culv. |  |  |  | Shri A.K. Sharma | S
[11 empty] | G-3 in Progress |  |  | Shri A.K. Sharma | S
[12 empty] | B.T. Completed |  | Shri S.Lal | S
[12 empty] | Completed |  | Shri S.P. Singh | S
18 | Sidhi-3 | Rampur Naikin | MP-41120 | Khaddi to Badesar | 6.2 | 2008-10-10 | 48 | 100.92 | 100.92 |  | GSB |  |  | Shri S. Lal | S
[11 empty] | G-3, CD in Progress |  |  | Shri J.N. Purohit | S
19 | Sidhi-3 | Rampur Naikin | MP-41121 | Dhanaha to Jamuniha | 8.815 | 2008-10-13 | 51 | 138.77 | 138.77 | E/W |  |  |  | Shri S.R.Sahu | S
[11 empty] | GSB & G-2 in Progress |  |  | Shri L.K.Jain | S
20 | Sidhi-3 | Rampur Naikin | MP-41122 | SH-52 to Gopalpur-Kudiya | 7.2 | 2008-09-24 | 32 | 54.05 | 54.05 | E/W |  |  |  | Shri A.K. Sharma | S
[11 empty] | GSB, CD in Progress |  |  | Shri A.K. Sharma | S
21 | Sidhi-3 | Rampur Naikin | MP-41123 | Padkhuri 587 to Padkhuri 588 | 3.6 | 2008-09-16 | 86 | 61.16 | 61.16 | E/W, Culv. |  |  |  | Shri A.K. Sharma | S
[11 empty] | G-2 |  |  | Shri S.K. Shukla | S
[11 empty] | G-3 in Progress |  |  | Shri J.N. Purohit | S
22 | Sidhi-3 | Rampur Naikin | MP-41124 | SH-52 to Ghunghuta | 8.6 | 2008-10-08 | 100 | 151.22 | 151.22 | E/W & GSB |  |  |  | Shri K.K. Chapra | S
[11 empty] | G-3, BT in Progress |  |  | Shri J.N. Purohit | S
[12 empty] | B.T. in Progress |  | Shri P.C. Mathur | S
23 | Sidhi-3 | Rampur Naikin | MP-41124 | Agdal to Bardaila | 5.4 | 2008-10-08 | 56 | 69.04 | 69.04 | E/W |  |  |  | Shri K.K. Chapra | S
[11 empty] | GSB, G2 in Progress |  |  | Shri L.K.Jain | S
24 | Sidhi-3 | Rampur Naikin | MP-41125 | SH-52 to Badokhar | 5.45 | 2008-10-08 | 88 | 94.08 | 94.08 | E/W |  |  |  | Shri S.R.Sahu | S
[11 empty] | G-2, G-3- in Progress |  |  | Shri L.K.Jain | S
[12 empty] | BT |  | Shri K.S. Vilku | SRI
25 | Sidhi-3 | Rampur Naikin | MP-41125 | SH-52 to Chadainiya Badokhar | 5.2 | 2008-10-08 | 60 | 69.23 | 69.23 | E/W |  |  |  | Shri S. Lal | S
[11 empty] | GSB & CD in Progress |  |  | Shri A.K. Sharma | S
[11 empty] | G-3 |  |  | Shri K.S. Vilku | S
26 | Sidhi-3 | Rampur Naikin | MP-41 B02 | Construction of Bridge across Ghugnuri Nallha on Katouli-Mamder-Gaddi Road | 0.17 | 2008-09-02 | 90.86 | 82.42 | 82.42 | Foundation |  |  |  | Shri A.K. Sharma | S
[10 empty] | Bottom raft |  |  |  | Shri S.R. Sahu | S
1 | Sheopur | Vijaypur | MP-3711 | Moreka to Tarra Kala | 8 | 30.04.08 | 43.42% |  | 86.52 | 11.12.08 |  |  |  | Shri M.L. Gupta | S
[11 empty] | 20.09.09 |  | Shri Baljeet singh Rajpal |  | SRI
[11 empty] | 20.11.09 |  |  | Shri J.N. Purohit | S
[12 empty] | 27.01.10 |  | Shri P.C. Mathur | S
General Manager
M.P. Rural Road Development Authority,
PIU ……………………….
SAMPLE ONLY