## Final Tgt Achieve
Target and Achievement upto 31.01 2011
S.No. | CGM | Name of PIU | Balance Work As per 31.4.2010 (revised as per MPR1) |  | Achievement till Jan-11 |  | Balance length as on 31 Jan 11 (as per MPR1) | BT + CC till Jan 11 achieve for ongoing work | Planing for Next Two month |  | Committed by Gm in Meeting (km)
|  |  | Physical Length in Km | Financial Rs. In Lakh | Expenditure In Lakh | Length of Road completed In Km |  |  | Expenditure In Lakh | Length of Road completed In Km
1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 3 | Alirajpur-1 | 163.448 | 3045 | 1334.78 | 77.45 | 85.998 | 27.283 | 270 | 36 | 28
2 | 3 | Alirajpur-2 | 242.595 | 5944 | 1845.74 | 56.76 | 185.835 | 30.145 | 685 | 48 | 48
3 | 4 | Anuppur | 144.81 | 1693 | 1312.33 | 39.85 | 104.96 | 70.829 | 204.69 | 10.852 | 10.852
4 | 2 | Ashoknagar | 78.87 | 1919 | 474.95 | 20.15 | 58.72 | 15.783 | 250 | 20.3 | 20.3
5 | 4 | Balaghat-04 | 54.1 | 1198 | 156.08 | 0 | 54.1 | 7.364 | 120 | 14.75 | 15
6 | 4 | Balaghat1 | 287.625 | 6317 | 1824.16 | 71.18 | 216.445 | 26.366 | 703 | 107.1 | 107.1
7 | 4 | Balaghat2 | 272.33 | 6404 | 2176.85 | 29.13 | 243.2 | 23.841 | 800 | 108.92 | 85
8 | 4 | Balaghat-3 | 220.16 | 4578 | 1564.42 | 27 | 193.16 | 35.864 | 900 | 65 | 65
9 | 3 | Barwani-1 | 191.455 | 3995 | 813.61 | 50.29 | 141.165 | 35.557 | 412 | 25.04 | 25.04
10 | E-in-c | Betul-1 | 122.23 | 3226 | 1421.04 | 56.26 | 65.97 | 32.967 | 600 | 45.33 | 45.33
11 | E-in-c | Betul-2 | 231.47 | 4162 | 2017.81 | 92.55 | 138.92 | 35.89 | 550 | 78.96 | 22
12 | E-in-c | Betul-3 | 103.25 | 2998 | 813.76 | 37 | 66.25 | 2.08 | 350 | 18 | 18
13 | 2 | Bhind | 326.035 | 3229 | 1686 | 175 | 151.035 | 33.131 | 650 | 53 | 53
14 | E-in-c | Bhopal | 88.525 | 1889 | 1106.42 | 42.1 | 46.425 | 25.283 | 600 | 48.02 | 48.02
15 | 3 | Burhanpur-1 | 183.43 | 3700 | 1618.33 | 51.7 | 131.73 | 9.451 | 1000 | 65 | 65
16 | 3 | Burhanpur-2 | 104.665 | 3427 | 216.61 | 12.7 | 91.965 | 13.399 | 550 | 65.74 | 65.74
17 | 2 | Chhatarpur | 318.829 | 3953 | 1501.8 | 125.5 | 193.329 | 62.184 | 210 | 12.1 | 12.1
18 | 4 | Chhindwara-1 | 140.945 | 5183 | 465.13 | 19 | 121.945 | 16.562 | 400 | 16.15 | 36
19 | 4 | Chhindwara-2 | 235.875 | 4977 | 833.81 | 65.7 | 170.175 | 31.679 | 475 | 41.81 | 41.81
20 | 4 | Chhindwara-3 | 219.245 | 4975 | 741.99 | 44.74 | 174.505 | 17.919 | 450 | 19 | 19
21 | 4 | Chhindwara4 | 79.12 | 3700 | 774.8 | 24.58 | 54.54 | 7.15 | 300 | 7 | 7
22 | 4 | Chhindwara-5 | 166.515 | 1393.7 | 446.92 | 20.93 | 145.585 | 1.796 | 470 | 13.05 | 13.05
23 | 2 | Damoh | 61.65 | 1219 | 507.4 | 35.45 | 26.2 | 16.45 | 190.55 | 5.17 | 5.17
24 | 2 | Datia | 259.677 | 2833 | 1298.94 | 31.35 | 228.327 | 298.952 | 1250 | 75 | 80
25 | 1 | Dewas | 224.2 | 2928 | 1456.58 | 89.85 | 134.35 | 70.411 | 571.25 | 39 | 39
26 | 3 | Dhar-1 | 285.2 | 7372 | 2245.24 | 89.15 | 196.05 | 39.8688 | 930 | 111.3 | 111.3
27 | 3 | Dhar-3 | 149.665 | 3483 | 1622.1 | 54.09 | 95.575 | 47.553 | 600 | 25 | 25
28 | 3 | Dhar-4 | 226.33 | 4877 | 2091.28 | 74.56 | 151.77 | 45.023 | 600 | 28 | 28
29 | 4 | Dindori01 | 247.835 | 5490 | 1911.72 | 106.69 | 141.145 | 64.383 | 750 | 60.5 | 60.5
30 | 4 | Dindori-02 | 151.46 | 2801 | 1245.73 | 44.8 | 106.66 | 42.485 | 720 | 60 | 60
31 | 2 | Guna | 81 | 598 | 473.76 | 16.3 | 64.7 | 36.205 | 148 | 13.79 | 12
32 | 2 | Gwalior | 250.732 | 3138 | 1048.42 | 19.33 | 231.402 | 85.947 | 230 | 26.2 | 26.2
33 | E-in-c | Harda | 306.375 | 5523 | 1439.94 | 82.11 | 224.265 | 65.722 | 710 | 53 | 53
34 | E-in-c | Hoshangabad | 198.16 | 5945 | 1446.42 | 28.25 | 169.91 | 24.098 | 829.38 | 49.52 | 50
35 | 3 | Indore | 128.558 | 2203 | 935.15 | 44.834 | 83.724 | 33.3745 | 270 | 12.659 | 13
36 | 4 | Jabalpur | 109.275 | 2752 | 1269.8 | 45 | 64.275 | 21.545 | 400 | 15 | 15
37 | 3 | Jhabua-1 | 221.785 | 3828 | 2042.55 | 137.02 | 84.765 | 51.4168 | 620 | 87.78 | 87.78
38 | 3 | Jhabua-2 | 283.28 | 5412 | 1137.0384 | 43.34 | 239.94 | 76.196 | 600 | 30 | 30
39 | 3 | Jhabua-3 | 95.54 | 3737 | 1440.23 | 56.5 | 39.04 | 6.3 | 945 | 23.3 | 23.3
40 | 4 | Katni | 121.527 | 2148 | 553.33 | 42 | 79.527 | 29.757 | 400 | 25.23 | 22
41 | 3 | Khandwa-1 | 377.55 | 5160 | 1287.84 | 87.43 | 290.12 | 178.158 | 627 | 28.95 | 28.95
42 | 3 | Khandwa-2 | 247.59 | 5013 | 1777.22 | 58.09 | 189.5 | 51.22 | 1000 | 96 | 80
43 | 3 | Khandwa-3 | 25 | 1483 | 786.41 | 25 |  |  | 160 | 13.6 | 13.6
44 | 3 | Khargone-1 | 221.695 | 4411 | 1335.89 | 58.21 | 163.485 | 36.7165 | 1208.03 | 60.26 | 60
45 | 3 | Khargone2 | 157.232 | 3043 | 1359.67 | 90.43 | 66.802 | 18.8 | 954 | 61.82 | 61.82
46 | 3 | Khargone3 | 249.523 | 6598 | 1462.25 | 33.4 | 216.123 | 6.44 | 1200 | 138.24 | 104
47 | 3 | Khargone-Barwah | 130.455 | 3057 | 1095.764 | 47.91 | 82.545 | 13.631 | 731 | 39.178 | 39.178
48 | 3 | Kukshi | 86.17 | 1718 | 691.22 | 40.06 | 46.11 | 23.17 | 450 | 27.93 | 27.93
49 | 3 | Maheshwar | 261.415 | 4254 | 2136.05 | 94.29 | 167.125 | 79.247 | 893 | 52 | 200
50 | 4 | Mandla | 177.65 | 3338 | 500 | 37.475 | 140.175 | 16.29 | 300 | 23.31 | 18
51 | 1 | Mandsaur | 96.91 | 699 | 641.1 | 38.41 | 58.5 | 47.739 | 92.43 | 0.495 | 0.495
52 | 4 | Mauganj | 225.6 | 3595 | 646.09 | 31.4 | 194.2 | 54.7086 | 650.38 | 72.55 | 72.55
53 | 2 | Morena02 | 127.83 | 3013 | 1141 | 23.8 | 104.03 | 10.48 | 500 | 29 | 80
54 | 2 | Morena-1 | 215.76 | 3322 | 1011 | 10.51 | 205.25 | 51.15 | 863 | 99.6 | 100
55 | 4 | Narsinghpur1 | 95.65 | 2291 | 1216.69 | 42.4 | 53.25 | 8.076 | 276 | 19.45 | 19.45
56 | 4 | Narsinghpur-2 | 168.42 | 3705 | 1174.68 | 32.8 | 135.62 | 21.199 | 800 | 84 | 42
57 | 1 | neenuch | 36 | 1093 | 781 | 36 | 0 | 0 | 0 | 0 | 0
58 | 2 | Panna | 204.35 | 5230 | 1389.7 | 15 | 189.35 | 71.099 | 1438.28 | 66.46 | 66.46
59 | 2 | Pawai | 221.57 | 3377 | 826.96 | 62.22 | 159.35 | 38.782 | 1675.71 | 61.53 | 61.53
60 | E-in-c | Raisen-1 | 75.885 | 1861 | 778.91 | 15.23 | 60.655 | 6.3025 | 135 | 26.85 | 8
61 | E-in-c | Raisen-2 | 155.595 | 3350 | 252.2 | 9.53 | 146.065 | 28.709 | 150 | 8 | 8
62 | E-in-c | Rajgarh-1 | 234.715 | 5180 | 1900.19 | 11.815 | 222.9 | 0.90004 | 1095 | 78 | 60
63 | E-in-c | Rajgarh-2 | 207.25 | 4515 | 994.58 | 30.1 | 177.15 | 22.131 | 985 | 69.35 | 69.35
64 | 1 | Ratlam | 240.271 | 4920 | 2586.17 | 85.25 | 155.021 | 70.015 | 1000 | 41.36 | 41.36
65 | 4 | Rewa-1 | 268.5 | 4582 | 1558.34 | 127.3 | 141.2 | 36.803 | 653.34 | 40.85 | 40.85
66 | 4 | Rewa-2 | 285.75 | 4622 | 614.33 | 49 | 236.75 | 101.43 | 180 | 16 | 20
67 | 2 | Sagar-1 | 204.275 | 5465 | 603.04 | 25.4 | 178.875 | 15.59 | 450 | 11.35 | 11.35
68 | 2 | Sagar-2 | 238.2 | 6283 | 327.2 | 13.8 | 224.4 | 26.47 | 550 | 19.5 | 85
69 | 4 | Satna-1 | 246.735 | 3009 | 1095.21 | 108.67 | 138.065 | 39.943 | 426 | 37.355 | 46
70 | 4 | Satna-2 | 197.095 | 2898 | 1259.26 | 50.45 | 146.645 | 37.674 | 410 | 47.26 | 47.26
71 | E-in-c | Sehore-2 | 131.29 | 2987 | 1390.86 | 38.79 | 92.5 | 27.7626 | 9 | 44 | 40
72 | E-in-c | Sehore-I | 342.23 | 6968 | 2797.23 | 68 | 274.23 | 42.014 | 850 | 100 | 100
73 | 3 | Sendhwa | 220.95 | 6449 | 1687.53 | 51.96 | 168.99 | 54.448 | 900 | 57.57 | 57.57
74 | 4 | Seoni | 338.285 | 2886 | 1686.05 | 73.47 | 264.815 | 112.7334 | 350 | 40 | 47
75 | 2 | Seopur | 271.25 | 5774.8 | 1018.66 | 54 | 217.25 | 39.337 | 890 | 145.05 | 82
76 | 4 | Shahdol-1 | 143.33 | 3073 | 822.09 | 54.34 | 88.99 | 28.92 | 400 | 67.8 | 68
77 | 4 | Shahdol-2 | 212.13 | 2956 | 663.88 | 80.59 | 131.54 | 50.14 | 450 | 36.36 | 36
78 | 1 | Shajapur | 282.89 | 3732 | 1653.32 | 125.3 | 157.59 | 77.9258 | 360 | 72.45 | 25
79 | 2 | Shivpuri-2 | 310.94 | 5020 | 678.14 | 15.45 | 295.49 | 37.558 | 1250 | 120.88 | 120
80 | 2 | Shivpuri-I | 408.1 | 5000 | 2938.31 | 114.7 | 293.4 | 22.085 | 916 | 48.65 | 48.65
81 | 4 | Sidhi-1 | 216.07 | 3425 | 1130.17 | 43.68 | 172.39 | 53.164 | 400 | 30 | 30
82 | 4 | Sidhi-2 | 425.71 | 3638 | 1605.68 | 77.36 | 348.35 | 183.04 | 600 | 60 | 60
83 | 4 | Sidhi-3 | 233.515 | 3412 | 1048.19 | 44.84 | 188.675 | 85.66 | 443.4 | 36 | 36
84 | 2 | Tikamgarh | 161.26 | 1731 | 777.87 | 67.62 | 93.64 | 35.52 | 700 | 50 | 50
85 | 1 | Ujjain-1 | 229.73 | 3185 | 1304.94 | 62.53 | 167.2 | 42.538 | 550 | 65.97 | 45
86 | 1 | Ujjain-2 | 237.085 | 2385 | 1625.13 | 51.9 | 185.185 | 72.366 | 769 | 64.75 | 64.75
87 | 4 | Umaria | 318.065 | 4981 | 1491.5641 | 84.22 | 233.845 | 53.542 | 725 | 89 | 89
88 | E-in-c | Vidisha | 313.525 | 6776 | 2467.62 | 38.73 | 274.795 | 29.628 | 1400 | 130 | 100
89 | 4 | Waidhan-1 | 311.24 | 3519 | 1081.39 | 92.34 | 218.9 | 8.9487 | 420 | 39.65 | 42
90 | 4 | Waidhan-2 | 148.505 | 2273 | 743.99 | 42.15 | 106.355 | 22.196 | 275 | 19 | 19
|  |  | 18314.517 | 339448.5 | 111155.5465 | 4853.544 | 13460.973 | 3810.6103 | 54224.44 | 4346.949 | 4025